|  |  | CBD |
| --- | --- | --- |
|  | CONVENTION ON BIOLOGICAL DIVERSITY |  | Distr. GENERAL UNEP/CBD/AHTEG-BDCC/2/2 26 September 2002 ORIGINAL: ENGLISH |

AD HOC TECHNICAL EXPERT GROUP ON BIOLOGICAL DIVERSITY AND CLIMATE CHANGE

Second meeting

Montreal, Canada

9-13 September 2002

Report of the second meeting of the Ad Hoc Technical Expert Group on Biological Diversity and Climate Change

The Ad Hoc Technical Expert Group on Biological Diversity and Climate Change held its second meeting at the Secretariat of the Convention on Biological Diversity from 9 to 13 September in Montreal.

# Item 1. 	Opening of the meeting

After a brief statement of welcome by the representative of the Executive Secretary, the two Co-chairs, Ms. Outi Berghäll (Finland) and Dr. Robert Watson (World Bank) opened the meeting on Monday, 9 September 2002, at 9 a.m.

The members of the Group introduced themselves (see list of participants in annex I).

# Item 2. 	Organizational matters

The Group adopted the provisional agenda prepared by the Executive Secretary (UNEP/CBD/AHTEG-BDCC/2/1) and the organization of work of the meeting contained in annex II to the annotated provisional agenda.  It was agreed that most of the work would consist of finalizing the chapters of the two products agreed upon at the first meeting, in small groups and that the Group as a whole would meet as needed, at least once a day, to take stock of the progress.

Item 3: 	Review of relevant decisions of the sixth meeting of the Conference of the parties to the convention on biological diversity

A representative of the Executive Secretary of the Convention recalled the mandate of the Group and drew attention to the decisions of the sixth meeting of the Conference of the Parties to the Convention on Biological Diversity relevant to the interlinkages between climate change and biodiversity change.

Item 4: 	Report on and finalization of the inter-sessional work of the ad hoc technical expert group

Products A (Assessment report on interlinkages between biological diversity and climate change) and B (Advice on the integration of biodiversity considerations into the implementation of the UNFCCC and its Kyoto Protocol) were presented by their respective editors (Habiba Gitay and Braulio Dias for product A and Horst Korn and Phocus Ntayombya for product B).

Following the discussions of the contents of the two products, the Group recognized that some areas were not yet sufficiently covered in the drafts for products A and B and agreed that further information will still be sought from relevant sources, including IPCC assessment reports and its Special Report on Land Use, Land-Use Change and Forestry.  The Group also decided that the two documents mentioned in paragraph 6 above should be merged into one single document with 5 chapters drawing on the materials so far prepared and other sources of information.

The Group developed an outline of the new document, and agreed on the following:

  - Target audience;

  - Style of the document;

  - Guidance to finalize the document:

Additional authors can be invited to contribute to the chapters;

The executive summary, to be ready only after the informal round of review, should be not just a summary of the different sections and chapters but a well integrated summary of all chapters;

Page and paragraph numbering will be formatted by the Secretariat.  The  names of all AHTEG members and other contributors will be used for the executive summary, with core team members listed as editors and others as contributors; chapter team members will be listed for each chapter starting with core team members in alphabetical order.  All authors of products A and B will also be considered authors in the new unified document;

Informal review should include the secretariat of the United Nations Framework Convention on Climate Change, biodiversity-related conventions and IUCN, WWF, Greenpeace International.  The Secretariat of the Convention on Biological Diversity will prepare individualized letters of invitation to review the document;

Chapter coordinators will give names of potential reviewers to the Secretariat as soon as possible.  Coordinators will suggest a specific chapter to each reviewers according to expertise;

The core team will discuss by e-mail if no funds are available;

Size of the document will be a total of 70 pages and the coordinators for each chapter, constituting with a representative of the Secretariat the “core team” (see the core team composition in annex III below).

The group then split into small working groups (see annex II for details on the different working groups).

The Group met 6 times in plenary. In the last two plenary sessions, the process for the finalisation, review and publication of the document was discussed and a timetable agreed upon as contained in annex III to this report.

The Secretariat of the Convention on Biological Diversity was requested to:

  - make available to the members of the group through the CBD restricted website the four chapters of the new document as drafted to date, the IPCC Third Assessment Reports and the IPCC special report on Land Use, Land-Use Change and Forestry.

  - send an e-mail to the core team for the confirmation of their availability for the next meeting,

  - contact UNFCCC to find out if this AHTEG can be represented at the UNFCCC expert meeting in February 2003.

In order to finalize the work, and to comply with the schedule of work as shown in annex III, additional funding is to be sought by the CBD Secretariat for the core team meetings (13-15 January and 18-20 April 2003) and the meeting of the whole group (14-17 April 2003). The co-Chair from Finland informed the meeting that the Government of Finland may be able to provide some financial assistance.

Item 5. 	OTHER matters

There was no other matters.

# Item 7. 	Adoption of the report and closure of the meeting

The Group considered a draft report of its meeting presented by one of the Co-Chairs on behalf of the Rapporteur.

Following the statements made by a number of participants, one of the Co-Chairs closed the meeting on Friday 13 September at 6 p.m.

Annex I

List of participants

## Governments

Ms. Outi Berghäll, Finland

Mr. Vaclav Burianek, Czech Republic

Mr. Samuel Dieme, Senegal

Dr. Horst Korn, Germany

Mr. Robert Lamb, Switzerland

Dr. Matt McGlone, New Zealand

Dr. Phocus Ntayombya, Rwanda

Dr. Bráulio Ferreira de Souza Dias, Brazil

Ms. Maria Feliciana Ortigão, Brazil

Dr. Gregory A. Ruark, United States of America

Dr. Peter Straka, Slovak Republic

Dr. Ian D. Thompson, Canada

Dr. Heikki Toivonen, Finland

Dr. Yoshitaka Tsubaki, Japan

Indigenous and Local Communities

Mr. Miguel Lovera, Paraguay

Organizations

### Collaborative Partnership on Forest (CPF)

Ms. Danielle Cantin, IUCN

Dr. Kanta Kumari, GEF

Mr. Ndegwa Ndiang'ui, UNCCD

### Other organizations

Dr. Janet Cotter, Greenpeace

Mr. Stephen Kelleher, WWF

Dr. M. V. K. Sivakumar, Switzerland

Resource persons

Dr. Habiba Gitay, Australia

Mr. Avelino Suarez, Cuba

Dr. Robert Watson, United States of America

Secretariat

Mr. Jo Mulongoy

Mr. Fabrice Lantheaume

Ms. Inhee Chung

-----

Annex II

# PROPOSED OUTLINE FOR THE REPORT

| CHAPTER TITLE | CO-LEAD AUTHORS** | NUMBER OF PAGES |
| --- | --- | --- |
| Executive Summary (part A: conclusions, part B: recommendations) | All authors | 5 |
| 1.Introduction | All authors Outi BERGHALL Jo MULONGOY | 2 |
| 2. Background on biodiversity* | Braulio DIAS Peter STRAKA Matt McGLONE Jo MULONGOY Vaclav BURIANEK Maria ORTIGAO | 10 |
| 3. Summary of impacts* | Habiba Gitay Miguel LOVERA Yoshitaka TSUBAKI Avelino SUAREZ | 10 |
| 4.Operationalisation of adaptation and mitigation options* | Horst KORN Phocus NTAYOMBA Outi BERGHALL Samuel DIEME Heikki TOIVONEN Greg RUARK Ian THOMPSON Ndegwa NDIANG UI Janet COTTER | 25 |
| 5. Tools, methods and instruments for evaluation of impacts and implementation of adaptation and mitigation options* | Bob WATSON Steven KELLEHER Kanta KUMARI Inhee CHUNG Sivakumar M.V.K. Fabrice LANTHEAUME Robert LAMB Danielle CANTIN | 25 |

*Each chapter will contain key conclusions/recommendations.

Authors in bold are also  team coordinators.

Annex III

Schedule and chapter coordinators

| Time Period | Action | Responsible |
| --- | --- | --- |
| Sept 13-Oct 21 | Finalize Zero-order chapters | Chapter teams/coordinators |
| Oct 21 | Send Chapters to SCBD | Chapter coordinators |
| Oct 21 | Personal letters to reviewers | Chapter coordinators |
| Oct 22-24 | Format chapters | CBD Secretariat |
| Oct 25 | Send to reviewers | CBD Secretariat |
| Oct 26-Nov 25 | Informal review |  |
| Nov 26-29 | Collate comments | CBD Secretariat |
| Nov 30 | Send review comments to authors | CBD Secretariat |
| Dec 1- Jan 5 | Chapter teams prepare next draft | Chapter teams/coordinators |
| Jan 6 | Send chapters to “core team” | Chapter coordinators |
| Jan 13-15 | Core team finalizes review copy | Core team |
| Jan 27-30 | Final formatting of review copy | CBD Secretariat |
| Jan 31 | Send to experts and governments | CBD secretariat |
| Jan 31 | Send to UNFCCC expert group | CBD Secretariat |
| Feb 1 – April 1 | Expert and government review |  |
| Feb xx-yy | Discussion at UNFCCC experts meeting |  |
| March 10-14 | SBSTTA 8 discussion of draft report |  |
| April 2-7 | Collate review comments | CBD Secretariat |
| April 8 | Send comments to authors | CBD Secretariat |
| April 14-17 | Meeting to prepare final report* | Authors |
| April 18 -20 | Final editing | Core team |
| April 21- May 5 | Page setting | CBD Secretariat |
| May 6 | Send to printers | CBD Secretariat |
| May 7 | Send copy to UNFCCC SBSTA | CBD Secretariat |
| June xx | Send printed report to Governments |  |
| Nov 10-14 | SBSTTA discussion |  |

*	Meeting subject to funding availability – if funds are not available the report will be finalized through e-mail and teleconferences.

# Chapter coordinators	(also members of the core team)

1.	Introduction				Outi Berghall

2.	Biodiversity and climate change	Braulio Dias

3.	Impacts				Habiba Gitay

4.	Options					Horst Korn/Phocus Ntayombya

5.	Tools					Robert Watson