|  |  |  | CBD |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | CONVENTION ON BIOLOGICAL DIVERSITY |  |  | Distr. GENERAL UNEP/CBD/COP/7/2/Add.1 30 September 2003 ORIGINAL ENGLISH |  |

CONFERENCE OF THE PARTIES TO THE CONVENTION ON BIOLOGICAL DIVERSITY

Seventh meeting

Kuala Lumpur, 9-20 and 27 February 2004

Item 22 of the provisional agenda

PROPOSED BUDGET FOR THE PROGRAMME OF WORK OF THE CONVENTION ON BIOLOGICAL DIVERSITY AND THE CARTAGENA PROTOCOL ON BIOSAFETY FOR THE BIENNIUM 2005-2006

Note by the Executive Secretary

Addendum

PROGRAMME AND SUBPROGRAMME ACTIVITIES AND RESOURCES REQUIRED

INTRODUCTION

- This document describes the resource needs for the Secretariat to undertake the programme of work for the biennium 2005 - 2006.  It provides further details on the proposed budget in document UNEP/CBD/COP/7/2.  The information it contains represents the Secretariat's best estimates as regards work priorities in the coming biennium; it remains a "work in progress", and will continue to evolve in the light of future developments in the Convention process.

- The document is organized into sections that correspond to the various programmes under the Secretariat.  The information on programme activities is presented using a standard template.  The table below provides an explanation of the template.  An explanation of the abbreviations used in this document is contained in the annex.

- The activities carried out will respond to demands and priorities. Further information concerning the components of the table can be provided, upon request.  Detailed descriptions will be made available in due time to Parties or Governments that express interest in such activities and in providing supplementary funding for them.

- The overall management section of each programme includes the resources, other than staffing, allocated from the core budget for the programme as a whole.  This includes items such as consultants, travel, expert meetings and equipment. This reflects the fact that the responsibility for these decisions resides with the director of the programme and the Management Committee of the Secretariat.  The Secretariat has been organized along these lines in order to retain the necessary degree of flexibility to respond effectively to the needs of the process.  The overall management section also includes a description of the key external links that the programme will have substantial contact with in order to carry out the described activities.  As the mandate for all of these management activities is Article 24 of the Convention, in the interests of brevity the section on “mandate” has not been included in the overall management section of each programme.

EXPLANATION OF THE TEMPLATE USED IN THE PROPOSED PROGRAMME BUDGET

| Overview of responsibilities | A brief description of the main responsibilities assigned to the programme/subprogramme. |
| --- | --- |
| Expected results | Goals which will have been achieved by the end of the biennium. Mandate: Articles of the Convention, and decisions of the Conference of the Parties, that provide the mandate for each goal. Means: The activities that will be undertaken to achieve the goal. Results: Products and other deliverables that the activities will generate. |
| Approved posts | Posts already approved by the Conference of the Parties and new posts required in the core budget to ensure delivery of the expected results. |
| New posts required |  |
| Resources from outside the core budget | Resources which will be sought from supplementary funding sources to support activities and projects related to the work of the programme/subprogramme. |

SUMMARY TABLES BY PROGRAMMES OF WORK

- Executive Direction and Management (EDM)

| Overview of responsibilities | Overall responsibility for the management of the Secretariat, implementation of the tasks assigned to the Secretariat under the Convention and the Biosafety Protocol; promoting coherence in the Secretariat’s work and ensuring responsiveness to the needs of the Parties and the Convention and Protocol subsidiary bodies; analysis of emerging policy issues; coordination of the Secretariat’s representation in international fora; promotion and maintenance of appropriate linkages and partnerships with relevant international organizations and processes; effective and smooth operation of the Secretariat; and provision of registry and mail functions for the whole Secretariat. |
| --- | --- |
| Expected results | 1. COP, COP-MOP, SBSTTA, other subsidiary bodies and their bureaux receive timely advice and guidance. Means: Oversight of the preparation of all documentation, including in-session, to be submitted to COP, COP-MOP and other bodies of the Convention and the Biosafety Protocol; coordination of inputs from other programmes; organization; servicing meetings of the Bureaux of the Convention and the Protocol; provision of advice and briefs to the Bureaux; guidance to programmes of the Secretariat and staff. Results: Decisions, documentation, calendars and schedules of work; advisory notes and opinions; and reports. |
|  | 2. The Convention and Protocol bodies are provided with the services and support necessary for the convening of official sessions and meetings. Means: Oversight of the preparation of conference facilities; oversight of the reproduction and distribution of documentation for Convention and Protocol bodies; mobilization of teams of temporary assistance. Conclusion of Host Government Agreements in a timely fashion to ensure the adequate provision of logistics and administrative requirements. Secure the necessary financial resources necessary to conduct meetings. Results: Well-organized meetings, and required documents submitted to the Convention and Protocol bodies in a timely fashion. |
|  | 3. Participation of Governments and observers in the sessions of the Convention and Protocol bodies is effectively managed. Means: Oversight of accreditation and registration of representatives; maintenance of contact databases; oversight of issuance of invitations to nominate funded participants. Results: Accredited, registered and, as appropriate, funded delegates; contact database. |
|  | 4. Overview of the Secretariat’s programme areas and effective coordination with, and representation at other relevant UN bodies and organizations. Means: Development of the Secretariat’s long-term programme of work with emphasis on issues requiring cross-programme coordination and cooperative arrangements within the Secretariat and with relevant bodies and organizations, including by concluding MOUs or MOCs. Results: Development of policy for strategic planning, ensuring programme linkages and implementation within the Secretariat, the effective integration of the CBD and Protocol programmes of work in that of relevant international bodies and agencies, as appropriate, and the effectual cooperation with these agencies and bodies to promote complementarities, inter-linkages and synergies. |
|  | 5.The views of the Parties are effectively communicated to relevant international organizations, conferences and other events and information from these processes is integrated into the Convention and Protocol processes, as appropriates. Means: Correspondence; convening of meetings and consultations with the heads of other Convention secretariats, programmes and organizations; attendance and delivery of statements at relevant meetings; preparation of written coherent inputs. Results: Improved information base for Convention bodies and Protocol and related processes; enhanced exchange of relevant information between the Convention and Protocol bodies, the secretariat and relevant international organizations. |
|  | 6. The Secretariat is managed efficiently and effectively, and in a way, which maximizes its ability to respond to the needs of the Convention and Protocol bodies and related processes. Means: Recruitment of programme directors and staff; organizing and chairing the Management Committee of Secretariat; ensuring coordination among programmes; oversight of Secretariat's financial and personnel policies and procedures, within the framework of the United Nations rules and regulations, and overseeing their application; promotion of information flow throughout the Secretariat, inter alia, by convening staff meetings; human and financial resources redeployment to meet evolving needs and priorities. Results: Well-managed Secretariat resources; motivated and capable staff. |
|  | 7. Information flowing into and out of the Secretariat is effectively managed and tracked. Means: Recording, tracking and following up on correspondence; maintenance of correspondence filing system; maintenance of the records management system; effective notification system, electronic fora on substantive issues. Results: Timely replies to correspondence; retrieval-based electronic archive of correspondence; archive of Secretariat-wide correspondence files, timely dissemination of information to a wider audience. |
|  | 8. The work of the Secretariat is adequately funded, in particular securing voluntary funding for approved activities of the Convention and Protocol. Means: Preparing a programme budget that anticipates the needs of the Convention and Protocol bodies; seeking contributions to the trust funds of the Convention for additional approved activities (BE), participation of developing country Parties (BZ) and use of the Biosafety roster of esperts (BF); overseeing the preparation of projects for supplementary activities. Results: Adequate contributions to the trust funds of the Convention. |
|  | 9. Implementation of the Convention’s strategic plan and the 2010 target of reducing the current rate of biodiversity loss Means: Undertaking intersessional activities including the organization of meetings, soliciting, compiling and synthesizing submission from Parties to develop methods to evaluate the progress in the implementation of the strategic plan; integrating and linking the achievement of the 2010 biodiversity target with millennium Development Goals and other related targets emanating from the World Summit on Sustainable Development Plan of Implementation; and liaising with relevant stakeholders, biodiversity related agreements and processes and the Bureaux of th e COP and SBSTTA. Results: The strategic goals and objectives of the Strategic Plan and the 2010 biodiversity target are integrated in the work programme of the Convention and the Protocol, the national biodiversity strategies and action plans, and national biosafety frameworks; increased collaboration and stronger synergies are developed with related conventions and agreements; a mechanism for the evaluation and periodic progress assessment for the implementation of the Strategic Plan and the 2010 biodiversity target is put in place. |
|  | 10. Mobilizing resources to address emerging issues as required Means: Identifying tasks and assigning responsibilities for action and follow-up within the Secretariat to issues that emerge during the intersessional period from subsidiary bodies. Results: Interim guidance from subsidiary bodies is implemented with a view to enhancing preparations for meetings of the COP. |
| External linkages | Executive Director of the United Nations Environment Programme and senior United Nations officials; ministers and other heads of delegations; government representatives; other convention secretariats; key academic and key non-governmental actors. |
| Approved posts New posts requested | Executive Secretary (ASG); Programme Officer, Inter-agency and Programme Coordination Affairs (P-5); Special Assistant to the Executive Secretary (P-4); GS Secretary; GS Information Assistant; GS Research Assistant; GS EDM Assistant. Programme Officer (P-3) post for monitoring and evaluation of the implementation of the strategic plan and the 2010 targets. |
| Resources required | 1. Staff costs: 2005: $796,900 2006: $820,800 2. COP Bureau meetings: 2005: $ 54,000 2006: $ 90,000 3. Consultants: 2005: $ 25,000 2006: $25,000 4. Travel on official business: 2005: $120,000 2006: $120,000 5. Temporary assistance and overtime: 2005: $ 8,000 2006: $ 8,000 |
| Resources from outside the core budget | BZ Trust Fund Regional meetings for COP8 – developing country participation 2006: $200,000 |

B. Scientific Technical and Technological Matters (STTM)

(a)	Overall management

| Overview of responsibilities | Managing the STTM programme: coordinating support to the SBSTTA, and to COP on relevant matters; representing the secretariat externally, especially with respect to scientific and technical matters; facilitating the flow of scientific information in the Convention process and working with scientific organizations in order to ensure that information is conveyed to Parties in a timely and effective fashion. |
| --- | --- |
| Expected results | 1. The human and financial resources of the STTM programme are coordinated effectively. |
|  | Means: Coordination among programme officers within the programme through meetings and documentation; liaison and coordination with other programmes and staff of the Secretariat; liaison and coordination with relevant scientific and technical bodies, networks and processes. |
|  | Results: - Priorities identified and work of different subprogrammes coordinated with a view to ensuring integrated and multidisciplinary strategies and approaches at national and international levels; - Enhanced use of existing knowledge and experiences among different thematic areas and sectors; - Complementarities between thematic and cross-sectoral programme areas and their components identified and developed; and - Programmes of work developed for new and emerging issues as identified by COP. |
|  | 2. Assistance in providing SBSTTA and its Bureau with the support and documentation necessary for their smooth functioning. |
|  | Means: Preparation of relevant technical papers and inputs for submission to SBSTTA; coordination of inputs from other programmes in the Secretariat; organizing and servicing SBSTTA Bureau meetings; providing information to Chair and mobilizing Secretariat resources to the Chair and Parties as requested. Results: Timely and high quality documentation for meetings of the SBSTTA and its Bureau. |
|  | 3. Activities with other organizations competent in science, technology and technical matters related to the Convention |
|  | Means: Maintaining links with other convention scientific bodies and other organizations, participating in other scientific and technical meetings, as appropriate; providing scientific and technical contributions to conferences, seminars and workshops. Results: Enhanced scientific and technical support between the Secretariat and relevant processes and events. |
|  | 4. Organization of liaison groups as required |
|  | Means: Consulting with Executive Secretary on the need for liaison groups, identifying participants and relevant organizations; preparing documentation and undertaking necessary logistical arrangements. Results: Peer review and enhanced quality of documents for meetings of the SBSTTA. |
|  | 5 Organization of ad hoc technical expert group meetings and inter-sessional work |
|  | Means: Selecting experts from those nominated by Parties; identifying experts from international organizations; preparing documentation and undertaking necessary logistical arrangements; organizing peer-review. Results: Document prepared by experts, reviewed and finalized possibly as a Technical Publication. |
|  | 6. Effective participation on behalf of programme in the Management Committee of the Secretariat |
|  | Means: Preparing as required internal documentation for effective decision-making; participating in meetings of the Committee, or organizing representation; conveying decisions of the Committee to staff of the STTM programme. Results: Effective coordination of the staff mostly for servicing meetings and on other substantive matters. |
| External linkages | Bureau of SBSTTA; Parties; UNEP; STAP; STRP of the Ramsar Convention; UNFCCC Secretariat, UNFCCC SBSTA, UNCCD Secretariat, UNCCD CRIC, CITES Secretariat and its Plants Committee, UNDP Dryland Development Centre (DDC), UNFF, FAO and other United Nations bodies, other intergovernmental organizations, and other organizations competent in science and technology. Memorandum of Cooperation with: UNCCD, FAO including its IPPC Secretariat and CGRFA/IT-PGRFA Secretariat, Botanic Garden Conservation International, Ramsar, IAIA; IUCN. New Memorandum of Cooperation in development: UNDP Dryland Development Centre. |
| Approved posts | Principal Officer -D-1; GS Secretary |
| Resources required | 1. Staff costs: 2005: $1,533,400 2006: $1,579,400 2. SBSTTA Meetings (2): 2005: $ 525,000 2006: $ 525,000 3. SBSTTA Bureau meetings: 2x1 meeting 2005: $25,000 2006: $ 25,000 4. Consultants (specified under the thematic areas and cross-cutting issues) 2005: $25,000 2006: $25,000 5. Ad hoc technical expert meetings (6): 2005: 4 x$60 000 2006: 2x$60 000 6. Travel on official business: 2005: $60,000 2006: $ 60,000 7. Temporary assistance and overtime 2005: $8,000 2006: $8,000 |
| Resources from outside the core budget | BZ Trust Fund SBSTTA 10 and SBSTTA 11 – developing country participation 2005: $540,000 2006: $540,000 |

(b)	Thematic areas programme

| Overview of responsibilities | Implementation and development where necessary, of the thematic programmes of work |
| --- | --- |
| Expected results | 1. Inland water biological diversity. |
|  | Mandate: Decision VI/2; decisions V/2 and V/21; decision IV/4; decision III/11, para. 15(h); decision III/21, para. 7; decision IV/5, para. 4; and decision IV/15, para. 2; and SBSTTA recommendations VIII/2, VI/3 and VI/5; and expected recommendations of SBSTTA 9 and decisions of COP 7. Means: Implement the refined programme of work; implement and report on the third Joint Work Plan between CBD and Ramsar; request submissions from Parties, Governments and relevant organizations for compilation and assessment; cooperation with Parties (particularly small island developing States), Governments and other relevant organizations, such as CSD, the Global International Water Assessment (GIWA), the Global Invasive Species Programme (GISP), WWAP, the Millennium Ecosystem Assessment, CMS and FAO. |
|  | Results ( based on SBSTTA recommendations VIII/2): - Proposal on ways and means for making future reviews of implementation of CBD programmes of work more comprehensive (para 1b of SBSTTA recommendation VIII/2); - Streamlining and improving the effectiveness of national reporting on inland water ecosystems, taking into account the work of the Task Force on Streamlining Forest-related Reporting established in the framework of United Nations Forum on Forests and other initiatives for harmonizing biodiversity-related national reports (para 1c of SBSTTA recommendation VIII/2) and development of cost-effective means to report on implementation of the programme of work as measured against the global targets defined in the Strategic Plan, in the Global Strategy for Plant Conservation, and in the Plan of Implementation of the World Summit on Sustainable Development, essentially using indicators and assessments at the global level by international organizations (para 3e of SBSTTA recommendation VIII/2); - Strengthened collaboration with the Ramsar Convention on Wetlands, and other organizations, institutions and conventions as a way to streamline many of the activities contained in the programme of work, promote synergies (para 1d and e of SBSTTA recommendation VIII/2); - Implementation of the programme of work including (i) conservation and sustainable use of inland water biodiversity (ii) enabling activities addressing many of the socio-economic gaps identified in the review of the programme of work; and (iii) monitoring and assessment (para 2a of SBSTTA recommendation VIII/2); - Formulation and adoption of outcome oriented targets and identified priorities for each activity, including timescales, taking into account the Strategic Plan of the Convention as well as the Strategic Plan of the Ramsar Convention 2003-2008, the Global Strategy for Plant Conservation and the Plan of Implementation of the World Summit on Sustainable Development (para 2g and 4b of SBSTTA recommendation VIII/2); - Progress towards the implementation of the Strategic Plan of the Convention on Biological Diversity and the Plan of Implementation of the World Summit on Sustainable Development, and their target of 2010 to reduce significantly the rate of biodiversity loss (para 2b of SBSTTA recommendation VIII/2); - Incorporation of the objectives and relevant activities of the programme of work in national biodiversity strategies and action plans, and wetland policies and strategies; cross-referencing to, and coherence with, the other thematic programmes of work (para 2d and e of SBSTTA recommendation VIII/2); - Implementation of the programme of work and further promotion of coordination and cooperation between national actors responsible for inland water ecosystems and biological diversity (para 2d of SBSTTA recommendation VIII/2); - Information and lessons learned from the application of national and regional water frameworks (para 2f of SBSTTA recommendation VIII/2); - Information on mountain water supply and examples of transferable technologies relevant to the implementation of the proposed revised programme of work on inland water biodiversity also relevant to mountain ecosystems (para 3a of SBSTTA recommendation VIII/2); - Information on specific examples of successful policy interventions to conserve and sustainably use inland waters (para 3c of SBSTTA recommendation VIII/2); |
|  | 12. Listing of major threats to inland water biodiversity, and their underlying causes, as a basis for the identification of priorities for early action, taking into account regional differences (para 5a of SBSTTA recommendation VIII/2); - Regarding the status and trends of inland waters biodiversity, development of (i) a work plan with defined timeframe, ways, means, and capacity needs for assessing the extent, distribution and characteristics, including, inter alia, physical, chemical and biological characteristics, of all types of inland water ecosystems at the global and regional scales; (ii) a report on information, and sources of information, on the trends of inland water biodiversity, definition of agreed baselines, relevant indicators and frequency of the assessments; and (iii) a work plan with ways and means for assessing processes and categories of activities which have or are likely to have significant adverse impacts on the conservation and sustainable use of inland water biological diversity (para 5b of SBSTTA recommendation VIII/2); - Establishment of databases on inland water ecosystem goods and services, their uses and related socio-economic variables; on species and all taxonomic levels; on basic hydrological aspects and water supply; and on the threats to which inland water ecosystems are subjected (para 5c of SBSTTA recommendation VIII/2); - Promotion and trainers training on the application of the guidelines, in particular in the circumstances of small island developing States and in the territories of States in which inland water ecosystems suffer from ecological disaster (para 5e and g of SBSTTA recommendation VIII/2); - Development of a complementary set of tools to assess the function and health of inland water ecosystems and the socio-economic and cultural values of biological diversity of inland waters (para 5f of SBSTTA recommendation VIII/2); - Development of a monitoring and reporting system to assess the experiences gathered with respect to the usefulness and applicability of the guidelines (para 5h of SBSTTA recommendation VIII/2); - A study on the linkages between conservation and sustainable use of inland water biodiversity and poverty alleviation/sustainable livelihoods, including human health considerations (para 5j of SBSTTA recommendation VIII/2); - Information about the function of inland water ecosystems (including factors that affect ecosystem functions, the valuation of ecosystem functions, and remedial actions to restore ecosystem functions) and its importance to land and resource managers for planning, evaluating and executing plans and programmes (para 6 of SBSTTA recommendation VIII/2); - Indicative lists of inland water ecosystems important in the framework of the Convention, as requested in paragraph 12 of the programme of work on inland water biodiversity annexed to decision IV/4, using the Ramsar criteria (para 7a of SBSTTA recommendation VIII/2); - Review of the Ramsar classification as the interim classification system on the basis of experiences accumulated by Parties, other Governments and relevant organizations (para 7b of SBSTTA recommendation VIII/2); - Contribution to the further elaboration of the guidelines on Ramsar criteria and provision of guidance, based on experiences, for the interpretation and application of the Ramsar criteria at the national and regional levels (para 7c and d of SBSTTA recommendation VIII/2). |
|  | 2. Marine and coastal biological diversity |
|  | Mandate: Decision VI/3 and V/3 including the annex on coral bleaching; decisions II/10 and IV/5 on the conservation and sustainable use of marine and coastal biological diversity; decision I/2, annex I, para. 4(k); decision III/10; decision III/11, para. 15(h); decision III/18 (SBSTTA recommendation II/9, para. 2); decision III/19, annex, para. 8(b); decision IV/15, para. 10. SBSTTA recommendation VIII/3 See also Jakarta Ministerial Statement on the Implementation of the Convention on Biological Diversity, para. 14; SBSTTA recommendations I/8 and VI/2 and VI/5, and expected decisions of COP 7. Means: Implementation of the programme of work including work plans on coral bleaching and physical degradation and destruction of coral reefs; compile case-studies and information, carry out studies, organize and service expert meetings as appropriate, maintain and foster further collaboration with relevant organizations, improve and maintain databases and Internet services, develop different kind of products (e.g. technical guidelines, gap analyses). |
|  | Results: - Enhanced capabilities of Parties to implement measures for the conservation and sustainable use of marine and coastal biological diversity (overall objective of the work programme); - Guidance and enabling activities for implementing the provisions of the Convention in the area of integrated marine and coastal area management (operational objectives (op. objs.) 1.1 and 1.2) ; - Guidelines for ecosystem evaluation and assessment, including indicators (op. obj. 1.3); - Ecosystem approaches to the sustainable use of marine and coastal living resources (op. obj. 2.1) ; - Options for conservation and sustainable use of marine and coastal genetic resources, including bioprospecting (op. obj. 2.2 and paragraph 12 of decision II/10); - Compiled information on, and increased capacity to assess and mitigate, biological and socio-economic consequences of coral bleaching and physical degradation and destruction of coral reefs (op. obj. 2.3); - Implementation of elaborated programme of work as it pertains to marine and coastal protected areas (as per COP 7 decision) (op. obj. 3.2). |
|  | - Implementation of elaborated programme of work as it pertains to mariculture (as per Cop 7 decision) (op. obj. 4); - Better understanding of the causes and impacts of introductions of alien species and genotypes, and implementation of elaborated programme of work as it pertains to invasive alien species (op. obj. 5.1); - Identification of gaps in existing or proposed initiatives and collected information on actions, on marine and coastal alien species and genotypes (op. obj. 5.2); - Incident list of introductions of alien species (op. obj. 5.3) ; - Database of initiatives on programme elements, particularly integrated marine and coastal area management (op. obj. 6.1); Roster database (op. obj. 6.2). |
|  | 3. Agricultural biological diversity. |
|  | ###### Mandate: Decision VI/5 and annexes I and II, SBSTTA recommendation VIII/7, para. 8; annex to recommendation 3 of the Open-ended intersessional meeting of the MYPOW; decision III/11 and decision IV/6 (also SBSTTA recommendation III/4); decision II/15; decision II/16; decision III/5 para. 2(c); decision III/19, Annex, para 8(c); V/5 para. 6; V/5 para.8; V/5 para. 12; V/5 para. 16; V/5 para. 18; V/5 para. 20 and 21; V/5 para. 22; V/5 para. 25; V/5 para. 28; V/5 para. 29; SBSTTA recommendation VII/7; and expected decision by COP 7. |
|  | Means: Compile case-studies and information, carry out studies, organize and service expert meetings as appropriate, maintain and foster further collaboration with relevant organizations, improve and maintain databases and Internet services. Support studies and service meetings to assist in: the review of ongoing activities and existing instruments relevant to agricultural biological diversity; coordinate and report on the implementation of the programme of work with partner organizations; and facilitate exchange of information through collaboration with FAO, UNEP and other relevant organizations and bodies. Collaborate with Parties, other Governments and other organizations, in particular FAO, CGRFA, MA, OECD, UPOV, WIPO and WTO. Assist in the establishment and implementation of the International Pollinators Initiative and the International Soil Biodiversity Initiative. Review and support the implementation of the Memorandum of Cooperation with FAO. Promote synergy with other programmes of works, with special attention to dry and sub-humid lands and assessments and indicators. |
|  | Results: - Roster of lead and support institutions and of experts; - Support the Global Plan of Action for the Conservation and Sustainable Utilization of Plant Genetic Resources for Food and Agriculture and the Global System for the Management of Farm Animal Genetic Resources (paragraph 3(b) of decision V/5). Steps for the implementation of the programme of work against the 4 programme elements (Annex to decision V/5; para. 2 of decision VI/5, and table 1 and 1 of Annex I to decision VI/5): - Coordination of development and implementation of the programme of work with partner institutions (para. 2 of decision VI/5); - Preliminary assessment of the status and trends of agricultural biodiversity (2006) developed and published (element 1 of annex to decision V/5); - A key set of standard questions and a menu of potential indicators of agricultural biodiversity that may be used by Parties and their national level, and agreed terminology of production environments (element 1 of annex to decision V/5); - Compilation of case studies on cost effective practices and technologies, promotion, partnership and forums, and policy (table 1 of annex 1 to decision VI/5); - Analysis of lessons learned from case studies on assessment, adaptive management, capacity building and mainstreaming (table 2 of annex 1 to decision VI/5); - Thirty selected case-studies published, analyzed and disseminated (element 2 of annex to decision V/5); - Examples at country level of operational mechanisms for participation by a wide range of stakeholder groups including civil-society organizations; involvement of farmers and local communities progressing toward their involvement in the majority of national programmes by 2010 (element 3 of annex to decision V/5); - Range of guidelines published at the international level (on topics to be determined according to needs at national and regional levels) (element 4 of annex to decision V/5); - Over 100 countries to participate in various assessments under activities 1.1 and 1.2 contained in annex to decision V/5, and; coordination between sectoral assessments and plans of action at national level in the majority of countries (element 4 of annex to decision V/5); - Recommendations on capacity-building and policy (table 2 of annex I to decision VI/5) as input to, inter alia, the in-depth review of the programme of work on agricultural biodiversity (para. 8, recommendation VIII/7 on MYPOW); and - Synthesis of relevant studies and analysis of gaps and opportunities in the implementation of the programme of work drawing upon the national thematic reports that include the thematic report on agricultural biodiversity (para. 6 of decision VI/5). |
|  | Genetic Use Restriction Technologies (GURTs) (paras.18 to 25 to decision VI/5): - Dissemination of information provided by Parties and other Governments on assessments of, inter alia, ecological, social and economic effects of GURTs (para. 19, decision VI/5); and - Report on development of GURTs and related initiatives. |
|  | International Pollinator Initiative (IPI) - in the framework of the action plan of the IPI led by FAO (paras 8 to 12, decision VI/5): - Preliminary report on the state of the world’s pollinators based on existing data and early results from assessment and adaptive management activities (element 1 of annex II to decision VI/5); - Case-studies compiled, published, analyzed and disseminated (element 2 of annex II to decision VI/5); and - Pilot projects implemented (element 3 of annex II to decision VI/5). |
|  | International Soil Biodiversity Initiative, led by FAO (para 13 of decision VI/5): - Development and implementation, in collaboration with the FAO, the plan of action for the Initiative (para 13 of decision VI/5); and - Mobilization of financial and other relevant resources for the implementation of the plan of action (para 13 of decision VI/5). |
|  | Cooperation with other organizations, initiatives and conventions: - Review and Implementation of the Memorandum of Cooperation with FAO, including with the CGRFA, IPPC and the secondment of a FAO staff member to the Secretariat; and - Extended collaboration with other relevant organizations. |
|  | 4. International Treaty on Plant Genetic Resources for Food and Agriculture. |
|  | Mandate: Decision VI/6, para. 4 and 5; and expected decision by COP 7. |
|  | Means: Memorandum of Cooperation with the FAO/CGRFA as it related to the International Treaty on Plant Genetic Resources for Food and Agriculture (IT-PGRFA). Compile information, carry out studies, organize and service expert meetings as appropriate, maintain and foster further collaboration with relevant organizations; cooperate and facilitate exchange of information with Parties, other Governments and other relevant organizations in related matters including, inter alia, benefit sharing, the material transfer agreement (MTA) and the interlinkages between the Treaty and the Bonn Guidelines. Participation in relevant meetings. |
|  | Results: - Priority areas of common interest identified and development of collaborative activities; - Memorandum of Cooperation with FAO/IT-PGRFA reviewed and implemented; - Capacity-building at regional level on the interlinkages between the Treaty and the Bonn Guidelines for Animal and Plant Genetic Resources, and their application in harmony; - Guidelines for the application in harmony of the Treaty and the Bonn Guidelines developed and published; and - Joint publication with FAO to promote the implementation in harmony of the Treaty and the CBD, including the Bonn Guidelines. |
|  | 5. Forest biological diversity. |
|  | Mandate: Decision V/4, decision II/9; decision III/12; decision IV/7, IV/16, annex II; and decision V/4: and SBSTTA recommendations II/8 and III/3. Also decision I/8, annex, para. 15; decision III/11, para. 15(h); decision III/19, annex, para. 8(c); decision IV/13, para. 4; SBSTTA recommendation VII/6; decision VI/22 and annex. Means: Implementation of the expanded programme of work. Compile case-studies and information, develop databases, organize and service scientific and technical meetings as appropriate; national mechanisms and pilot projects; peer-review mechanisms; use of national and international data bases; review of implementation of programme of work. Develop guidelines. Cooperation with Parties, bodies, governments, and other relevant organizations, including in particular the Collaborative Partnership on Forests (CPF), UNFF Secretariat, UNCCD Secretariat, CITES, UNESCO, IPCC, SCOPE. |
|  | Results: - Criteria and indicators for forest biological diversity; - Research and technology priorities; - Characterization and analysis from forest ecosystems to global scale and development of general classification of forests on various scales in order to improve the assessment of status and trends of forest biological diversity; - Improvement of knowledge on, and methods for, the assessment of the status and trends of forest biological diversity; - Measures for enhancing integration of conservation and sustainable use of biological diversity in forest-management systems and mechanisms; - Identification of traditional forest systems and promotion of the wider application in sustainable forest management; - Reduction of the threats and mitigation of the impacts of threatening processes on forest biological diversity - Protection, recovery and restoration of forest biological diversity - Identification of mechanisms that facilitate the financing of activities for maintenance of forest biological diversity; - Contribution to ongoing work in other international and regional organizations and processes, in particular to the implementation of the proposals for action of the Intergovernmental Forum on Forests/UNFF; - Identification of the contribution of networks of protected areas to the conservation and sustainable use of forest biological diversity. - Analysis of human impact on forests, including fire - Methods and techniques for the valuation of forest biodiversity goods and services; - Guidelines for the implementation of ecosystem approach in forest-management systems and mechanisms, and application of the ecosystem approach to the management of all types of forests; - Improvement of understanding of the role of forest biodiversity and ecosystem functioning, and of the infrastructure for data and information management for accurate assessment and monitoring of global forest biological diversity; |
|  | - Information on sustainable use of forest biodiversity with recommendations for management actions. - Information support for facilitating implementation of the expanded programme of work - Identification of effects of insufficient forest law enforcement on forest biological diversity; - Development of a toolkit for capacity building on integrated approaches and planning to reduce negative impacts on forest biological diversity - Assessment of fire impacts on forest biodiversity - Proposals for the integration of non-timber forest resources in forest inventories - Proposals for harmonization of forest-related data collection - Information on effects of climate change on forest biological diversity and integration of biodiversity considerations into climate change mitigation and adaptation activities. - Recommendations on sustainable management of forest biological diversity in order to facilitate implementation of activities of expanded programme of work. |
|  | 6. Biological diversity of dry and sub-humid lands |
|  | Mandate: Article 24 of the Convention; decision VI/4: decision V/23; decision III/13; and anticipated COP 7 decisions, including MYPOW recommendation to review in-depth ongoing work of the programme of work on biological diversity of dry and sub-humid lands at COP 8 in 2006 (see UNEP /CBD/COP/7/5). Additionally, joint work programmes with the UNCCD, CMS, and RAMSAR Means: Carry out studies, compile case studies and information, develop databases, organize and service scientific and technical meetings as appropriate; cooperation with Parties, governments and other relevant organizations, in particular the Secretariat of UNCCD, and other environmental Conventions, other collaborating partners in the implementation of the programme of work; review of progress in the implementation of the programme of work. Results: Based on SBSTTA recommendation VIII/4 (Annex 1), taking into account recommendation 3 of the Open-ended intersessional meeting on the MYPOW: - In-depth review of the programme of work, taking into account items identified as priorities by the World Summit on Sustainable Development, such as poverty alleviation, human health, sustainable communities and livelihoods, and hotspots, other areas of biodiversity importance, ecological networks and corridors; - State of progress, including obstacles, in achieving the goals of the Strategic Plan and progress towards the achievement of the Convention’s 2010 targets and the Millennium Development Goals - Review and assessment report on status and trends and draft elaborated of indicators (in collaboration/liaison with LADA (Global Land Degradation Assessment of the Food and Agriculture Organization) and the Millennium Ecosystem Assessment (MA); - Review and assessment of areas of value/under threat; production of a draft map and assessment report, with the support of a liaison group; - Reports and publications on the structure and functioning of dry and sub-humid lands; publication of summary review document; - Draft reports on information on local and global benefits derived from drylands biodiversity; draft report on socio-economic-impact of biodiversity loss and linkage to poverty, and; collection of case-studies on these inter-linkages through an innovative case-study collection mechanism and production of reports; production of relevant publications; - Identification of best management practices, including applying ecosystem approach; development of guidelines for the assessment of good practices and documentation of best practices; development of and innovative case-study collection mechanism; - Identification, documentation, synthesize and dissemination of options for conservation and sustainable use of drylands biological diversity, as well as options for sustainable livelihoods through, for instance, regional sharing-of-experiences workshops, which would lead also to draw lessons-learnt and guidance on various issues; these activities would include capacity building between and for Parties. - Support joint synergy activities, including workshops and demonstration projects, at the local, national, regional and global levels |
|  | 7. Biological diversity of mountain ecosystems |
|  | Mandate: Article 24 of the Convention; decision VI/30; recommendation VIII/1; MYPOW recommendation 3 in Annex to document UNEP/CBD/COP/7/5; and decision IV/16, annex II; and expected COP 7 decisions on this and other thematic areas. |
|  | Means: Implementation of the programme of work on mountain biodiversity, including by carrying out desk studies, compiling case-studies and information, developing databases, organizing and servicing scientific and technical meetings as appropriate: fostering cooperation with other relevant organizations such as those indicated in paragraph 3 of annex I to recommendation VIII/1 A i.e. the Ramsar Convention, the United Nations Convention to Combat Desertification (UNCCD), the United Nations Framework Convention on Climate Change (UNFCCC), the Food and Agriculture Organization of the United Nations (FAO), the United Nations Educational, Scientific and Cultural Organization (UNESCO), the International Centre for Integrated Mountain Development (ICIMOD), the International Centre for Agricultural Research in the Dry Areas (ICARDA), the International Partnership for Sustainable Development in Mountain Regions, the International Human Dimensions Programme on Global Environmental Change (IHDP), the Centre for Mountain Studies, the Consorcio para el Desarrollo de la Ecoregion Andina (CONDESAN), the Mountain Research Initiative (MRI), the Global Mountain Biodiversity Assessment (GMBA) of DIVERSITAS, the International Union of Forest Research Organizations (IUFRO), the Alpine Convention, and the World Conservation Monitoring Centre (WCMC) |
|  | Results: - Ways and means to reduce at global, regional and national levels mountain biological diversity loss and contribute to the 2010 biodiversity target, and thus contribute to poverty alleviation in mountain ecosystems and in lowlands dependent on the goods and services of mountain ecosystems and thereby contribute to the objectives of the Strategic Plan of the Convention on Biological Diversity, the Plan of Implementation of the World Summit on Sustainable Development, and the Millennium Development Goals (paras 4 and 5 of annex I to SBSTTA recommendation VIII/1A); - Assessment of problems that are specific to mountain biological diversity, including: (i) the particularly high concentration of biological diversity hotspots, (ii) ecosystem and species fragility and their vulnerability to human and natural disturbances, (iii) the characteristic upland-lowland interactions, in particular with relation to water and soil resources; (iv) high levels of cultural diversity, and the particularly key role of indigenous and local communities in the conservation and management of mountain biological diversity (para 6 of recommendation VIII/1A); - Establishment of national programmes of work with targeted goals, objectives, and actions, with specific actors, timeframes, inputs, and expected measurable outputs (para 8 of recommendation VIII/1A); - Progress in implementation of the programme work with its 14 goals and actions specified in Annex I to recommendationVIII/1A establishing national programmes of work with targeted goals, objectives, and actions, with specific actors, timeframes, inputs, and expected measurable outputs, including in particular the prevention and mitigation of the negative impacts of key threats; restoration of degraded mountain ecosystems; maintenance of genetic diversity in mountain ecosystems in particular through the preservation and maintenance of traditional knowledge and practices; establishment of regional and transboundary collaboration; increased public education, participation and awareness in relation to mountain biological diversity; enhancement of legal, policy and institutional framework for the conservation and sustainable use of mountain biodiversity; assessments of status and trends of mountain biological diversity and description of causes of changes, and identification of options for conservation and sustainable use of mountain biological diversity; and promotion of the development, validation, and transfer of appropriate technologies for mountain ecosystems, including indigenous technologies (Annex I to recommendation VIII/1A and recommendation VIII/1B); - Information on positive and negative experiences on the development and transfer of technologies and technical cooperation, and best practices on the transfer of technologies relevant to the conservation and sustainable use of mountain biodiversity and the fair and equitable sharing of the benefits arising from the utilization of genetic resources (para (c) of recommendation VIII/1B); - Expanding role of the clearing-house mechanism of the Convention as a central mechanism for exchange of information on relevant technologies, with inter alia a searchable catalogue (including database) of technologies that are in the public domain, and a portal that international organizations can be encouraged to use to disseminate technologies.. |
|  | 8. Biological diversity of small islands |
|  | Mandate: Preamble and para 6 of Art. 20 of the CBD; Recommendation of Open-ended intersessional meeting on the MYPOW; SBSTTA recommendation VIII/2, 3B and 7; decisions VI/ 3, 5, 9, 10, 17, 19, 22, 23, |
|  | Means: Carrying out studies, compiling case-studies and information, developing databases, organizing and servicing scientific and technical meetings as appropriate: fostering collaboration, in particular, with ICRI and its partners, UNEP regional seas programmes, UNESCO Intergovernmental Oceanographic Commission, FAO; IAIA; |
|  | Results - Status and trends of and threats to, biodiversity, taking into account in particular the impact of tourism development, and introduction and spread of invasive alien species on biodiversity and livelihoods; - Identification of issues of overarching importance, particularly the relevant socio-economic issues identified by the World Summit on Sustainable Development; - Strategies towards the achievement of the 2010 targets of significantly reducing the rate of biodiversity loss, and other targets (MDG and WSSD Plan of Implementation), including development of global targets and related measures, such as monitoring and indicators; - Development of mechanisms to support implementation e.g. financial mechanism, clearing-house mechanism, technology transfer, capacity-building (including inter alia para 5e (on application of guidelines for rapid assessment of inland water biodiversity) and para 5g (on practical training for the application and adaptation of these rapid assessment methods) of SBSTTA recommendation VIII/2); - Consideration of specific situation of small island states in the implementation of the thematic programmes of work and work on cross-cutting issues, including inter alia: - Implementation of para 2 of decision VI/3: work plan on coral bleaching; and implementation of para 25 of SBSTTA recommendation VIII/3 on enhancing capabilities for, and establishment and maintenance of, marine and coastal protected areas and their networks; - paras 12 and 16 of decision VI/5: on International Pollinators Initiative and assessment, conservation and sustainable use of world’s animal genetic resources; - paras 6 and 7 of decision VI/9and target 15 on capacity for implementing the Global Strategy for Plant Conservation; - paras 18 and 42 of decision VI/10 on capacity conduct cultural, environmental and social impact assessment regarding developments proposed to take place on, or which are likely to impact on, sacred sites and on lands and waters traditionally occupied or used by indigenous and local communities; and on for the establishment and maintenance of mechanisms to protect traditional knowledge at national and subnational levels, and for building the capacity of indigenous and local communities to develop strategies and systems for the protection of traditional knowledge - para 8 of decision VI/15 on incentive measures - para 10 d, f, g and h of decision VI/17on financial mechanism: - para 3b of decision VI/19on development of adequate capacity to deliver initiatives on communication, education and public awareness; - para 17 of decision VI/22 on capacity and technology transfer for the implementation of the programme of work on forest biodiversity: - paras 19, 31 an 34 of decision VI/23 on capacity and implementation of programmes on invasive alien species: - paras 5 and 11e, g, h and k of decision VI/24 on capacity for implementing the Bonn Guidelines on Access to Genetic Resources and Fair and Equitable Sharing of the Benefit Arising out of their Utilization - migratory species (para 18 of decision VI/20) - Programme of work on biodiversity of small island States |
| Approved posts New posts requested | P-4 Inland Waters; P-4 Terrestrial Ecosystems/forest biodiversity; P-4 Dry and sub-humid lands Ecologist; P-4 Jakarta Mandate/Marine and coastal biodiversity. G7 Programme Assistants (2) P-3 Mountain Biodiversity; For the coordination of the work on small island states biodiversity, an existing position to be reclassified/upgraded to include this function. G-7 Programme Assistant (1) |
| Resources from outside the core budget | BE Trust Fund: P-4 Agrobiodiversity (FAO); SPO/JPO Trust Funds: P-5 Forest Biodiversity (Netherlands); P-2 Forest Biodiversity (Italy). Additional requirements: Consultants: 2005: $55,000 2006: $15,000 Liaison groups or other types of formal consultations: 6 of which 2 on dry and sub-humid lands will require funding ($40 000) for participants from developing countries. 2005: $40,000 2006: $0 Workshops: 7 2005: 6x$60,000 2006: $60,000 JPOs (P2): 3 i.e. one for the work on biodiversity of small island states, one for marine and coastal biodiversity/high seas, and one to assist with the dry and sub-humid land biodiversity programme of work |

(c)	Cross-cutting issues

| Overview of responsibilities | Implementation and development where necessary, of cross-cutting issues: alien species; ecosystem approach; scientific assessments; impact assessments; targets, baselines and indicators; Global Taxonomy Initiative; protected areas; climate change; migratory species; and restoration and rehabilitation of degraded ecosystem and recovery of threatened species.. |  |
| --- | --- | --- |
| Expected results | 1. Invasive alien species (IAS) |  |
|  | Mandate: Decision VI/23 and relevant COP 6 decisions on other thematic and cross-cutting issues (paras 2 and 7 on impact on pollinators, and element 2 of the plan of action for the international initiative for the conservation and sustainable use of pollinators in Annex II to decision VI/5; appendix 2 to decision VI/7A on impact assessment; decision VI/8 on the Global Taxonomy Initiative; and programme of work on forest biodiversity annexed to decision VI/22); programme of work on mountain biodiversity annexed to SBSTTA recommendation VIII/1; proposed revised programme of work on inland water biodiversity annexed to SBSTTA recommendation VIII/2; SBSTTA recommendation VIII/3 on marine and coastal biodiversity; programme of work on dry and subhumid land annexed to SBSTTA recommendation VIII/4; guidelines for tourism development annexed to SBSTTA recommendation VIII/5; recommendation 3 of the Open-ended intersessional meeting of the MYPOW; decisions V/8 and V/14; decision IV/1C; SBSTTA recommendation IV/4; paras. 9 and 10 of decision III/9; decision IV/4, annex, paras 8(c)(vi), 9(e)(iv) and 9(h); decision IV/5, annex, programme area 5; and decision IV/7, annex, paras. 32, 35 and 52; SBSTTA recommendation VI/4 and VI/5; and expected decisions of COP 7. |  |
|  | Means: Compile information and case-studies, organize and service meetings as appropriate, maintain and foster further collaboration with GISP, FAO, IPPC and the Interim Commission on Phytosanitary Measures, IMO, OIE, WHO and FAO, Ramsar Convention, IUCN and other relevant organizations; development and implementation of strategy/plan for enhanced use of CHM for technical and scientific cooperation using invasive alien species as primary focus. Additional funding from GEF. |  |
|  | Results: - Status of implementation of the guidelines (para 5 of decision VI/23) - International instrument prepared by IMO in collaboration with CBD and others to address the environmental damage caused by the introduction of harmful aquatic organisms in ballast water, including as appropriate, mechanisms to minimize hull-fouling as an invasion pathway (para 7 of decision VI/23) - Incorporation of criteria related to the threats to biological diversity posed by invasive alien species in the work of the International Plant Protection Convention (IPPC), the Office International des Epizooties (OIE), the Food and Agriculture Organization of the United Nations (FAO), the International Maritime Organization (IMO), the World Health Organization (WHO) and other relevant international instruments and organizations on standards and agreements, including for risk assessment/analysis (para 8 of decision VI/23); - Development of national invasive alien species strategies and action plans, including capacity building and taking into account known and potential pathways for the introduction of invasive alien species and opportunities to minimize incursions and manage risks (paras 10 to 14 of decision VI/23) - Identification and exploration of gaps and inconsistencies in the international regulatory from a technical perspective of the threats of invasive alien species to biological diversity, including consideration of various pathways for the transmission of invasive alien species (para 9 of decision VI/23); - Information of potential effects of global change on the risk of invasive alien species to biodiversity, and related ecosystem goods and services, and consideration of these aspects in the work of United Nations Framework Convention on Climate Change (UNFCCC); WTO, FAO, WHO, UNDP, the World Bank and other development agencies (para 15 of decision VI/23); - As part of the promotion of the implementation of Article 8h of the Convention, development of guidance, best practices and pilot projects that address the threats of invasive alien species to particular sites or habitats, including means to enhance the capacity of ecosystems to resist or recover from alien species invasions, in the work of the Convention on the Conservation of Migratory Species of Wild Animals, the Ramsar Convention on Wetlands, the Convention on the Conservation of European Wildlife and Natural Habitats, the Convention on International Trade in Endangered Species of Wild Fauna and Flora, the World Heritage Convention, and the Man and the Biosphere Programme of the UNESCO (para 16 of decision VI/23); |  |
|  | - Initiative to address impediments to the management of marine alien species, particularly to address technical problems related to the identification and control of marine invasions (para 20 of decision VI/23); - Information gathered and disseminated through the Clearing house mechanism on issues listed in para 24 of decision VI/23: - The characteristics of invasive species and the vulnerability of ecosystems and habitats to invasion by alien species, and the impact of climate change on these parameters(52); - The impact of alien species on biological diversity; |  |
|  | - Analysis of the importance of various pathways for the introduction of invasive alien species; - The socio-economic implications of invasive alien species particularly the implications for indigenous and local communities; - The development of environmentally benign methods to control and eradicate invasive alien species, including measures for use in quarantine and to control fouling of ship hulls; - The costs and benefits of the use of biocontrol agents to control and eradicate invasive alien species; - Means to enhance the capacity of ecosystems to resist or recover from alien species invasions; - Priorities for taxonomic work through, inter alia, the Global Taxonomy Initiative(53); - Criteria for assessing risks from introduction of alien species to biological diversity at the genetic, species and ecosystem levels; - The use of the traditional knowledge of indigenous and local communities in the development and implementation of measures to address invasive alien species, in accordance with Article 8(j) of the Convention; - Enhanced role of the clearing-house mechanism in facilitating scientific and technical cooperation on the above topics and the creation and maintenance of the global information network, and for on-line educational programme (paras 25 and 32 of decision VI/23); - Development and implementation of a joint programme of work through the Global Invasive Species Programme partnership network among the Convention on Biological Diversity, the Convention on Wetlands (Ramsar, Iran, 1971), IMO, IPPC and other relevant bodies (para 26 of decision VI/23); - Technical tools and related information (e.g. case-studies, anthologies of existing terminology used in international instruments, lists of procedures for risk assessment/analysis and pathway analysis, inventory of existing expertise, databases, and systems for reporting new invasions) to support efforts for the prevention, early detection, monitoring, eradication and/or control of invasive alien species and to support public awareness-raising and environmental education to the extent possible (paras 27 and 28 of decision VI/23); - Means to facilitate capacity enhancement for eradication work on alien species on continents and islands (para 31 of decision VI/23); - Identify a mechanism(s) for providing Parties with access to financial support for rapidly responding to new incursions by alien species (para 33 of decision VI/23) |  |
|  | 2. Ecosystem approach |  |
|  | Mandate: decision VI/12 Decision IV/1 B; decision II/8, para. 1; decision II/9; decision III/12, para. 6(b); decision III/19, annex, para 3; decision IV/1 B; and decision IV/1 A, para. 4;and anticipated decisions of COP 7. |  |
|  | Means: Compile case studies and national experiences; promote the approach through pilot projects and capacity building; collaborate with relevant organizations applying the approach or similar approaches e.g. Ramsar Convention, FAO, WWF, IUFRO, UNFF and CPF. Results: - Lessons learnt from case studies in all thematic programmes of work and relevant work on cross-cutting issues on application of principles and operational guidelines; - Integration of the approach in national biodiversity strategies and action plans, and similar plans and strategies across sectors; - Clarification of the concept with other similar concept used by our partners, using the model of the comparative study between ecosystem approach and sustainable forest management; - Dissemination of information and advice to Parties on the use of the ecosystem approach in implementing the Convention; |  |
|  | 3. Impact assessment |  |
|  | Mandate: Article 14.1, and articles 3 and 4 of the Convention; decision IV/10 C; decision V/13 and decision V/6; SBSTTA recommendation VII/10; decision VI/7 A, anticipated recommendations of SBSTTA 9; and anticipated decision of COP 7. Means: Compile and disseminate current experiences in environmental impact assessment (EIA) and strategic environment assessment (SEA) procedures that incorporate biodiversity-related issues, as well as experiences of Parties and other governments in applying guidelines; further develop and refine the guidelines; strengthening of capacities in areas relevant to EIA and SEA as well as other accompanying measures such as incentives, participation, legislative authority, and monitoring and auditing. Cooperate with International Association for Impact Assessment (IAIA), Ramsar Convention and other relevant organizations. Results: - Case studies on EIA and SEA and experiences integrating biodiversity-related issues compiled and disseminated through various means of communication including, inter alia, the clearing-house mechanism and national reporting; - Guidelines for the incorporation of biodiversity considerations in EIA and SEA incorporating all stages of the EIA and SEA processes taking into account the ecosystem approach (particularly principles 4, 7 and 8) finalized and implemented; - Human and institutional capacity building for EIA and SEA integrating biodiversity; - Memorandum of Cooperation with IAIA reviewed and implemented. |  |
|  | 4. Indicators, targets and baselines |  |
|  | Mandate: Articles 7 and 14 of the Convention, decisions II/8, III/10; and decision IV/1 A, paras. 3 and 4; decision II/9, annex para. 15; decision III/11, para. 15(m) (agriculture); decision III/12, para. 10(a), annex, first para. (c), second para. (a) (forests); decision IV/4, annex para. 15(c) (inland waters); decision IV/5, annex, op. obj. 1.3 (marine); decision IV/6, para. 6 (agriculture); decision IV/7, annex II, part 3 (paras. 40-49) (forests); decision II/17, annex, para. (j) (guidelines for national reports); SBSTTA recommendation VII/11, decision VI/7 B; and anticipated decisions of COP 7. Means: Expert meetings on time-bound and quantifiable targets for the implementation of the CBD; promotion of pilot programmes; development of training programme for the development of national-level monitoring programmes; collaboration with relevant organizations, such as UNEP-WCMC, Netherlands Institute for Health and Environment (RIVM), European Centre for Nature Conservation (ECNC), OECD; internet-based expert database on status and trends of taxonomic groups as indicators of ecosystem quality. Results: - Progress in the work of SBSTTA to provide further advice to Parties on indicators; - Establishment of programmes to develop and test indicators, and mobilization of financial and other appropriate resources for capacity building; - Establishment of programmes to provide training on the development and implementation of indicators; - Establishment of an internet-based expert database on status and trends of taxonomic groups as indicators of ecosystem quality and mobilization of funds and other appropriate resources for setting up and maintenance of database reimbursement of contributors. |  |
|  | 5. Global Taxonomy Initiative |  |
|  | Mandate: Article 7 and annex I; decision VI/ 8; decision III/10, paras. 3 (endorsement of SBSTTA Recommendation II/2) and 10 (guidance to the financial mechanism); decision IV/1 D; decision V/9; decision IV/4, annex, paras. 16 and 21 (inland waters); decision IV/5, annex para. 6 and op. obj. 6.2 (marine and coastal); decision IV/7, annex, paras. 42 and 44 (forest); decision II/8, para. 7 (components of biodiversity particularly under threat); decision III/5, para. 2(b) (guidance to the financial mechanism); decision IV/13, para. 2 (guidance to the financial mechanism); decision V/3, para 6 (e), Annex A (a), Annex B (marine and coastal); decision V/5, para 15 (b), Annex A, para 3 (c) (agriculture); decision V/8, para 14 (g), Annex II para 1(e) (alien species); SBSTTA recommendation VI/6 including the Programme of work for the Global Taxonomy Initiative (GTI). Means: Promoting country-driven projects; encouraging national and regional assessments of taxonomic capabilities in respect of CBD requirements in thematic areas and cross-cutting issues; developing cooperation between ex situ institutions in developing and developed country Parties; facilitating investments in building relevant capacities; developing the clearing-house mechanism; encouraging information availability; promotion of Pilot Projects; implementation of the programme of work. |  |
|  | Results: - In-depth review of the programme of work, taking into account items identified as priorities by the World Summit on Sustainable Development, such as human health, hotspots and other areas of biodiversity importance, including (i) information on taxonomic needs and capacities at national, regional and global levels, (ii) systems and infrastructure needed to obtain, collate and curate the biological specimens, (iii) improved and effective infrastructure/system for access to taxonomic information; (iii) key taxonomic objectives are integrated within the thematic work programmes and within the work on cross-cutting issues of the Convention to generate information needed for decision-making in conservation and sustainable use of biological diversity and its components (iv) the expected outputs listed under each of the 18 planned activities of the programme of work (Annex to decision VI/8); - State of progress, including obstacles, in achieving the goals of the Strategic Plan and the programme of work, - Contribution of the programme of work to the achievement of the Convention’s 2010 targets and the Millennium Development Goals; - Development/strengthening and implementation of national, regional, sub regional taxonomy initiatives, partnerships and institutions, based on the global initiative, in coordination with existing initiatives, such as the Global Biodiversity Information Facility and the clearing-house mechanism of the Convention (paras 3 and 4 of decision VI/8); - Dissemination and promotion of the GTI guide (para 5 of decision VI/8); - Strengthening of national and regional networks to aid the Parties in their taxonomic needs in implementing the Convention on Biological Diversity (para 6c of decision VI/8); - Strengthened capacity at the national and regional levels. |  |
|  | 6. Global Strategy for Plant Conservation |  |
|  | ###### Mandate: Decision VI/9 (paras. 1, 4, 8, 10) including the Annex on the strategy and its targets, with particular attention to paragraphs 14(b) and 16 to 20; decision VI/29, para. 30; annex II to the report of the MYPOW meeting (March 2003) on proposed in-depth review of the GSPC by COP-9; see also decision 12.11(n) and 12.12 of the 12th session of the COP to CITES; and expected decision by COP 7. |  |
|  | Means: Establish monitoring mechanisms such as global and regional liaison groups (e.g. liaison group meetings); compile case-studies and information; carry out studies; organize and service expert meetings as appropriate; maintain and foster further collaboration with relevant organizations; improve and maintain databases and Internet services; facilitate exchange of information and cooperation with Parties, other Governments and relevant organizations and stakeholders including those mentioned in para 14(b) and 19 of the annex to decision VI/9; implementation of the Memorandum of Cooperation with Botanic Gardens International (BGCI). |  |
|  | Results: - Memorandum of Cooperation with Botanic Gardens Conservation International reviewed and implemented, including the provision of a staff member seconded to SCBD (decision VI/29, para. 30); - Targets taken into consideration in the periodic reviews of the thematic and cross-cutting programmes of work of the CBD (decision VI/9, para.10(a)); - Flexible coordination mechanisms through for instance global and regional liaison groups (decision VI/9, annex, para. 20); - Ways and means developed, within the Convention’s thematic and cross-cutting programmes of work, for promoting implementation of the GSPC, and for monitoring and assessing progress (decision VI/9, para. 10(b)); - Development of national targets including sub-targets, milestones, baseline data, and monitoring mechanisms towards 2010 and their incorporation into relevant plans, programmes and initiatives, including national biodiversity strategies and action plans (decision VI/9, annex, para. 16); - Further refinement of the global targets and the development of sub-targets, activities and milestones; development of baseline data and a series of indicators in order to monitor progress towards achieving the targets toward 2010 (decision VI/9, annex, para. 17); - Development, establishment and monitoring of regional components of the Strategy through for instance regional workshops (decision VI/9, annex, para. 18); - Collaboration with a range of actors in the design, development and implementation of the strategy, including inter alia, in addition to Parties, international initiatives, NGOs, indigenous and local communities, the private sector (decision VI/9, annex, para. 19); - Dissemination of information, including on regional components, through the clearing-house mechanism and means including those of related partners institutions; - Identification of gaps where new initiatives are required and mobilization of necessary resources for globally significant actions and for capacity building of Parties to develop and monitor national targets (decision VI/9, para. 7; and annex, para. 2); - Report on the progress made in the implementation of the Global Strategy; - Report on the progress made in reaching the global targets (final review at COP9) (decision VI/9, para. 8; recommendation VIII/7, para. 8, annex (MYPOW)). |  |
|  | 7. Protected areas |  |
|  | Mandate: Article 8 of the Convention, decision VI/ ; decision IV/15, para. 6; decision IV/16; decision II/9, annex, para. 13, decision III/12; annex; paras. (a) and para. (f), decision IV/4, annex I, para. 8(c); decision IV/5, annex, para. 1 and part C, programme element 3; and decision IV/7, annex, paras. 3(h), 17 and 52. |  |
|  | Means: Carry out studies, compile case studies and information, develop databases, organize and service scientific and technical meetings as appropriate. Foster collaboration, in particular with protected area programmes, the IUCN World Commission on Protected Areas, the World Heritage Convention, UNESCO-MAB, Biosphere Reserves, Ramsar Convention, Convention on Migratory Species, regional ecological networks, and local and indigenous communities. . |  |
|  | Results (mainly based on the work of the AHTEG on protected areas): - Expansion and strengthening of the overall contribution of protected area systems to (i) the goal of the Strategic Plan of the Convention and the WSSD 2010 biodiversity target; and (ii) the Millennium Development Goals (MDGs); - Expansion of comprehensive and representative national systems of protected areas, including community conserved areas; - Integration of sites and national systems of protected areas into relevant sectors and broader landscapes, taking into account the ecosystem approach and the concept of ecological networks; - Strengthening of existing and establishment of new transboundary protected areas to enhance conservation of biological diversity, implement the ecosystem approach, and improve international cooperation; - Promotion of systematic, highly participatory and science-based site planning processes that lead to clear biodiversity objectives, targets, management strategies and monitoring programs, including inventory of habitats or species requiring protected areas; - Revision of legislation and regulatory measures to prevent and mitigate the negative impacts of key threats to protected areas, and use of suitable and rigorous impact assessments; - Measures and experience for the prevention of the introduction of invasive alien species that potentially threaten the biodiversity of protected areas, and the control and, where possible, eradication of established invasive species in protected areas; - Information on policy reforms, including use of social and economic valuation and incentives, to provide a supportive enabling environment for more effective establishment and management of protected areas and protected areas systems; - Increased communication, education, public awareness and understanding of the importance and benefits of protected areas; - Adoption of voluntary minimum standards and best practices for planning, selecting, establishing, managing and governance of protected area sites and systems; - Adoption and implementation of a framework for monitoring, evaluating and reporting protected areas management effectiveness at sites, national system, and transboundary protected area levels; - Regular assessment of national protected areas statistics, which will enable monitoring of protected areas status and trends at national, regional and global scales, and assist in evaluating progress in meeting global biodiversity targets; - Improved understanding of the biodiversity found in protected areas and the values, goods, and services they provide; - Synergy with other conventions and agreement promoting the use of protected areas; - Enhanced capacity for protected areas - Guidelines for inclusion of restoration and rehabilitation areas in ecological networks, in accordance with Article 8 of the Convention. |  |
|  | 8. Climate change and biodiversity |  |
|  | Mandate: Articles 6, 7 and 14 of the Convention, COP decisions VI/3 (marine and coastal biodiversity), 15 (incentives), 20 (cooperation with other bodies) 22 (forest biodiversity), and 23 (invasive alien species),; decisions V/3, 4 and 25, including all COP decisions referring to threats posed to biodiversity, in particular decisions V/6, 8and 21; and SBSTTA recommendations I/8, VI/2, 5 and 7; and expected decisions from COP 7. |  |
|  | Means: Compile information on actual and potential impact of climate change on biodiversity and on possible role of biodiversity in adaptation and mitigation measures; foster cooperation with UNFCCC and its IPCC, UNCCD and related agreements such as the Ramsar Convention and the Convention on Migratory Species, and organizations such as FAO, United Nations Development Program, the Global Environmental Facility, the United Nations Forum on Forests and other members of the Collaborative Partnership on Forests, IUCN, WWF, Greenpeace, the Nature Conservancy, the World Wildlife Fund, and the Millennium Ecosystem Assessment. |  |
|  | Results: - Implementation of approaches and wide use of tools integrating biodiversity considerations into the implementation of UNFCCC and the Kyoto Protocol; - Fostering the development and adaptation of management principles, tools and practices that enhance biodiversity’s capacity to mitigate climate change; - Consideration of climate change aspects that contribute to the conservation and sustainable use of biodiversity in all CBD programmes of work. - Case studies illustrating the potential of biodiversity both to mitigate and adapt to global climate change, and lessons from these experiences; - Information and experiences on the application of relevant tools, approaches and processes for designing and evaluating the economic, environmental and social implications of projects related to mitigating or adapting to climate change within the broader context of sustainable development; - A minimum set of environmental standards, and/or best practices that, if properly incorporated into national planning efforts, can help to design, monitor, and assess the impact of climate change mitigation and adaptation activities on biodiversity, including human societies; - Capacity building inter alia to equip countries and key stakeholders with the necessary information, tools and capacity to understand, negotiate and reach agreements under the Kyoto Protocol, to ensure that the resulting projects are balanced with respect to climate change and biodiversity considerations, and consistent with national priorities; - Enhanced knowledge on: (i) interactions between climate change and land-use change impacts on biodiversity, (ii) effects of atmospheric CO2 enrichment on productivity, species composition and carbon dynamics in different ecosystems; (iii) ecosystem resistance and resilience; (iv) capacity of species to disperse and evolve in response to climate change conditions, including development of data and models for the geographical distribution of species; (v) aspects that would provide a realistic projection of the future state of the Earth’s ecosystems, including in particular present and projected climate change impacts on soils and on coastal and marine ecosystems; - Enhanced use of the systematic application of environmental impact assessments, strategic environmental assessments, decision analytical frameworks, indicators and valuation techniques in the context of climate change and biodiversity; |  |
|  | 9. Migratory species |  |
|  | Mandate: Articles 7, 8, 10 and 18.3 of the Convention; COP decision VI/20, decision V/21; SBSTTA recommendation VI/8; and expected COP decisions inter alia on ecosystem approach; protected areas; and biodiversity and climate change.. Means: Continue compilation and dissemination through the CBD clearing house mechanism case studies on migratory species and their habitats taking into account the regional agreements and cooperation developed and to be developed under the CMS; develop and implement a capacity building programme and specific projects aimed at incorporating the conservation and sustainable use of migratory species and their habitats, particularly in accordance with the implementation of the joint programme of work. |  |
|  | Results: - Integration of migratory species considerations in NBSAPs and present and future CBD programmes of work in accordance with the joint work programme endorsed by COP (paras 17 and 21 of decision VI/20) - Implementation of the joint work programme between CBD and CMS - Enhanced capacity and sectoral and transboundary cooperation for migratory species programmes/projects (para 19 of ) - Compilation of case studies and their dissemination through the CBD clearing house mechanism (para 20) |  |
| Approved posts New posts required | P-4 GTI/Invasive Alien Species specialist, P-4 In situ and Ex situ Conservation. NB: Global strategy for Plant Conservation is under the Programme Officer for Agrobiodiversity; and Migratory species is under the Programme Officer for dry and sub-humid lands. In kind contribution: P-4 Global Strategy for Plant Conservation (Botanic Gardens Conservation International, UK; August 2003 to July 2005) Consultants: P-3 Ecosystem approach, and Biodiversity and climate change; G-7 Programme Assistant- Ecosystem approach, and Biodiversity and climate change |  |
| Resources from outside the core budget | BE Trust Fund Consultants: 2005: $20,000 2006: $0 Liaison groups or other types of formal consultations: 2 2005: $5,000 2006: $5,000 Workshops: 15 2005: 6x$60,000 2006: 9x$60,000 JPOs (P2): 1 for GTI |  |

C.  Social, Economic and Legal Matters (SEL)

(a)	Overall management

| Overview of responsibilities | Deputize for the Executive Secretary; Management of the SEL work programmes, coordinate support for relevant Convention bodies; act as Secretary of COP, of intersessional meetings, of the Working Groups on Access and Benefit-sharing and article 8(j); external representation; cooperate with relevant UN and other international organizations; identify emerging issues within the remit of the programme. |
| --- | --- |
| Expected results | 1. Staff, financial resources, and activities of the programmes are effectively managed. |
|  | Means: Identification of priorities for allocation of resources and raising of supplementary funds, as needed; recruitment and motivation of competent staff, appraisal of their performance and promotion of their career development; supervising; coordination and guidance of work by the programme officers; contribution, through the Secretariat's Management Committee, to overall Secretariat management, and to the establishment and application of Secretariat policies and procedures. |
|  | Results: Budgets and detailed work plans for each work programme and for the unit as a whole; unit fully staffed with competent staff/members; efficient implementation of SEL work programmes and smooth conduct of COP and other meetings. |
|  | 2. Meetings of the Ad Hoc Working Group on Article 8(j), the Ad Hoc Working Group on Access and Benefit-sharing, as well as workshops and expert meetings on incentives, tourism, as well as liability and redress, are provided the support and documentation necessary for their effective and smooth functioning. |
|  | Means: Act as Secretary for the meetings; Preparation of documentation; participation in sessional planning; coordination of inputs from other programmes; assisting with the servicing of meetings; provision of advice on specific topics to the chairs and mobilization of teams to provide the chairs and other elected officers with substantive support and secretarial assistance particularly during sessions and consultations. Results: Smooth conduct of meetings; Required documents submitted to relevant meetings and ultimately to the COP. |
|  | 3. Cooperation with other relevant organizations on SEL work programme |
|  | Means: Preparation of correspondence; convening of meetings and other gatherings, as appropriate; promotion and coordination of contact by units; participation in relevant conferences, seminars and workshops. Results: Exchange of relevant information between Convention bodies and competent international organisations and other conventions. |
|  | 4. Legal matters relating to the host country arrangements and other matters as required. |
|  | Means: Implementation of the Host Government Agreement between the Convention and the Government of Canada; managing day-to-day relations with the Government of Quebec; and undertaking reviews of pertinent legal issues, preparing legal briefs and opinions, and providing legal advice and support as required to the Executive Secretary, Convention bodies and other divisions of the Secretariat. Results: Effective arrangements with host country, and legal advice and support to the Executive Secretary, Convention bodies and Secretariat divisions. |
|  | 5. Effective participation on behalf of the unit in the Management Committee of the Secretariat |
|  | Means: Preparing as required internal documentation for effective decision-making; participating in meetings of the Committee, or organizing representation; conveying decisions of the Committee to staff of the SEL programmes; assume interim duties in absence of the Executive Secretary. Results: Effective coordination of the staff mostly for servicing meetings and on other substantive matters. |
| External linkages | Parties and Governments, CSD, UNGA, WTO, OECD, WIPO, UNCTAD, organizations representing local and indigenous groups, other relevant non-governmental organizations, academic and research institutes, press and media, other convention secretariats. |
|  | 6. Deputize for the Executive Secretary |
|  | Means: Acting as Officer-in-Charge of the Secretariat during absences of Executive Secretary Results: Effective and smooth functioning of the Secretariat during Executive Secretary absences |
| Approved posts | Principal Officer (D-1); GS-Secretary |
| Resources required | 1. Staff Costs: 2005:$1,098,300 2006: $1,131,200 2. Consultants: 2005:$ 25,000 2006: $ 25,000 3. Article 8(j) meeting 2005: $ 0 2006: $370,000 4. Ad Hoc Working Group on ABS 200 $250,000 2006: $0 5. Meeting Expert Groups 2005:$ 45,000 2006 $ 0 6. Travel on official business: 2005:$ 60,000 2006: $60,000 7. Temporary assistance and overtime 2005: $ 8,000 2006: $ 8,000 |
| Resources from outside the core budget | BZ Trust Fund Ad Hoc Open-ended Working Group on ABS 2005 : $540,000 |

- (b)	Access and benefit-sharing

| Overview of responsibilities | Implementation of the programme of work on access and benefit-sharing. |
| --- | --- |
| Expected results | 1. Assist in the implementation of COP decisions on access and benefit-sharing. |
|  | Mandate: Articles 1, 15, 16 and 19 of the Convention; decisions II/4, II/11, III/15, III/16, III/17, IV/8, V/26, VI/24 and anticipated decision from COP-7 Means: Collecting information on issues related to access and benefit-sharing, liaising with relevant inter-governmental and non-governmental organizations, Governments and the private sector regarding relevant developments and providing relevant input to other fora; providing support in discussions regarding the negotiation of an international regime on ABS; providing support in the implementation of the Action Plan on capacity-building for ABS; organising and servicing meetings as appropriate; maintaining the roster of experts; maintaining the database on existing ABS measures; maintaining the database on ongoing capacity-building projects related to ABS; disseminating relevant information through the clearing-house mechanism. |
|  | Results: - Meetings of the Ad Hoc Open-ended Working Group on Access and Benefit-sharing; - Support to negotiations of an international regime on ABS; - Support for the implementation of the Action Plan on capacity-building; - Roster of experts; - Database on ABS measures - Database on capacity-building projects for ABS; - Dissemination of relevant information through the clearing-house mechanism. |
|  | 2. Intellectual property rights. |
|  | Mandate: Articles 16, 19 and 15 of the Convention, decisions III/15, III/17, III/21, IV/8, IV/9, IV/15, V/26, VI/24 and anticipated decision of COP-7. |
|  | Means: To gather relevant information/documentation, organize and service meetings as appropriate; monitor developments in the WTO TRIPs Council, the WTO Committee on Trade and Environment; and monitor developments in the WIPO Intergovernmental Committee on Intellectual Property, Genetic Resources, Traditional Knowledge and Folklore; liaise with Secretariats of WIPO and WTO and other representatives of NGOs, Governments and the private sector working on these issues; examining relevant issues; prepare relevant documentation for meetings as required. |
|  | Results: - Observer status in the TRIPs Council; - Close collaboration with the WIPO and WTO Secretariats; - Appropriate information on intellectual property issues, particularly on WIPOs work, made available to WG on ABS; - Appropriate documentation prepared on issues related to IPRs and ABS arrangements for relevant meetings, as required. |
| Approved posts: | P-4 Programme Officer (existing P-3, Access and Benefit-Sharing). Increased workload and level of responsibility resulting from the adoption of the Bonn Guidelines and to further work on intellectual property rights, capacity-building and other approaches as well as the commitment at WSSD to negotiate an international regime on ABS within the framework of the CBD require upgrading of this post to P-4. GS Programme Assistant ABS |
| Resources from outside the core budget | BE Trust Fund Regional workshops on capacity-building for ABS in 2005 (3) and in 2006 (1). 2005: $200,000 2006: $80,000 |

- Economics, trade and incentive measures

| Overview of responsibilities | Assist in implementation of relevant COP decisions on incentive measures, trade and other economic aspects relevant for the implementation of the objectives of the Convention |
| --- | --- |
| Expected results | 1. Assist in the implementation of the COP programme of work on incentive measures. |
|  | Mandate: Article 11 of the Convention; decision V/15; decision VI/15; anticipated decision of COP 7. |
|  | Means: Organize and service meetings and prepare or oversee preparation of relevant documentation, including analytical studies and draft policy guidance, as appropriate for the further implementation of the programme of work; coordinate work with relevant organizations and experts, compile country-driven case studies, best practices and other relevant information on the utilization of incentive measures, in particular further information on perverse and positive incentives; disseminate relevant information through the clearing-house mechanism and other appropriate means. Results: - Appropriate documentation prepared; - Meetings organized and serviced; - Collected information made available to Parties, through the Clearing-House Mechanism and other means; |
|  | - Assist the further integration of work on incentives into thematic programmes and programmes on other cross-cutting issues, provide advice as appropriate with regard to other economic aspects of biological diversity. |
|  | Mandate: Articles 7, 10 and 14 of the Convention; decisions IV/4 annex 1; V/3 paragraph 13; V/23 annex 1; VI/5 annex 1; VI/22 annex 1; anticipated decisions from COP 7. Means: Give advice on economic issues as appropriate to the Executive Secretary and to Secretariat staff responsible for thematic programmes and programmes on other cross-cutting themes; provide input into relevant documentation as appropriate; liaise with relevant organizations and experts; collect information on and explore the applicability of different incentive measures in specific thematic and/or cross-cutting areas, taking the specific situation of developing countries into account; disseminate information through the clearing-house mechanism and other appropriate means. Results: - Advice given and relevant input delivered to thematic work programmes and to work programmes on other cross-cutting issues. |
|  | - Assist Parties in exploring the linkages and promoting synergies with international organizations/agreements focused on economic policies, in particular trade policies, as well as in exploring and exploiting potential synergies pertaining to economic aspects of implementation of other Multilaterial Environmental Agreements (MEAs) |
|  | Mandate: Articles 8(j), 11, 15, 22 and 24; decision III/17, paragraphs 4-6; decision IV/15, paragraphs 7-9, 17; decision VI/20; anticipated decision of COP 7. |
|  | Means: Liaise with relevant organizations such as OECD, UNCTAD and the WTO, including their relevant bodies, as well as relevant MEAs such as CITES, Ramsar, UNFCCC; compile information on the relationship of trade liberalization, biological diversity and biosafety as well as on the relationship between the provisions of the multilateral trading system and the objectives of and the mechanisms envisaged under the Convention; explore possible synergies and mutual supportiveness between the objectives of the Convention and trade policies; explore the interaction and possible synergies between the objectives of the Convention, and in particular its provision on incentive measures, and the implementation of other MEAs; promote possible synergies, when appropriate and feasible, in relevant international meetings and workshops; disseminate relevant information as appropriate and provide relevant expertise to other work programmes. Results: - Relevant studies and other information collected, analyzed and made available as appropriate; - Relevant meetings attended, possible synergies of the Convention and the work programmes of other relevant international organizations and MEAs explored and, where appropriate and feasible, promoted; - Relevant input to other work programmes provided. |
| Approved posts | P-4 Programme Officer (Economist); GS Programme Assistant (50 %). |
| Resources from outside the core budget | None |

(d)	Technology transfer

| Overview of responsibilities | Assist in implementation of relevant COP decisions on technology transfer and cooperation |
| --- | --- |
| Expected results | 1. Assist in the implementation of the COP programme of work on technology transfer and cooperation |
|  | Mandate: Articles 16, 18 and 19 of the Convention; anticipated decision of COP 7. |
|  | Means: Organize and service meetings and prepare or oversee preparation of relevant documentation, including analytical studies and draft policy guidance, as appropriate for the implementation of the first phase of the programme of work; establish and coordinate work with relevant organizations and experts, compile country-driven case studies, best practices and other relevant information on various aspects of technology transfer as spelled out in the programme of work, with a view to identify tools and mechanisms for technology transfer and cooperation; disseminate relevant information through the clearing-house mechanism and other appropriate means. Results: - Appropriate documentation prepared; - Meetings organized and serviced; - Collected information analyzed and made available to Parties, through the Clearing-House Mechanism and other means. |
|  | 2. Assist in establishing the Clearing House Mechanism of the Convention as an international gateway for information on technologies for conservation and sustainable use of biodiversity, or that make use of genetic resources. |
|  | Mandate: Articles 16, 17, 18 and 19; decision V/14 annex 2; anticipated decision from COP 7. Means: Cooperate closely with responsible Secretariat staff with a view to developing options and mechanisms for establishing the Clearing House Mechanism as an international gateway for information of relevant technologies; provide input into relevant documentation as appropriate; compile information of relevant technologies, both proprietary and in the public domain, including information on traditional technologies and information on relevant technology databases at national and international levels; liaise with relevant organizations and experts at national and international levels with a view to explore and exploit potential synergy. Results: - Relevant technologies and technology databases identified; - Contacts with relevant organisations established, synergies identified; - Options to establish Clearing House Mechanism as information gateway for technology transfer developed; input into relevant documentation provided as appropriate. |
|  | - Assist the implementation of provisions on technology transfer and cooperation in relevant thematic programmes and programmes on other cross-cutting issues. Mandate: Articles 16, 18 and 19; decisions III/16 in conjunction with SBSTTA recommendation II/3; II/10 annex 2; IV/4 annex 1; VI/9, annex; VI/22 paragraphs 16, 19, annex; VI/23, annex; VI/25, annex 2. Means: Provide advice to Secretariat staff responsible for thematic programmes and programmes on other cross-cutting themes and provide input into relevant documentation as appropriate, with a view to ensuring integration of technology transfer considerations in other work programmes; liaise with relevant organizations and experts; collect information on technologies, technology databases and other relevant information, e.g., on policy measures for enabling environments for technology transfer as applicable in specific thematic and/or cross-cutting areas, including traditional technologies and issues of south-south technology transfer; disseminate information through the clearing-house mechanism and other appropriate means. Results: Advice provided and relevant input delivered to thematic work programmes and to work programmes on other cross-cutting issues. |
| New posts required | P-3 Programme Officer; GS Programme Assistant (50 %). |

(e) 	Island biodiversity, sustainable use and tourism

| Overview of responsibilities | Development and implementation of the island biodiversity thematic programme of work and implementation of decisions on sustainable use, including tourism, taking into account relevant developments in other forums. |
| --- | --- |
| Expected results | - To develop and assist in implementation of the island biodiversity programme of work. Mandate: Preamble and para 6 of Art. 20 of the CBD; Recommendation of Open-ended intersessional meeting on the MYPOW; SBSTTA recommendation VIII/2, 3B and 7; decisions VI/ 3, 5, 9, 10, 17, 19, 22, 23. Means: Carrying out studies, compiling case-studies and information, developing databases, organizing and servicing scientific and technical meetings as appropriate: fostering collaboration, in particular, with ICRI and its partners, UNEP regional seas programmes, UNESCO Intergovernmental Oceanographic Commission, FAO; IAIA. Results: 1. Status and trends of and threats to, biodiversity, taking into account in particular the impact of tourism development, and introduction and spread of invasive alien species on biodiversity and livelihoods; - Identification of issues of overarching importance, particularly the relevant socio-economic issues identified by the World Summit on Sustainable Development; - Strategies towards the achievement of the 2010 targets of significantly reducing the rate of biodiversity loss, and other targets (MDG and WSSD Plan of Implementation), including development of global targets and related measures, such as monitoring and indicators; - Development of mechanisms to support implementation e.g. financial mechanism, clearing-house mechanism, technology transfer, capacity-building (including inter alia para 5e (on application of guidelines for rapid assessment of inland water biodiversity) and para 5g (on practical training for the application and adaptation of these rapid assessment methods) of SBSTTA recommendation VIII/2); - Consideration of specific situation of small island states in the implementation of the thematic programmes of work and work on cross-cutting issues, including inter alia: - Implementation of para 2 of decision VI/3: work plan on coral bleaching; and implementation of para 25 of SBSTTA recommendation VIII/3 on enhancing capabilities for, and establishment and maintenance of, marine and coastal protected areas and their networks; - paras 12 and 16 of decision VI/5: on International Pollinators Initiative and assessment, conservation and sustainable use of world’s animal genetic resources; - paras 6 and 7 of decision VI/9and target 15 on capacity for implementing the Global Strategy for Plant Conservation; - paras 18 and 42 of decision VI/10 on capacity conduct cultural, environmental and social impact assessment regarding developments proposed to take place on, or which are likely to impact on, sacred sites and on lands and waters traditionally occupied or used by indigenous and local communities; and on for the establishment and maintenance of mechanisms to protect traditional knowledge at national and subnational levels, and for building the capacity of indigenous and local communities to develop strategies and systems for the protection of traditional knowledge - para 8 of decision VI/15 on incentive measures - para 10 d, f, g and h of decision VI/17on financial mechanism: - para 3b of decision VI/19on development of adequate capacity to deliver initiatives on communication, education and public awareness; - para 17 of decision VI/22 on capacity and technology transfer for the implementation of the programme of work on forest biodiversity: - paras 19, 31 an 34 of decision VI/23 on capacity and implementation of programmes on invasive alien species: - paras 5 and 11e, g, h and k of decision VI/24 on capacity for implementing the Bonn Guidelines on Access to Genetic Resources and Fair and Equitable Sharing of the Benefit Arising out of their Utilization - migratory species (para 18 of decision VI/20) - Programme of work on biodiversity of small island States |
|  | 2. To facilitate the implementation of the principles and guidelines for the sustainable use of biodiversity and to assess the applicability and status of the implementation of such guidelines. . Mandate: Article 1 and 10 of the Convention, decision V/24, VI/13 and anticipated decision of COP-7. Means: Develop ways and means to further integrate sustainable use in NBSAPs and into sectoral and cross-sectoral plans, programmes and policies taking into account the need to alleviate poverty and linkages with programmes on indicators, incentives and ecosystem approach; disseminate the principles and guidelines for the sustainable use of biodiversity; gather relevant information on experiences and lessons learned for the further improvement of the principles and guidelines; assemble and compile case studies on the implementation of the principles and guidelines. Results: Dissemination of principles and guidelines, availability of case studies, integration of principles and guidelines into CBD programmes and NBSAPs and various sectors and programmes. |
|  | 3. To undertake further research, in collaboration with relevant organizations, on issues pertaining to the sustainable use of biodiversity and investigate how sustainable use can contribute to the achievement of the biodiversity target. Mandate: Article 1 and 10 of the Convention, decision V/24, VI/13 and anticipated decision of COP-7. Means: Collect and disseminate information on appropriate technologies for sustainable use and on how sustainable use can contribute to the achievement of the biodiversity target of significantly reducing the rate of biodiversity loss by 2010; and investigate a series of issues, including: - the impacts of sustainable use and non sustainable use on livelihoods, and ecosystems goods and services; - the role of women in the sustainable use of biodiversity; - the relationship between resilience of ecosystems and the sustainable use of biodiversity; - use of terms, management plans and the applicability of the principles and guidelines on the use of components subject to multiple jurisdictions; the functional relationship between different components of biological diversity in the context of sustainable use. Results: Availability and dissemination of results. |
|  | 4. To promote and facilitate the implementation of the CBD guidelines on biodiversity and tourism and to assess the applicability and status of the implementation of such guidelines. . |
|  | Mandate: Articles 10 and 11 of the Convention, decision V/25, VI/14 and anticipated decision of COP-7 Means: - Development of a user’s manual, a checklist and a streamlined and user-friendly core set of voluntary guidelines; - Preparation of a glossary of terms used in the guidelines; - Gathering and compilation of case studies on the implementation of the guidelines; - Gathering and compilation of best practices and lessons learned on the involvement of indigenous and local communities in sustainable tourism and eco-tourism projects; - Gathering and compilation of information on the implementation of pilot projects. |
|  | Results: Availability of the manual, checklist, streamlined set of guidelines and relevant case studies to all Parties. |
|  | 5. To represent the SCBD in the CSD and in other relevant forums, as appropriate, with regard to implementation of the CSD decisions on tourism and the dissemination of the CBD guidelines on biodiversity and tourism. |
|  | Mandate: Articles 10 and 11 of the Convention, decisions IV/15, IV/16, V/25 and VI/14 and anticipated decision of COP-7. |
|  | Means: Liaise with DESA, the World Tourism Organization and UNEP/DTIE; support representation at relevant meetings and workshops for the dissemination of the CBD guidelines; promote the work under the CBD and the guidelines within the CSD. |
|  | Results: To ensure that implementation and follow-up to the World Ecotourism Summit and WSSD decisions on sustainable tourism fully incorporates the guidelines developed by the Convention and relevant decisions of the COP and ensure that CBD guidelines are integrated by other relevant processes. |
| Approved posts: | P-4 Programme Officer (existing P-3, Sustainable Use and Tourism) Island Biodiversity, Sustainable use and tourism. Increased workload and level of responsibility resulting from addition of a new work programme (island biodiversity) require upgrading of this post to P-4. GS – Programme Assistant Sustainable Use and Tourism (50%) |
| New posts required: | None |
| Resources from outside the core budget | BE Trust Fund Consultant for the development of the manual 2006:US $ 10,000 Consultant to undertake research on sustainable use issues 2006: US $ 30,000 |

(f)	Traditional knowledge (Article 8(j) and related provisions)

| ### Overview of responsibilities | Implementation of the programme of work on traditional knowledge, innovations and practices. (Article 8 (j) and related provisions). |
| --- | --- |
| ### Expected results | 1. Assist in the integration of relevant tasks of the programme of work into the thematic programmes of the CBD. ## Mandate: Articles 8(j), 10(c), 17.2 and 18.4 of the Convention; decisions III/14, IV/9, the programme of work of decision V/16, and decisions VI/10A and VI/5. Means: Development and collection of information relevant to the tasks and implementation of the programme of work; solicit information from Parties, Governments, I/LCs and other relevant organizations, consult with the liaison group on Article 8(j) and related provisions. In collaboration with the Secretariat of the Commission on Genetic Resources for Food and Agriculture of the FAO, examine the implications of the International Treaty on Plant Genetic Resources for Food and Agriculture (ITPGRFA) on the issues under Article 8(j) and related provisions. Analyse relevant national reports and document progress made by Parties in each of the thematic areas dealt with under the CBD. Liaise with STTM and the AHTEG on GURTs to further analyse the potential impacts of GURTs on smallholder farmers, indigenous and local communities and on Farmers’ Rights, and also provide advice on indigenous and local community (I/LC) participation in the meetings of the AHTEG. Results: Prepare relevant documentation for the Ad Hoc Open-ended Intersessional Working Group on Article 8(j), as requested by COP 7 for the further development of. - the implications of the ITPGRFA on the issues under Article 8(j) and related provisions - the integration of relevant tasks of the programme of work on Article 8(j) and related provisions into the thematic programmes of the CBD; and - the potential impacts of GURTs on smallholder farmers, indigenous and local communities and on Farmers’ Rights. |
| # Expected Results | 2. Assist in the development and implementation of the second phase of the programme of work. ## Mandate: Articles 8(j), 10(c), 17.2 and 18.4 of the Convention; decisions III/14, IV/9, second phase of the programme of work of decision V/16, and decision VI/10B. Means: Development and collection of information relevant to the tasks and implementation of the second phase of the programme of work outlined in decision V/16; solicit information from Parties, Governments, indigenous and local communities (I/LCs) and other relevant organizations, consult with the liaison group on Article 8(j) and related provisions; establish and maintain a roster of I/LC experts. Results: Documentation for the meeting of the Ad Hoc Working Group on Article 8(j) and Related Provisions; liaise and consult with Parties and liaison group on Article 8(j), CHM and STTM; develop a Roster of I/LC experts. |
|  | 3. Carry out work on the second phase of the composite report on status and trends in relation to Article 8(j) and related provisions and assist in its implementation; assist in the development and implementation of the second phase of the report. ## Mandate: Articles 8(j), 10(c), 17.2 and 18.4 , Decisions III/14, IV/9, task 5 of the programme of work of decision V/16, and decision VI/10C. Means: Compile and synthesize information and studies from existing sources including national reports, submitted by parties, Indigenous and local community organizations and relevant institutions. Engage and supervise a regionally representative team of consultants to carry out desk top study on status and trends regarding knowledge, innovations and practices of indigenous and local communities as outlined in the second phase in decision V/10C. Prepare Terms of Reference. Oversee the coordination and drafting of the reports. Collation and synthesis of regional report. Results: Composite report and recommendation on the status and trends in relation to article 8(j) and related provisions. Relevant studies and other information collected, analyzed and made available through the CHM. |
|  | 4. Assist in the implementation of COP decisions pertaining to Article 8(j) and related provisions. Mandate: Articles 8(j), 10(c), 17.2 and 18.4 of the Convention; decisions III/14, IV/9, V/16, and VI/10, and anticipated decision at COP 7. Means: Prepare relevant documentation as requested for the implementation of the programme of work. Coordinate and liaise with relevant indigenous and local community and other organizations and experts as well as Parties. Collect information to assist in the preparation of documents. Providing support in the further development of the guidelines on cultural, environmental and social impact assessment; further collaboration with environmental secretariats to develop a multi-convention approach for the participation and involvement of indigenous and local communities; consult with parties and relevant funding institutions to further establish and secure potential source of funding for the participation of Indigenous and local community to meetings held under the convention and work in collaboration with CHM to develop further an appropriate communication network. Results: - Documentations for the Ad Hoc Open-ended Intersessional working Group on Article 8(j) and related provisions. - Meetings of the Ad Hoc Open-ended Working Group on Article 8(j) and Related Provisions. - Further development of a multi-convention mechanism such as guidelines or a set of principles for the participation of indigenous and local community in the conservation and management of biodiversity and the environment as well as their involvement in meetings under relevant environmental conventions. - Guidelines or a set of principles for the participation of indigenous and local communities to meetings held under the framework of the Convention. - Further development for the inclusion of the guidelines on cultural, environmental and social impact assessment within environmental legislation and processes and in strategic environmental assessment. - Representation and participation of Indigenous and local communities on national and sub-national bodies created to oversee development in which they have an interest; - Development of a culturally appropriate communication network within the CHM. |
|  | 5. Suggested elements for a sui generis system for the protection of traditional knowledge, innovations and practices relevant for the conservation and sustainable use of biological diversity. ## Mandate: Articles 8(j), 10(c), 17.2 and 18.4 of the Convention; decisions III/14, IV/9, tasks 11 and 12 of the programme of work of decision V/16, and VI/10F. Means: Collection of information on existing contractual arrangements and draft agreements concerning access and use of TK and equitable sharing of benefits between I/LCs and Governments, the private sector and research institutions; compile and synthesize relevant information and cases studies regarding strategies to protect TK (use of existing IPRs, sui generis systems, customary law, contractual arrangements, TK registers/databases, and codes of practice); liaise with the ABS Programme Officer; liaise with the WIPO Intergovernmental Committee on Intellectual Property and Genetic Resources, Traditional Knowledge and Folklore; liaise with Parties, other Governments, relevant organizations, including I/LC organizations; and consult with the I/LC liaison group on Article 8(j). Results: Documentation for the Ad Hoc Working Group on Article 8(j) and Related Provisions addressing the issue of sui generis systems for the protection of TK with respect to clarification of relevant terminology; existing and proposed sui generis systems; role of TK registers/databases in protecting TK; equitable sharing of benefits arising from use of TK; and suggested elements for sui generis legislation for the protection of TK relevant for the conservation and sustainable use of biological diversity. |
| Approved posts: | 1. P-4 Programme Officer (Traditional knowledge); 2. GS-Programme Assistant |
| Resources from outside the core budget | BZ Trust Fund - Ad Hoc Open-ended Working Group on Article 8(j) and related provisions meeting February 5 days.- meeting and developing country participation 2006: $540,000. - Participation of indigenous and local communities in meetings held under the Convention 2005-2006 $200,000 BE Trust Fund - Liaison Group workshop to meet once before COP 8 – 2005 $20,000; - Completion of phase 2 of the Composite Report – $120,000 |

##### D.  Implementation and Outreach (I & O)

(a)	Overall management

| Overview of responsibilities | Management of the programme, coordinate support for inter-sessional review meetings facilitating the implementation of the Convention, external representation, identify emerging issues within the remit of the division. |
| --- | --- |
| Expected results | 1. The programme's staff, financial resources, and activities are effectively managed. |
|  | Means: Identification of priorities for allocation of resources and raising of supplementary funds, as needed; recruitment and motivation of competent staff, appraisal of their performance and promotion of their career development; coordination and guidance of work by the units; contribution, through the Secretariat's Management Committee, to overall Secretariat management, and to the establishment and application of Secretariat policies and procedures. Results: Budgets and detailed work plans for each unit; programme fully staffed with competent individuals. |
|  | 2.Inter-sessional review meetings, such as ISOC and MSP, are provided with the support and documentation necessary for their smooth functioning. |
|  | Means: Preparation of procedural documentation; coordination of inputs from other programmes; provision of advice to the presiding officer as required and mobilization of teams to provide the presiding officer and other elected officers with substantive support and secretarial assistance during sessions and consultations. Results: Required documents submitted to intersessional review meetings; well organized meetings as required. |
|  | 3. The various components of the programme cooperate with organizations, bodies, processes and persons competent in matters within the remit of the division. |
|  | Means: Liaison and maintenance of regular consultation and correspondence; convening of meetings and other gatherings, as appropriate; promotion and coordination of contact by units; participation in conferences, seminars and workshops. Results: Exchange of relevant information between Convention bodies and external processes. |
|  | 4. Effective participation on behalf of the programme in the Management Committee of the Secretariat |
|  | Means: Preparing as required internal documentation for effective decision-making; participating in meetings of the Committee, or organizing representation; conveying decisions of the Committee to staff of the implementation and outreach programme. Results: Effective coordination of the staff mostly for servicing meetings and on other substantive matters. |
| External linkages | Parties and Governments, UN bodies, other intergovernmental organizations, bilateral and multilateral funding institutions, GEF and its implementing agencies, relevant non-governmental organizations, academic and research institutes, press and media, other convention secretariats, educational and curriculum development institutions, electronic communications networks, major groups, including the private sector, and the general public. |
| Approved posts: | D-1 –Principal Officer; P-5 Senior Programme Officer; GS-Secretary. |
| Resources required | 1. Staff Costs: 2005: $740,500 2006: $762,700 2. Consultants: 2005: $ 25,000 2006:$ 25,000 3. Travel on official business: 2005: $60,000 2006: $60,000 4. Global Biodiversity Outlook (GBO) 2005: $0 2006: $100,000 5. Information materials/Handbook 2005: $160,000 2006: $100,000 6. Library Acquisitions 2005: $25,000 2006: $ 25,000 6. Temporary assistance and overtime 2005: $8,000 2006: $8,000 |
| Resources from outside the core budget | BZ Trust Fund Meeting on the Multi-year Programme of work upto 2010 (MYPOW) Developing Country participation 2005: $240,000 BE Trust Fund 3 CHM Regional Workshops (LAC; Africa; EEC) 2005: $200,000 1 CHM Regional Workshop (Asia) 2006: $80,000 |

(c)	Communication, education and public awareness

| Overview of responsibilities | Support the implementation of the programme of work for the Global Initiative on Communication, Education and Public Awareness (CEPA) focusing on consolidating and strengthening: - A global communication, education and public awareness network; - Exchange of knowledge and expertise; and - Capacity building for communication, education and public awareness: Support the implementation and achievement of the provisions of other relevant decisions concerning the Global Initiative on Communication, Education and Public Awareness (CEPA) in consultation with Consultative Working Group of Experts on CEPA. |
| --- | --- |
| Expected results | - An operational and effective global communication, education and public awareness network. Mandate: Article 13 of the Convention and decision VI/19. Means: Enhancement of the electronic portal and an alternative information dissemination mechanism towards the establishment of a global network on communication, education and public awareness, building on, where possible, existing initiatives. Identify additional potential partners and stakeholders through the expansion of a registry of education and communications experts, organizations and networks (governmental; non-governmental; indigenous; religious; sectoral - business and industry, agriculture, fisheries, forests, tourism; media). Results: The communication, education and public awareness global network for networking is operational further strengthened and linked to the clearing-house mechanism; Regularly updated lists of networks and contact addresses, available on the Internet and on CD-ROMs; Enhanced communication and knowledge exchange nationally and regionally |
|  | - Enhanced exchange of knowledge and expertise to meet the needs of Parties and other stakeholders Mandate: Article 13 of the Convention and decision VI/19. Means: Documentation and analysis of national reports from the Parties on communication, education and public awareness to develop and implement appropriate interventions to address identified needs for communication, education and public awareness support; Further identification of links and provision of searchable means to access biodiversity knowledge through the clearing-house mechanism; Further research, collection and exchange of communication, education and public awareness projects and case-studies through the world Wide Web, workshops, CD-ROMs, and publications; Sharing of knowledge about tools and criteria for best practices; Provision of copyright free graphics and materials, subject to available funding, for adaptation; and development of the global network in programme 1 above to facilitate the above actions. Results: Updated suite of biodiversity communication and education solutions for practitioners and parties and stakeholders; Professional exchange of expertise enhanced and made more accessible. |
|  | - Collaborative efforts to support the implementation of other provisions of decision VI/19 Paragraph 4., the Strategic Plan, the achievement of the 2010 target and the Millennium Development Goals (MDGs). Mandate: Article 13 of the Convention and decision VI/19, para. 4. In addition, decision VI/26. Means: In collaboration with the Consultative Working Group of Experts on CEPA (UNESCO, UNEP, IUCN, WWF and other experts: Continue to monitor and evaluate the implementation of the Global Initiative for its follow-up phases and report regularly on its implementation to the meetings of the Conference of the Parties; Support the implementation of the communication, education and public awareness dimensions of existing and new cross-cutting issues and thematic areas, and specifically those priorities and action plans established in the Strategic Plan for the Convention; continue to promote, in collaboration with the relevant agencies, the development and implementation of demonstration projects that can serve as models to initiate similar projects that can be adopted by Parties; Seek the submission of relevant case-studies on biodiversity communication, education and public awareness from relevant sources; strengthen the implementation of the corporate communication strategy for the Secretariat. Support and publicise the implementation and progress of activities aimed at achieving the 2010 target and the Millennium Development Goals (MDGs) Results: enhanced understanding and awareness about the outcomes of the implementation process of the Global Initiatives and their contributions to the convention process and the Strategic Plan; wider access to and utilization of outputs and outcomes of the CEPA dimensions of the thematic areas and cross cutting issues; application of appropriate models and best practices developed from demonstration projects and case studies; and dissemination of appropriate promotional materials, products and services generated from an operational and effective communication strategy for the Secretariat; wider dissemination of promotional materials on progress achieved towards meeting the 2010 target and the MDGs. |
| Approved posts: | G-6 Programme Assistant |
| New posts required: | P-3 Programme Officer - Education and Training |
| Resources from outside the core budget | None |

(d)	Financial Matters

(i) Financial resources

| Overview of responsibilities | Support implementation of the provisions of the Convention on financial resources, including exploration of national financial measures, increased collaboration with bilateral, regional and multilateral funding channels, and promotion of the involvement of private sector |
| --- | --- |
| Expected results | 1. Identification and monitoring of financial resources in support of the Convention Mandate: Article 20 of the Convention and decisions I/2, II/6, III/6, IV/12, V/11 and VI/16 Means: Monitoring of financial resources provided other than through the financial mechanism; exploration of ways and means for mobilizing and channelling financial resources; assistance to developed country Parties in compiling standardized information on their financial support for the objectives of the Convention; assistance to funding institutions to compile financial information relating to the Convention; assistance to funding institutions in providing information on ways in which their activities support the Convention; identification of where and how developing country Parties might gain access to financial resources; monitoring of specific funding programmes of various funding institutions that are related to the elements of the programme of work of the Convention; assistance, where appropriate, in country dialogues of interested funding institutions; awareness-raising on the need to provide resources to support the elements of the programme of work Results: Publication of Guide to Sources of International Assistance for Biological Diversity, and Access to Funding Institutions and Development Agencies, and Introduction to the Operations of the Financial Mechanism; Updated database on financial resources in support of the Convention; system of information exchange for Parties; workshops on resources identification, mobilization and management; publications; reports to COP. |
|  | 2. Collaboration with relevant international organizations and funding institutions Mandate: Articles 20 and 21, para. 4, of the Convention and decisions II/6, III/6, IV/12, V/11 and VI/16 Means: Exploration of possible ways of collaborating with funding institutions to facilitate their efforts to achieve greater support for the Convention; coordination of the establishment of focal points system for financial resources; facilitation of consideration of strengthening existing financial institutions to provide financial resources for the Convention; promotion of efforts of funding institutions to make their activities more supportive of the Convention; convening of a workshop on biodiversity finance to facilitate the sharing of information, experience and knowledge; study on characteristics specific to biodiversity activities and their implications to funding decisions; establishment of reporting relationship between the Convention and funding institutions and relevant international organizations; promotion of coordination, coherence, and synergies in financing for biological diversity; sharing of information including success stories and best practices of utilizing available financial resources; centralization of information on biodiversity related activities of funding institutions and other donors. Results: Electronic platform on financing for biological diversity; publication of An Introduction to Funding Guidance of the Convention on Biological Diversity, and Database of Biodiversity-related Projects in Developing Countries around the World; system of information sharing between funding institutions; workshops on financing for biological diversity; reports to COP. |
|  | 3. Exploration of financial measures in support of the national implementation of the Convention Mandate: Article 20, paragraph 1; decisions IV/12, V/11 and VI/16. Means: Promotion of sharing of experience and knowledge on financial measures between Parties; development and promotion of guidelines on financial measures in support of the national implementation of the Convention; convening capacity building workshops on financial measures and project formulation and implementation; synthesis and dissemination of national experience on financing for biological diversity; development of new financial instruments for implementation of the Convention; assistance in the review of national budgets and monetary policies to promote conservation and sustainable use of biological diversity; development and implementation of global and regional projects to support the implementation of various programmes of work of the Convention, compilation of information concerning debts and biodiversity. Results: Projects supporting the implementation of the programme of work; focused database on financial measures in support of national implementation of the Convention; information sharing on national funding measures and debt versus biodiversity; workshops to promote capacity building on project development and implementation; reports to COP. |
|  | 4. Promotion of the involvement of private sector in the implementation of the Convention Mandate: Articles 20 and 21 of the Convention and decisions III/6, IV/12, V/11 and VI/16. Means: Development of a global initiative on banking, business and biodiversity; promotion of biodiversity consideration by private funding institutions in collaboration with UNEP financial-sector initiatives; promotion of biodiversity efforts of charitable institutions; monitoring of national measures to promote the involvement of private sector; international workshops on private sector financing to support the Convention and the global initiative on banking, business and biodiversity. Results: Establishment of the global initiative on banking, business and biodiversity; database on private financial resources in support of the Convention; information-sharing with Parties and private sector; international workshops on private sector financing; reports to COP. |
| Approved post | P-4 Programme Officer (Financial resources and instruments); G-7 Programme Assistant (50%) |
| New post required | None |
| Resources from outside the core budget | None |

(ii) Financial mechanism

| Overview of responsibilities | Support implementation of the Convention by undertaking tasks assigned to the Secretariat in respect of financial mechanism, including development and promotion of implementation of guidance for the financial mechanism, elaboration of further guidance, and review of the effectiveness of the financial mechanism |
| --- | --- |
| Expected results | 1. Management of the relationship with the financial mechanism of the Convention Mandate: Articles 20.2, 21 and 39; decisions I/2, II/6, III/5, III/8, IV/11, IV/13, V/12, V/13, and VI/17 Means: Monitoring of activities of the financial mechanism in relation to the COP guidance; liaison with the financial mechanism and Parties with respects to matters relating to the financial mechanism; consultation with the financial mechanism on its biodiversity proposals, funding strategy, operational programmes, policy and criteria, project cycle management, and funding portfolio; participation in relevant technical and policy-making meetings; assessment of the amount of amount of funding required to assist developing country Parties to implement the Convention as maybe requested by the Conference of the Parties, and participation in the GEF replenishment process. Results: GEF Council decisions, GEF policy documents, biodiversity projects, reports to COP. |
|  | 2. Elaboration of guidance to the financial mechanism Mandate: Decisions IV/11, V/13 and VI/17 Means: Study on development of further guidance in relation to previous guidance; monitoring of implementation of COP guidance; compilation of recommendations for further guidance for consideration by the COP; consultation with the financial mechanism on recommendations for further guidance; liaison with Parties with respect to matters relating to further guidance Results: Advice to the Parties; reports to COP; exchange of views with GEF |
|  | 3. Implementation of COP decisions on the review of the effectiveness of the financial mechanism Mandate: Article 21 of the Convention, and decisions I/2, II/6, III/7, IV/11, V/12 and VI/17 Means: Development and implementation of terms of reference for the review of the effectiveness of the financial mechanism; liaison with GEF and Parties on matters relating to the effectiveness of the financial mechanism; invitation for submission of information and views from Parties, relevant intergovernmental and non-governmental organizations; selection of evaluators; assistance to development of questionnaire, desk reviews, interviews and site visits; country and thematic case-studies; collaboration with the GEF monitoring and evaluation programme; participation in relevant workshops. Results: Communications with Parties, country and thematic case-studies, support to evaluation processes, workshops, reports to COP |
| Approved post: | P-4 Programme Officer (Financial resources and instruments); G-7 Programme Assistant |
| New post required: | None |
| Resources from outside the core budget | BE Trust Fund 2005: Workshop on the Financial Mechanism $80,000 2005: Advisory Group on the Financial Mechanism $20,000 |

E.  Biosafety (BS) *

(a) 	Overall management

| Overview of responsibilities | Assist the Executive Secretary in overall coordination and management of the programme; preparation and servicing of the meetings of the COP/MOP; coordination of support to COP/MOP and COP on relevant matters; external representation; identify and guide development of work on emerging issues within the remit of the programme. |
| --- | --- |
| Expected results | 1. Management of staff, financial resources, and activities in a way that maximizes fulfilment of needs identified by the Biosafety Protocol bodies, and contributes to the overall management and effective operation of the Secretariat. |
|  | Means: Identification of priorities for allocation of resources and raising of supplementary funds, as needed; recruitment and motivation of competent staff, appraisal of their performance and promotion of their career development; coordination and guidance of work by the programmes and subprogrammes; contribution, through the Secretariat's Management Committee, to overall Secretariat management, and to the establishment and application of Secretariat policies and procedures. |
|  | Results: Budgets and detailed work plans for each programme and sub-programme; unit fully staffed with competent individuals. |
|  | 2. COP/MOP, COP and their Bureaux are provided with the support and documentation necessary for their smooth functioning. |
|  | Means: Preparation of necessary documentation, including in-session, to be submitted to COP/MOP and to COP, coordination of inputs from other programmes as necessary; support the organization and servicing of COP/MOP Bureau meetings; provision of advice to the Chair of the COP/MOP and mobilization of teams to provide the Chair of the COP/MOP and other elected officers with substantive support and secretarial assistance during sessions and consultations. Results: An annotated agenda for, and report of, each session of COP/MOP; required documents submitted to COP/MOP and its subsidiary bodies, well organized Bureau meetings as required. |
|  | 3. Effective participation on behalf of programme in the Management Committee of the Secretariat |
|  | Means: Preparing as required internal documentation for effective decision-making; participating in meetings of the Committee, or organizing representation; conveying decisions of the Committee to staff of the biosafety programme. Results: Effective coordination of the staff mostly for servicing meetings and on other substantive matters. |
| External linkages | Parties and Governments, United Nations bodies, other intergovernmental organizations, bilateral and multilateral funding institutions, GEF and its implementing agencies, relevant NGOs, academic and research institutes, press and media, other conventions secretariats, electronic communications networks, major groups, including the private sector and general public. |
| Approved posts | P-5- Senior Programme Officer; GS- Secretary (G-6) |
| Resources required | 1. Staff costs: 2005: $525,300 2006:$541,100 2. MOP Bureau meetings 2005: $ 50,000 2006: $50,000 3. Consultants/Sub-contracts 2005: $ 25,000 2006: $25,000 4. Travel on official business: 2005: $ 60,000 2006: $60,000 5. BCH Advisory Committee meetings 2005: $ 40,000 2006: $ 40,000 6. Liaison group meetings (2/year) 2005: $80,000 2006 $ 80,000 7. Meetings of the COP/MOP (two meetings during the biennium 2005-2006, i.e., MOP-3 and MOP-4 ; assumption here that MOP-2 will be held in 2004, MOP-3 in 2005, and MOP-4 in 2006) 2005: $ 525,000 2006: $425,000 8. Compliance Committee meetings (two meetings during the biennium 2005-2006; assumption here that the compliance will meet once a year, and will consist of 15 people, i.e., 3 from each region) 2005: $60,000 2006: $60,000 9. Open-ended Ad hoc Liability & Redress WG Meetings (four meetings during the biennium 2005-2006; assumption here that there will be one meeting in 2004, two meetings in 2005 and two meetings in 2006) 2005: $ 740,000 2006: $740,000 10. Temporary assistance/overtime 2005: $8,000 2006 $ 8,000 |
| Resources from outside the core budget | BE Trust Fund 1. Regional meetings on the Biosafety Protocol (4/year) 2005: $40,000 2006: $40,000 2. Technical Expert meetings (Article 18: assumption here that there will be one meeting in 2005 in order for the COP/MOP to be able to take a decision regarding paragraph 2a of Article 18; approximately 70 participants, of which 40 from developing countries and CETs). 2005: $160,000 2006: $ 0 3. BCH Technical Expert meetings 2005: $60,000 2006: $60,000 4. Consultants 2005: $ 20,000 2006: $150,000 5. Equipment 2005: $ 0 2006: $ 50,000 BZ Trust Fund 1. Meetings of the COP/MOP – developing country participation 2005: $250,000 2006: $250,000 2. Regional meetings on the Biosafety Protocol (4/year) – developing country participation 2005: $100,000 2006: $100,000 3. Open-Ended Ad Hoc Meetings of Liability & Redress WG- developing country participation 2005: $1,080,000 2006: $1,080,000 BF Trust Fund Support to developing country Parties and Parties with economies in transition in the use of the Biosafety Roster of Experts 2005: $200,000 2006: $200,000 |

(b) 	Enabling programme for the Implementation of the Biosafety Protocol

| Overview of responsibilities | Promoting and facilitating the effective implementation of the Protocol |
| --- | --- |
| Expected results | 1. Procedures and mechanisms to facilitate decision-making by Parties of import. |
|  | Mandate: Article 10, paragraph 7 of the Protocol. |
|  | Means: Parties to identify their capacity needs in order to make decisions in the time frames required by the Protocol; demand-driven procedures and mechanisms to facilitate decision-making to be developed; the roster of experts and the Biosafety Clearing-House to be developed as some of the main mechanisms to provide the necessary support, upon request, for facilitating decision-making by Parties of import. |
|  | Results: - Database on needs of Parties in risk assessment and risk management; - Roster of experts developed to assist Parties with risk assessment and capacity building for decision-making; - Relevant information to assist Parties in decision-making available on the Biosafety Clearing-House. |
|  | 2. Liability and redress |
|  | Mandate: Article 27 of the Protocol. Means: - Service the meetings of open-ended ad hoc group of legal and technical experts - Prepare documents for the meetings - Contribute to the Convention’s work on liability and redress issues. |
|  | Results: - Identification of elements, which could be included in a liability and redress regime for the Protocol and the Convention; - Recommendations on rules and procedures regarding liability and redress for the COP/MOP and the COP. |
|  | 3. Monitoring and Reporting |
|  | Means: - Compile and analyze interim national reports submitted by governments |
|  | Results: Improved implementation of the provisions of the Protocol on the basis of the analyses of submitted reports |
|  | 4. Handling, transport, packaging and identification |
|  | Mandate: Article 18 of the Protocol. Means: - Compile information that would facilitate the consideration of a decision on the detailed requirements of paragraph 2(a), including on unique identification of LMOs; - Compile views on the understanding and implementation of the documentation requirements of paragraph 2; - Compile information and views with regard to standards for identification, handling, and transport practices with a view to facilitate the consideration of the need for and modalities of developing such standards in accordance with paragraph 3; - Service any COP-MOP or interssesional meetings that would possibly be convened to address matters relating to Article 18. Results: Recommendations on the appropriate implementation of the requirements contained in Article 18. |
|  | 5. Compliance |
|  | Mandate: Article 34 of the Protocol. Means: - Service the meetings of the Compliance Committee - Prepare documents for the Committee - Any other work relating to the Committee |
|  | Results: Adoption of procedures and mechanisms to promote compliance and address cases of non-compliance by the COP/MOP. |
|  | 6. Cooperation with relevant organizations, arrangements and processes |
|  | Means: - Identify areas of cooperation between the CBD and the relevant bodies with regard to issues pertinent to the Protocol - Apply for observer status at relevant bodies and committees (e.g. the SPS/TBT Committees of the WTO) |
|  | Results: Implementation of the Protocol benefits from, and builds on, relevant ongoing processes and takes into account relevant international rules and standards. |
| Approved posts: New posts required: | P-4-Legal and Policy Affairs Officer; P-3 Legal Affairs Officer; GS Programme Assistant (G-7) None |
| Resources from outside the core budget | None |

F.  Resource Management and Conference Services (RMCS)

(a)	Overall management

| Overview of responsibilities | Management of the programme, facilitating the administration of the Secretariat, ensuring that conference facilities, personnel and financial resources are in place to enable the smooth functioning of the Secretariat. |
| --- | --- |
| Expected results | 1. The programme’s staff and activities are managed in an efficient manner that supports the operations of the Secretariat. Means: Supervision, coordination and guidance of the work of the staff within the programme; appraisal of the performance of staff; consultation with the executive direction and management programme regarding the allocation of human and financial resources within the Secretariat; participation in the Management Committee of the Secretariat; collaboration with the different divisions of the Secretariat regarding the schedule for conferences/meetings. Consultation with UNEP/UNON regarding administration financial resources and conference services as necessary. Results: Detailed work plans for staff members within the unit; up to date meeting plans for the Secretariat; availability of funds for the operations of the Secretariat; documentation prepared for the COP/COP Bureau as required. |
|  | 2. Effective participation on behalf of programme in the Management Committee of the Secretariat Means: Preparing as required internal documentation for effective decision-making; participating in meetings of the Committee, or organizing representation; conveying decisions of the Committee to staff of the RMCS programme. Results: Effective coordination of the staff mostly for servicing meetings and on other substantive matters. |
| External linkages | UNEP, UNON other United Nations agencies at the duty station; the host Government; diplomatic missions and delegations; other convention secretariats |
| Approved Posts: | P-5-Chief, Fund Management /Administration (UNEP) (existing P-4 post); |
| Resources required | 1. Staff costs: 2005: $520,700 2006: $536,300 2. COP meetings: 2005: $ 0 2006: $900,000 3. Inter-sessional review meeting 2005: $200,000 2006: $ 0 4. Travel on official business: 2005: $ 60,000 2006: $ 60,000 5. Temporary assistance and overtime 2005: $ 8,000 2006 $ 8,000 |
| Resources from outside the core budget | P-5-Chief, Fund Management /Administration (UNEP) funded by UNEP. |

(b) 	Financial resource management

| Overview of responsibilities | In cooperation with UNEP and UNON, RMCS provides the Secretariat with fund management and financial accounting. |
| --- | --- |
| Expected results | - Convention finances are efficiently managed. Mandate: Article 24 of the Convention. |
|  | Means: Preparation of budgets and related reports; monitoring and certification of expenditures: management of trust funds and interest accounts; efficient procurement of goods and services and timely payment of bills; reports of payments of indicative contributions and voluntary fund-raising; securing of cost-effective travel arrangements; management of common-service arrangements in Montreal. |
|  | Results: Proposed biennial programme budgets; financial reports to COP; records for audit; notice of indicative contributions sent to each Party annually, payments recorded accurately. |
| Approved posts: | P-2-Finance Officer (UNEP); GS Finance Assistant (UNEP) (G-8); GS GS Fund Management Assistant (UNEP) (G-6); |
| Resources from outside the core budget | All staff funded by UNEP |

(c)	Conference planning and management

| Overview of responsibilities | In cooperation with UNEP and UNON, RMCS provides the Secretariat with conference services for all meetings convened by SCBD |
| --- | --- |
| Expected results | 1. Meetings of COP and its subsidiary bodies and workshops are successfully organized. Mandate: Article 24 of the Convention. Means: Liaison with commercial conference facilities; creation of necessary temporary infrastructure at conference facilities (including rental and installation of furniture and equipment); hiring and training of temporary staff. Results: Suitable conference facilities for each session; teams of temporary staff to perform various functions before and during each session. |
|  | 2. Conference services are provided at all sessions. Mandate: Article 24 of the Convention. Means: Coordination with conference service providers (UNON and others). Results: Simultaneous conference room interpretation is all six languages of the CBD at all official meetings of the COP and its subsidiary bodies; conference rooms staffed with conference officers and technicians and equipped with sound systems. Security presence at all sessions. |
|  | 3. Maximum participation of Parties and other invited participants in the meetings of the Secretariat Mandate: Article 24 of the Convention. Means: Close coordination and liaison with support services and the responsible programme units with regard to nomination of delegates, travel arrangements and meeting documentation. Results: Conference participants receive documentation on time and travel arrangements to attend the meetings are facilitated. |
|  | 4. Documentation is produced on time and distributed before, during and after sessions of the Convention bodies. Mandate: Article 24 Means: Editing of documents; liaison with translators and documents service providers (UNON and others); maintenance of a document collection facility as the Secretariat. Results: Edited and, as appropriate, translated original documents; printed copies of documents; distribution of documents at the time specified before sessions of the Convention bodies. |
| Approved Posts: New Posts required: | P5- Editor; P-3 Conference Officer; G-5-Conference Services Assistant (G-5) Editorial Assistant (G-7) G-5 Information Assistant None |
| Resources from outside the core budget | G-5-Conference Services Assistant funded by UNEP |

(d) 	Administrative and personnel services

| Overview of responsibilities | In cooperation with UNEP and UNON, RMCS provides the Secretariat with personnel and administrative services. |
| --- | --- |
| Expected results | - Efficient management of the human resources of the Secretariat for the Convention. Mandate: Article 24 of the Convention. Means: Personnel actions all initiated and followed up with UNEP/UNON on recruitment, appointment and promotion processes; hiring of consultants and temporary staff; maintenance of personnel records and candidate rosters; implementation of performance appraisal system; liaison with the Staff Association; oversight of payroll and entitlements/benefits for GS staff; leave monitoring. Results: Recruitment, appointment, contract extensions of personnel are being initiated and followed up promptly with UNEP/UNON, performance appraisal system is fully functional, staff training needs are being investigated and responded to, leave records are being maintained, Secretariat staff is kept informed of staff rules and regulations. |
|  | 2. Management of the fellowships programme including Junior Professional Officers (JPOs). Mandate: Article 24 of the Convention. Means: Administrative actions initiated and followed up for the placement of JPOs within the Secretariat and the issuance of fellowships to as appropriate. Results: Recruitment of JPOs in a timely manner; granting of fellowships and acceptance and successful undertaking of fellowships by approved applicants. |
|  | 3. Travel services are provided for staff members as well as meeting participants. Mandate: Article 24 of the Convention. Means: Liaison with staff members/participants regarding travel arrangements; booking of most economic flights; checking of visa requirements; hotel bookings as required; preparation of travel authorisations including calculation of entitlements; calculation of travel claims; Results: Travellers are booked via the most economical and direct routes and arrive at their destinations in a timely manner. |
|  | 4. The computer and network systems of the Secretariat are well maintained. Mandate: Article 24 of the Convention. Means: Continuous services and maintenance of the systems; timely response in case of needs; adequate and timely upgrade of software and hardware. Results: Smooth running of the computer and network systems which respond to the needs of the secretariat work programme. |
| Approved posts: New posts required: | P-3 Administrative Officer (UNEP); GS- Personnel Assistant (G-7); GS Administrative Assistant (G-7); GS- Travel Assistant (G-7); Travel Assistant (G-6); GS- Receptionist (G-5); GS- Messenger (G-4); None |
| Resources from outside the core budget | P-3 Administrative Officer ; GS- Personnel Assistant (G-7) and GS Administrative Assistant (G-7) funded by UNEP |

G.  Shared resources of the Convention and the Protocol

(a)	Impact assessment, liability and redress

| Overview of responsibilities | Assist in the implementation of COP decisions relating to liability and redress. |
| --- | --- |
| Expected results | Mandate: Article 14 of the Convention; decision IV/10 C; decision V/18; and VI/11 |
|  | Means: (a) Support to the work of the group of legal and technical experts on liability and redress through: information gathering; compilation of case-studies; reviewing national reports for relevant information; requesting, and compiling and synthesizing information from Parties, Governments, relevant international and regional organizations; (b) Research and analyses on issues and topics identified in decision VI/11; |
|  | (c) Guidelines on the establishment and implementation of national legislative regimes, policy and administrative measures on liability and redress for damage to biological diversity; (d) Organization of meetings of the group of legal and technical experts on liability and redress; and (e) Information dissemination on liability and redress and on experiences through, inter alia, the clearing-house mechanism. |
|  | Results: - Synthesis reports and analyses on issues relating to liability and redress; - Guidelines on the establishment and implementation of national legislative regimes, policy and administrative measures on liability and redress for damage to biological diversity; - Information on regimes, measures and experiences disseminated through, inter alia, the clearing-house mechanism; 4. Meetings of the legal and technical experts group on liability and redress organized; |
| Approved posts: | P-5 Programme Officer (existing P-4 Legal Advice and Support). The workload for this post has increased significantly as the Convention process has matured more and more issues requiring legal inputs have emerged: notable recent examples include the legal regulation of alien invasive species; the articulation between the CBD and the WTO framework; the possible negotiation of an international legal regime on access to genetic resources and benefit-sharing; etc. The entry into force of the Biosafety Protocol will also demand regular inputs on a number of substantive and procedural issues, hence the recommendation to upgrade the post to P-5. GS – Programme Assistant Legal Affairs (50%) |
| Required resources: | 1. Staff costs 2005: $1,984,100 2006: $2,043,600 2. General operating expenses: 2005: $ 520,000 2006: $520,000 3. Communications: 2005 $ 213,000 2006: $ 213,000 4. Supplies and materials: 2005 $ 50,000 2006: $ 50,000 5. Furniture and equipment: 2005: $ 50,000 2006: $ 50,000 6. Maintenance of premises and equipment: 2005: $ 90,000 2006: $90,000 7. External printing: 2005: $ 55,000 2006: $ 55,000 8. CHM/BCH 2005: $20,000 2006: $ 20,000 9. Training/fellowships: 2005: $ 35,000 2006: $35,000 - Library acquisitions 2005: $25,000 2006: $25,000 11. Insurance 2005: $200,000 2006: $200,000 12. Hospitality: 2005: $ 25,000 2006: $ 25,000 |
| Resources from outside the core budget | None |

(b)	Review and consolidation of COP decisions

| Overview of responsibilities | Assist in the implementation of COP decisions relating to the review and consolidation of its decisions. |
| --- | --- |
| Expected results | Mandate: COP decisions V/20 and VI/27B |
|  | Means: Review the implementation of COP decisions and make proposals to the Conference of the Parties, in consultation with the Bureau and with the participation of Parties and relevant international organizations, regarding the retirement of decisions and elements of decisions and the consolidation of its decisions in specific subject areas. |
|  | Results 1. Retirement by the Conference of the Parties of decisions and elements of decisions which have either been fully implemented, of no continuing relevance or effect, or of only historical value. 2. The adoption by the Conference of the Parties of a consolidated body of decisions in each subject area. |
| Approved posts: | P-5 – Programme Officer (Legal Advice and Support) GS – Programme Assistant Legal Affairs (50%) |
| New posts required: | None |
| Resources from outside the core budget | None |

(c)  	Scientific Assessments

| Overview of responsibilities | Assist in the implementation of COP decisions relating o scientific assessments |
| --- | --- |
| Expected results | Mandate: Articles 7 and 25, para. 2, of the Convention; all decisions on programmes of work; decision III/10; recommendation 1 of ISOC; SBSTTA recommendations IV/1 and VI/5; decision VI/7-C; anticipated recommendations of SBSTTA 9; and anticipated decisions of COP 7. Means: Coordinate with other assessment initiatives, conduct research and studies in assigned substantive areas, in particular pilot assessment projects; produce technical and scientific reports, peer review; carry out pilot assessment projects; further development and refinement of the guidelines; cooperate with relevant regional and global assessments, such as the FAO Forest Resources Assessment (FRA), the Millennium Ecosystem Assessment (MA) and the Global Inland Water Assessment (GIWA). Results: - Advice to Parties on scientific and technical assessments; - Dissemination of information compiled and analyzed as well as of the results of experts activities to Parties and other Governments; - Results of pilots assessment projects; - Programme for scientific and technical assessments in all programmes of work on thematic areas; - Enhanced cooperation with MA, GIWA, FAO/FRA and other relevant assessments |
|  | 2. Risk Assessment |
|  | Means: - Facilitate implementation of any decision of the COP/MOP regarding clarification of the issues involved in risk assessment - Facilitate implementation of any decision of the COP/MOP regarding the development of guidance and a framework for a common approach in risk assessment |
|  | Results: Common understanding and effective implementation of risk assessment provisions of the Protocol by governments, including review and analysis of risk assessments submitted by exporters under Article 15(2). |
|  | Risk Management Means: - Facilitate implementation of any decision of the COP/MOP regarding Article 16 paragraph 5 - Cooperation with other relevant bodies and organizations: - Cooperation with relevant bodies with regard to scientific aspects of the Protocol (e.g., risk assessment and management), including with IPPC (COP Decision 6/20 paras 31-34) and others (e.g., Codex, OIE, OECD, WTO). - Contribute to relevant CBD work programmes on related scientific issues such as implementation of Article 8h of the Convention (alien species) |
|  | Results: Effective management of LMOs resulting from common understanding and agreement among governments and relevant bodies and organizations regarding approaches to risk management and priorities for management actions. |
| Approved posts: New posts required: | P-4 Scientific Assessment; P-3- Programme Officer/Scientific Assessment; None |
| Resources from outside the core budget | None |

(d) Information exchange

|  | 1. Clearing-house mechanism (CHM) |
| --- | --- |
| Overview of responsibilities | - Promote and facilitate technical and scientific cooperation, within and between countries and regions· - Develop a global mechanism for exchanging and integrating information on biodiversity· - Develop the necessary human and technological network - Assist in the development of the Biosafety Clearing-House |
| Expected results | 1. Governments and other interested parties have access to required expertise and information to assist decision and policy making, and initiate new projects based on technical and scientific cooperation; Mandate: Articles 18.3, 17 of the Convention, the CHM Strategic Plan Informal Advisory Committee recommendations, COP V/14 decisions. Means: Creation of new information and database systems to share and exchange information; creation of interoperable systems of information for data mining and less duplication of work; development of new communication channels to search, locate and retrieve expertise. Results: An updated, dynamic, database-driven and interactive web site with relevant information on CBD thematic areas of work, experts, and Convention and Protocol information and other relevant areas (national reports, financial resources, etc.). |
|  | 2. The CHM synergizes existing expertise and initiatives to foster greater cooperative work. Mandate: Articles 18.3, 17 of the Convention, the CHM Strategic Plan Informal Advisory Committee recommendations, COP V/14 decisions. Means: Participate in existing and new bioinformatics initiatives; Share CHM expertise and experience; Organize CHM workshops and meetings to foster sharing of expertise and synergize new initiatives. Results: Development of new systems and networks to foster and promote technical and scientific cooperation; Greater developing countries participation in new initiatives and projects; CHM input in new projects and initiatives.. |
|  | 3. The CHM makes available information interoperability guidelines for greater information sharing and integration. Mandate: Articles 18.3, 17 of the Convention, the CHM Strategic Plan Informal Advisory Committee recommendations, COP V/14 decisions.. Means: Dissemination of interoperability guidelines and toolkit. Results: Governments share and make interoperable national systems; Creation of central portals to access distributed data and information; Technical knowledge transferred to the developed world. |
|  | 4. The CHM assists in the development of the Biosafety Clearing-House Mandate: Article 20.1 of the Cartagena Protocol. Means: Development and implement an interactive web-based and non-web, non-electronic mechanism to assist countries to register information as required under the Cartagena Protocol. Results: A fully functioning and accessible Biosafety Clearing-House. |
|  | 5. The CHM organizes capacity building regional workshops Mandate: Articles 18.3, 17 of the Convention, the CHM Strategic Plan Informal Advisory Committee recommendations, COP V/14 decisions. Means: Organization of regional workshops to introduce CHM initiatives and technologies. Results: Developing countries can more effectively implement the CBD and participate fully in the work of the Secretariat and the CHM. |
|  | 6. The CHM develops pilot initiatives to assist work on the thematic issues within the work programme of the SBSTTA Mandate: Articles 18.3, 17 of the Convention, the CHM Strategic Plan Informal Advisory Committee recommendations, COP V/14 decisions. Means: Development of pilot initiatives within the 5 thematic areas and the 14 cross-cutting issues of the CBD. Results: Initiatives assist SBSTTA in the development and implementation of initiatives within their work programme. |
|  | 7. Information-sharing and the Biosafety Clearing-House (BCH) |
|  | Mandate: Article 20 of the Protocol. |
|  | Means: |
|  | - Information acquisition, management and evaluation for biosafety, and assistance to Parties in implementing the information sharing component of AIA (e.g. analyze and evaluate information submitted to the BCH in order to assess the implementation and effectiveness of the Protocol; develop and advise Parties on common information submission formats; prepare reports on the number, type and frequency of evaluations and transboundary movements; prepare reports for the Conference of the Parties on implementation of the information sharing component of AIA) - Electronic dissemination of information (e.g. creating, updating and maintaining the BCH databases and website; contributing to the development and content of information-exchange protocols at other organizations To Whom It May Concern: facilitate effective exchange of information relevant to implementation of the Protocol; evaluating the development of Internet issues related to information management and developing related policies; facilitation of electronic discussion fora to facilitate the exchange of information between national governments using Internet tools) |
|  | Results: Identification of the country needs for, and meeting those needs to establish, an operational Biosafety Clearing-House. |
| Approved posts: New posts required: | P-4 Programme Officer, Clearing-house Mechanism P-4- Programme Officer/BCH Scientific and Technical Information; P-3 Programme Officer, Internet & Electronic Communications P-3 Programme Officer, Website Management P-3 Computer Information Systems Officer P-3 Computer Systems Officer (to be upgraded from P-2) G-7 Computer Operations Assistant G-7 Programme Assistant, Clearing-house Mechanism None |
| Resources from outside the core budget | None |

(e)	Reporting

| Overview of responsibilities | Support implementation of the Convention by undertaking tasks assigned to the Secretariat in respect of national reports, thematic including analysis of measures taken by Parties and their effectiveness, and of the preparation of reviews of the state of implementation. Production of the Global Biodiversity Outlook report series. |
| --- | --- |
| Expected results | 1. Assist Parties with the preparation of thematic reports on issues for in-depth consideration at COP-8 and provide SBSTTA and COP with analysis of information contained therein Mandate: Article 26 of the Convention; decision V/19 paragraph 7, and expected decision from COP-7 Means: Preparation of formats for thematic reports and preparation of thematic reports on one or more items for in-depth consideration of the Conference of Parties and SBSTTA in liaison with national focal points, GEF and implementing agencies, relevant specialist institutions and experts; assist STTM with analysis of information in the relevant thematic reports. Results: Support to Parties for the preparation of thematic reports; provision to SBSTTA and COP of timely and analytical reports and recommendations based on comprehensive analysis of the thematic reports |
|  | 2. Prepare detailed analysis of the third national report with status updates on the NBSAPs, implementation of the Strategic Plan and progress towards the achievement of the 2010 target and the Millennium Development Goals for consideration of COP-8. Mandate: Article 26 of the Convention; decision V/19 and VI/25 and expected decisions from COP-7. # Means: Analysis of the 3rd national report focusing on the strategic goals and objectives established under the Strategic Plan, the measures taken to achieve the 2010 target and Millennium Development Goals (MDGs) as well as the provisions of decision VI/25 paragraph 3(d) for the consideration of COP-8 Results: Timely and appropriate analyses and recommendations prepared for COP-8, in particular on the implementation of the Strategic Plan and the achievement of progress towards the 2010 target and the MDGs. |
|  | 3. Contribute to the identification and application of synergies and opportunities for streamlining reporting requirements by Parties, reporting on the 2010 target and the Millennium Development Goals. Mandate: Decision V/19 and expected decision from COP-7; follow-up to the outcomes of WSSD and other relevant meetings on 2010 target and MDGs. Means: Continued collaboration with other convention secretariats, UN/DESA, UNEP and other relevant bodies; analysis of outcome of pilot projects; joint reporting activities on the 2010 target and MDGs, incorporation of recommendations of the World Summit on Sustainable Development and related meetings on the 2010 target and MDGs regarding harmonization of reporting. Results: Implementation and consolidation of means to harmonize reporting under related treaties and initiatives (MDGs) that maximize availability of information contained in reports and reduce demands on Parties, leading to greater availability of relevant information and increased support to decision-making and policy formulation. |
|  | 4. Dissemination of reports and other material relevant to assessment of implementation of the Convention, achievement of the 2010 target and MDGs Mandate: Decisions II/17, IV/14, V/19 and expected decision from COP-6. Follow-up to the outcomes of WSSD and other relevant meetings on 2010 target and MDGs. Means: Continued dissemination through the clearing-house mechanism of national reports, national biodiversity strategies and action plans, biodiversity country studies and other national, regional and global information on the status and trends of biodiversity and the state of implementation of the Convention, progress towards the achievement of the 2010 target and the MDGs. Results: Facilitation of access by Parties and other users to information on implementation of the Convention. |
|  | 5. Further development of methodologies for assessing the state of implementation of the Convention, and identification of ways and means to further facilitate national implementation. Mandate: Article 26 of the Convention; decisions IV/14(4), V/19, V/20, VI/26. # Means: In the context of monitoring and evaluation of the implementation of the Strategic Plan, liaison with specialist institutions and experts, with implementing agencies and other organizations supporting national and regional capacity development in biodiversity planning, and with national focal points and biodiversity managers. Results: - Provision of timely and relevant advice to the COP on the status and evaluation of progress of the implementation of the Convention; - Increased synergies among mechanisms for implementation at national, regional and global levels; and - Improved identification of priority needs for capacity development and financial support. |
|  | 6. Preparation and publication of the Global Biodiversity Outlook (GBO) report series as a periodic report on biological diversity and implementation of the Convention. Mandate: Decision II/1, VI/25 paragraph 6 Means: Collation and analysis of national reports and other relevant information and in collaboration with specialist institutions and with the assistance of expert consultants, the Global Biodiversity Outlook Advisory Group; undertake preparation of the third edition of the GBO report. Supervise design and production and liaison with publishers. Results: High-quality publication that provides a comprehensive status of the implementation of Convention, the Strategic Plan, progress towards the achievement of the 2010 target and the Millennium Development Goals. Contribution to public education and awareness about biodiversity and the Convention. |
| Approved posts | P-3 Environmental Affairs Officer G-7 Programme Assistant |
| New posts required | None |
| Resources from outside the core budget | None |

(f) Outreach and Capacity-building

|  | 1. Consolidation, strengthening and/or development of capacity building for communication, education and public awareness. Mandate: Article 13 of the Convention and decision VI/19. Means: Strengthening and/or development of capacity of the Parties to market biodiversity to other sectors, and also to mainstream biodiversity into the work of other sectors; further development of professional capacity of educators and communicators; and enhancement of stakeholder participation and community development though communication, education and public awareness. Results: A range of individuals and institutions with an enhanced understanding of the needs, methods and mechanisms of stakeholder participation; individuals and institutions with capacity to plan and manage biodiversity communication and education; communicators pack or set of tools (among others); update and expanded online training courses in communication (among others); and greater access at the community level to communication and public education and awareness programmes, courses and resources. |
| --- | --- |
|  | 2. Mechanisms to promote capacity-building for the effective implementation of the Protocol |
|  | Mandate: Article 22 and Article 28, paragraph 3 of the Protocol and decisions II/4, III/6 and EM-I/3, paragraph 14, of the Conference of the Parties. Means: 1. Administration of the Coordination Mechanism - Maintain the databases on capacity-building projects, opportunities and country needs in the BCH - Identify and disseminate relevant information, best practices and lessons learned in biosafety capacity-building initiatives i.e. Act as a central contact point (clearinghouse) for existing biosafety capacity-building initiatives, to facilitate information sharing and cooperation at the international and regional levels. - Prepare and disseminate synthesis reports on the progress in implementing the capacity-building Action Plan, on the basis of the submissions by Governments and relevant organizations - Convene and service meetings of the Liaison Group on capacity building on biosafety, as necessary - Organize, subject to availability of funding, periodic coordination meetings for governments, relevant organizations and donors - to promote and facilitate collaboration, coordination and synergies between different capacity-building initiatives in order to avoid duplication and inefficient use of limited resources - Promote broad common understanding of the capacity-building needs and approaches for the effective implementation of the Protocol - Administer the roster according to the interim guidelines (numerous functions) - Administer the voluntary fund according to the interim guidelines |
|  | 2. Other potential roles of the Secretariat in supporting countries to implement the capacity-building provisions of the Protocol and in developing and implementing outreach programmes. - Undertake analysis and synthesis of the capacity-building needs and priorities of different countries for the effective implementation of the Protocol - Identify existing bilateral and multilateral funding and other opportunities for biosafety capacity-building and advise countries accordingly - Keep countries abreast of important developments with respect to capacity-building for biosafety - Develop common formats for sharing information and foster consistency in the use of biosafety capacity-building concepts, tools and approaches. - Prepare documents for COP/MOP, including suggestions of innovative ways and means for advancing capacity-building in developing countries and countries with economies in transition. - Implement any other requests by the Conference of the Parties serving as the meeting of the Parties regarding capacity-building. - Contribute to development and implementation of the CBD and Protocol outreach Results: Effective use of the roster of experts; development of a coordination mechanism for the implementation of the Action Plan with a view to promoting partnerships and to maximize complementarities and synergies between various capacity building initiatives; development and implementation of an outreach strategy for the Protocol and the Convention as a whole.. |
| Approved posts: New posts required: | P-3 Environmental Affairs Officer/Capacity Building and Outreach; P-3 Information Officer; GS Programme Assistant (G-7) None |

(g)	Library and Publications

| Overview of responsibilities | Provide the Secretariat and the interested public with comprehensive and relevant information on biological diversity. |
| --- | --- |
| Expected results | 1. The Library collection and the bibliographic database on biological diversity are efficiently managed. Mandate: Articles 24, 13 and 17 of the Convention. Means: Acquisition of relevant documents (journals, monographs, etc.); cataloguing, indexing, labelling and shelving of documents; monitoring of library use. Processing of documents; data entry; maintenance of the database. Results: Database on pertinent documents on biological diversity; access of users to relevant documents published on biological diversity; availability of the bibliographic database on SCBD intranet. Maintenance of computerized files. Storage and preservation of library materials. |
|  | 2. Users can access information on library collection through Intranet and through other information products. Mandate: Articles 13, 17 and 24 of the Convention. Means: Maintaining an Intranet window for the library through SCBD web site. Publication of list of acquisitions and other information products are made available on request. Results: Updated information on library materials for internal and external users. Promotion of the Convention and the exchange of information. |
|  | 3. Provide the Secretariat with a records and archives management system. Mandate: Article 24 of the Convention. Means: Draft policies, procedures, objectives and guidelines affecting the development and maintenance of SCBD‘s records and archives. Results: Implementation and maintenance of a records and archives management system for the Secretariat. |
|  | 4. The publications are well produced and managed efficiently. Mandate: Articles 13, 17 and 24 of the Convention. Means: Coordination of the design, printing and distribution of SCBD publications. Management of stock of publications. Maintenance of SCBD website on publications. Production of promotional tools. Dissemination of relevant information material to targeted groups. Results: Increasing availability of well-produced and relevant publications. |
| Approved post: | P-4 Documentation Officer (to be upgraded from P-3) |
| New post required: | G-7 Programme Officer (50% staff time) |
| Resources from outside the core budget | None |

Annex

ABBREVIATIONS

BCH		Biosafety Clearing House

CGRFA 		Commission on Genetic Resources for Food and Agriculture

CHM 		Clearing-house mechanism

CIFOR	Centre for International Forestry Research

CITES 	Convention on International Trade in Endangered Species of Wild Fauna and Flora

CMS 		Convention on the Conservation of Migratory Species of Wild Animals

COP 		Conference of the Parties to the Convention

COP 1 		first meeting of the COP, Nassau, 28 November to 9 December 1994

COP 2 		second meeting of the COP, Jakarta, 4 to 17 November 1995

COP 3 		third meeting of the COP, Buenos Aires, 3 to 14 November 1996

COP 4 		fourth meeting of the COP, Bratislava, 4 to 15 May 1998

COP 5 		fifth meeting of the COP, Nairobi, 15 to 26 May 2000

COP 6 		sixth meeting of the COP, the Hague, 7 to 19 April 2002

COP 7		seventh meeting of the COP, Kuala Lumpur, 8 to 20 and 27 February 2004

COP/MOP-1	first meeting of the COP serving as the Meeting of the Parties, Kuala Lumpur, 23 to 27 Feb. 2004

CSD 		Commission on Sustainable Development

CTE 		WTO Committee on Trade and Environment

ExCOP 		first extraordinary meeting of the Conference of the Parties to the Convention

FAO 		Food and Agriculture Organization of the United Nations

GEF 		Global Environment Facility

GISP	Global Invasive Species Programme

GIWA	Global Inland Waters Assessment

GTI 		Global Taxonomy Initiative

IACSD	Inter-Agency Committee on Sustainable Development

ICCP		Intergovernmental Committee on the Cartagena Protocol on Biosafety

ICGEB	International Centre for Genetic Engineering and Biotechnology

ICLARM	International Centre for Living Aquatic Resources Management

ICRI 		International Coral Reef Initiative

IFF 		Intergovernmental Forum on Forests

IMCAM 	integrated marine and coastal area management

IMO 		International Maritime Organization

IOC 		Intergovernmental Oceanographic Commission

IPF 		Intergovernmental Panel on Forests

IPR 		intellectual property rights

IUCN 		World Conservation Union

IUFRO	International Union of Forestry Research Organizations

MDG		millennium development goals

MEA		multilateral environmental agreements

MOP		meeting of the parties

MTPW		medium-term programme of work

MYPOW	multi-year programme of work

OECD 		Organisation for Economic Co-operation and Development

Ramsar 		Convention on Wetlands of International Importance, especially as Waterfowl Habitat

SBSTTA  	Subsidiary Body on Scientific, Technical and Technological Advice

SBSTTA 1 	First meeting of SBSTTA, Paris, 4 to 8 September 1995

SBSTTA 2 	Second meeting of SBSTTA, Montreal, 2 to 6 September 1996

SBSTTA 3 	Third meeting of SBSTTA, Montreal, 1 to 5 September 1997

SBSTTA 4 	Fourth meeting of SBSTTA, Montreal, 21 to 25 June 1999

SBSTTA 5 	Fifth meeting of SBSTTA, Montreal, 31 January to 4 February 2000

SBSTTA 6 	Sixth meeting of SBSTTA, Montreal, 12 to 16 March 2001

SBSTTA 7 	Seventh meeting of SBSTTA, Montreal, 12 to 16 November 2001

SBSTTA 8 	Eighth meeting of SBSTTA, Montreal, 10 to 14 March 2003

SBSTTA 9 	Ninth meeting of SBSTTA, Montreal, 10 to 14 November 2003

SCOPE	Scientific Committee on Problems of the Environment

STAP	Scientific and Technical Advisory Panel (of GEF)

TRIPs 		Agreement on Trade-related Aspects of Intellectual Property Rights

UN/DESA	United Nations Department of Economic and Social Affairs

UNCCD	United Nations Convention to Combat Desertification in those Countries Experiencing Serious Drought and/or Desertification, particularly in Africa

UNCED	United Nations Conference on Environment and Development

UNCLOS 	United Nations Convention on the Law of the Sea

UNCTAD 	United Nations Conference on Trade and Development

UNEP 		United Nations Environment Programme

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNFCCC	United Nations Framework Convention on Climate Change

UNGA 		United Nations General Assembly

WIPO 		World Intellectual Property Organization

WSSD		World Summit on Sustainable Development

WTO 		World Trade Organization

UNEP/CBD/COP/7/1.

All in 2005 except where indicated: (i) Inland water biological resources (2 of which one in 2006); ii) marine and coastal biological diversity (1); iii) small island biodiversity (1); iv) invasive alien species (1 in 2006);  v) indicators, targets and baselines (1).

In 2005: Inland water biodiversity (2); dry and sub-humid lands (2); small island biodiversity (2); in 2006: Inland water biodiversity (1); agrobiodiversity (1) and forest biodiversity (1)

In 2005 (NB: some may start in 2006 or may take place in both years): Inland water biodiversity (2); dry and sub-humid lands (2).  In 2006: Agrobiodiversity (1); Forest biodiversity (1).

In 2005: Inland water biodiversity (2); marine and coastal biodiversity (1); regional dry and sub-humid land biodiversity (3). In 2006: agrobiodiversity (1).

In 2005: invasive alien species (3); ecosystem approach (1); GTI (1); protected areas (1); migratory species (1). In 2006 : biodiversity and climate change (1).

In 2005 invasive alien species (1); and in 2006: invasive alien species (1). (Staff travel only).

In 2005: Global Taxonomy Initiative (1) Global Plant Strategy –regional  (2); Climate change and biodiversity –regional (2); Migratory Species (1). In 2006: Invasive alien species (1) Impact assessment (1); Global Plant Strategy-regional (2); Protected areas (2); Climate change and biodiversity – regional (2); Climate change and biodiversity (1).

New P-3 Post requested to support the expanded scope of the education, training and awareness dimensions of CEPA (strategic plan, outreach activities with schools and universities, 2010 target capacity development etc.)