|  |  |  |  | CBD |
| --- | --- | --- | --- | --- |
|  |  |  |  | Distr. GENERAL CBD/COP/15/7 31 August 2022 ORIGINAL: ENGLISH |
| CONFERENCE OF THE PARTIES TO THE CONVENTION ON BIOLOGICAL DIVERSITY Fifteenth meeting Agenda item 7 |  |  | CONFERENCE OF THE PARTIES SERVING AS THE MEETING OF THE PARTIES TO THE CARTAGENA PROTOCOL ON BIOSAFETY Tenth meeting Agenda item 6 | CONFERENCE OF THE PARTIES SERVING AS THE MEETING OF THE PARTIES TO THE NAGOYA PROTOCOL ON ACCESS TO GENETIC RESOURCES AND THE FAIR AND EQUITABLE SHARING OF BENEFITS ARISING FROM THEIR UTILIZATION Fourth meeting Agenda item 6 |  |

Montreal, Canada, 7-19 December 2022

PROPOSED BUDGET FOR THE PROGRAMMES OF WORK OF THE CONVENTION ON BIOLOGICAL DIVERSITY, THE CARTAGENA PROTOCOL ON BIOSAFETY AND THE NAGOYA PROTOCOL ON ACCESS AND BENEFIT-SHARING FOR THE BIENNIUM 2023-2024

Note by the Executive Secretary

# I.	INTRODUCTION

- The Conference of the Parties at its fourteenth meeting (COP) and the respective meetings of the Parties of the Cartagena and Nagoya Protocols (MOP) requested Executive Secretary to prepare an integrated programme of work and budget for the period 2021-2022, to be submitted to the Conference of the Parties at its fifteenth meeting (COP-15) and to the respective meetings of the Parties to the Protocols (decisions 14/37, para. 48), CP-9/16, and NP-3/16.

- The programme of work and budget should set out the objectives, tasks to be completed by the Secretariat and results expected in regard to each budget item, following the format of the proposed biennial programme budget for the United Nations Environment Programme (UNEP), with three alternatives as follows:

- Making an assessment of the required rate of growth for the programme budget (BY, BG and BB trust funds) which should not exceed a 4 per cent increase from the total 2019-2020 level minus the amount on budget line K on extraordinary meetings on the post-2020 global biodiversity framework (GBF), in nominal terms;

- Maintaining the programme budget (BY, BG and BB trust funds) at the total 2019-2020 level minus the amount on budget line K on extraordinary meetings on the post-2020 global biodiversity framework in real terms;

- Maintaining the programme budget (BY, BG and BB trust funds) at the total 2019-2020 level minus the amount on budget line K on extraordinary meetings on the post-2020 global biodiversity framework in nominal terms.

- Due to the pandemic, COP-15 and related meetings were postponed. As the Secretariat’s funding would expire on 31 December 2020, an interim budget for 2021 was submitted and subsequently approved on 27 November 2020 by the extraordinary meeting of the Conference of the Parties to the Convention and by the meetings of the Parties to the Protocols (decisions CBD/EM-/2/1, CP-EM-1/1, and NP-EM-1/1), as supplementary to decisions 14/37, CP-9/16 and NP-3/16. In these decisions, the Executive Secretary was requested to prepare budget proposals for the period 2022-2023, taking account of paragraph 48 of decision 14/37.

- The pandemic led to further rescheduling of COP-15 and the concurrent meetings of the Parties to the Protocols. It was decided to organize the meetings in two parts, whereby the first part of the meetings would be held from 11 to 15 October 2021 and the second part would be held in 2022. Accordingly, Part I of the meetings was held in Kunming, China, with a limited local presence and with others participating virtually. At this first part of COP-15, and at the first parts respectively of the tenth meeting of the Parties to Cartagena Protocol (CP-MOP-10) and of the fourth meeting of the Nagoya Protocol (NP-MOP-4), the Parties approved an integrated programme budget of $18,439,546 for 2022 and confirmed the extension of parts of the 2019/2020 budget until after the end of the second part of COP-15 pending consideration and adoption of the programme budget for the biennium 2023-2024 by the Conference of the Parties, at the second part of its fifteenth meeting.

- In line with the requests in the aforementioned decisions, the present document presents Zero-Real Growth and Zero-Nominal Growth scenarios for the integrated programme of work and budget for the period 2023-2024, each one net of the allocations for the extraordinary meetings for the post-2020 global biodiversity framework. The Zero-Real Growth shows an eight per cent increase over the four years since 2018 when the 2019-2020 biennium was adopted (i.e. just under two per cent increase per year), reflecting cost increases (see para. ‎14 below).

- The aforementioned decisions also requested “making an assessment of the required rate of growth for the programme budget” but specified that this “should not exceed a 4 per cent increase from the total 2019-2020 level minus the amount on budget line K on extraordinary meetings on the post-2020 global biodiversity framework, in nominal terms”.  Since this cap implies a diminished budget in real terms, it is not possible to prepare within it a scenario for the “required rate of growth”.

- In decision 14/34, the Conference of the Parties expressed its commitment to developing a transformative post-2020 global biodiversity framework that would put biodiversity on a path to recovery towards achieving the 2050 vision of living in harmony with nature. The Secretariat anticipates new mandates and an increased workload to support the implementation of this ambitious agenda. The growing prominence of biodiversity issues globally and their linkages to other critical issues such as climate change and health is also expected to have workload implications for the Secretariat. The current structure and staffing levels of the Secretariat are not adequate to address the existing demands and mandates requested of the Secretariat. With these demands and mandates set to increase, the ability of the Secretariat to deliver on these requests will become more precarious without significant new and additional resources beyond those provided for in the scenarios presented in the present document.

- In an effort to address these staffing and resource limitations, the Secretariat is preparing a supplementary budget proposal in the form of an additional scenario, which not only addresses the needs for existing mandates arising from previous decisions of the Conference of the Parties and of the Parties to the Protocols, but also the requirements to meet the increased workload associated with supporting the implementation of the post-2020 global biodiversity framework. This supplementary proposal will be issued as an addendum to this budget document for the biennium 2023-2024.

- In response to decision 14/37 and subsequent audit recommendation by the Office of Internal Oversight Services (OIOS), the Secretariat established an internal working group, with the assistance of UNEP, to develop and enhance its results-based-budgeting (RBB) framework. The framework is a programme and budget process where (a) the programme formulation revolves around a set of predefined objectives and expected results, (b) expected results justify the resource requirements which are derived from and linked to outputs required to achieve such results, and (c) actual performance in achieving results is measured by objective performance indicators. Prepared initially for the biennium 2021-2022 in view of the postponement of COP-15 caused by the COVID-19 pandemic, the RBB framework presented in the present document pertains to the biennium 2023-2024. While considerable effort has been made in developing a Secretariat-wide RBB framework, more work is still required to develop specific indicators of achievement as can be seen in section III below. The framework is further presented below along with the underlying Theory of Change and the assumptions made in this regard, which are intended to serve as the basis for this integrated programme budget.

- The present document presents a summary of the budget proposals for the core budget and for voluntary budgets (section II), introduces the results-based framework (section III), and provides details of the programme and associated budgetary requirements (section IV).

- The present document should be read in conjunction with document CBD/COP/15/6, which will provide a report on administrative and budgetary matters as requested by the Parties in paragraphs 49 and 50 of decision 14/37, including information such as income and budget performance, unspent balances, status on surplus and carry-overs, as well as any adjustments made to the budget for the biennium 2019-2020 and the interim budget for 2021. The Secretariat is also preparing a proposal to revise the structure and rules related to the BZ Trust Fund (CBD/COP/15/7/Add.3), as requested in paragraph 37 of decision 14/37, for adoption by the Conference of the Parties at its fifteenth meeting.

- The draft decision for consideration by the Conference of the Parties will be provided in the compilation of draft decisions (CBD/COP/15/2). The draft decisions for the respective meetings of the Parties of the Cartagena and Nagoya Protocols will also be provided in the respective compilations (CBD/CP/MOP/10/1/Add.5, and CBD/NP/MOP/4/1/Add.5).

# II. 	SUMMARY OF THE BUDGET PROPOSAL

## A. Core Budget

- This section provides an overview of all the post and non-post resources requested for the core budget under the zero-real growth (ZRG) and zero-nominal growth (ZNG) scenarios compared to the approved resources for the biennium 2019-2020.

- The overall resources for the biennium 2023-2024 in a zero-real growth scenario amount to $40,443,800 reflecting a net increase of $2,909,700 (or 8 per cent) compared with the approved core budget for the biennium 2019-2020 less the provision for the extraordinary meetings on the post-2020 GBF ($1,310,000). Resource changes result from two factors, namely: (a) technical adjustments mainly relating to increases in post adjustment for international staff related to the cost-of-living survey by the International Civil Service Commission (ICSC) that took place in Montreal, Canada in November 2021, currency fluctuations in Canadian dollars and inflation, and (b) other resource changes taking into account previous expenditure patterns.

- The provision for posts was calculated using United Nations common standard salary costs for 2023, using the newly established post adjustment multiplier for Montreal of 55.8 for 2023 referred to above and an estimated post adjustment multiplier of 58.0 for 2024 for Secretariat staff during the biennium 2023-2024.  In addition, the Secretariat has applied a vacancy rate of 5 per cent for Professional posts and zero per cent for General Service positions for existing posts, as well as the application of a delayed recruitment factor of 50 per cent in the first year for all new posts requested in line with the standard UNHQ Programme Budget guidelines. This was done in an effort to reduce the overestimation and bring budgeted salary cost estimates closer to actual salary costs expected to be incurred during the biennium 2023-2024.

#### Table 1. Financial resources

(In thousands of United States dollar

| Approved Core Budget for 2019-2020 |  | 38,844.1 a/ |
| --- | --- | --- |
| Approved Interim Core Budgets for 2021-2022 |  | 35,212.2 b/ |
| Zero-real Growth Scenario for 2023-2024 |  | 40,443.8 c/ |
| Zero-nominal Growth Scenario for 2023-2024 |  | 37,181.2 d/ |
| a/ Includes $1,310.000 for extraordinary meetings on post-2020 as per decision 14/37 |  |  |
| b/ Interim budgets for 2021 and 2022 at the maintenance level to ensure SCBD operations during COVID-19 pandemic. |  |  |
| c/ Reflects 8 per cent increase above approved core budget for 2019-2020 less provision for extraordinary meetings on post-2020. |  |  |
| d/ Reflects 0 per cent increase above approved core budget for 2019-2020 less provision for extraordinary meetings on post-2020. |  |  |

#### Table 2	. Approved post resources by biennium

|  | Number | Level |
| --- | --- | --- |
| Core budget |  |  |
| Approved for the biennium 2019-2020 | 78 | 1 ASG, 3 D-1, 10 P-5, 12 P-4, 14 P-3, 9 P-2/1, 29 GS |
| Approved for the biennium 2021-2022 | 78 | 1 ASG, 3 D-1, 10 P-5, 13 P-4, 13 P-3, 9 P-2/1, 29 GS |
| Zero-real Growth Scenario for 2023-2024 | 86 a/ | 1 ASG, 1 D-2, 2 D-1, 10 P-5, 17 P-4, 17 P-3, 9 P-2/1, 29 GS |
| Zero-nominal Growth Scenario for 2023-2024 | 78 b/ | 1 ASG, 1 D-2, 2 D-1, 10 P-5, 13 P-4, 13 P-3, 9 P-2/1, 29 GS |

a/ 8 new posts requested as follows: 4 P-4, 4 P-3 and upgrade of D-1 to D-2

b/	Upgrade of D-1 to D-2

- The proposal is based on the cost sharing ratio between the Convention and the Cartagena and Nagoya Protocols in a pro-rated ratio of 72%: 15%: 13% respectively, in keeping with the integration of the processes and Secretariat functions carried out under the functional review and assessed in accordance with the United Nations scale of assessments. This ratio envisages an increase in the proportion attributed to the Nagoya Protocol (from 11% to 13%) in line with the increase in the number of Parties to the Protocol to 138 in 2022.

- Tables 3 provides an overview of the financial resources by components.

- The Secretariat, in line with the United Nations Secretariat financial regulations and rules, applies a 13 per cent programme support cost on core and voluntary extrabudgetary funding, to cover incremental costs associated with providing administrative backstopping support for the Secretariat, of which one-third (1/3) is charged by UNEP for its services in accordance with an agreed cost-sharing framework. The balance (2/3) is used to cover the costs of the Secretariat’s own support component provided by the Administration, Finance and Conference Services Division, described below under Section E on Administrative Support.

- Table 4 provides an overview of the staffing resources requested under each scenario by level compared with the authorized staffing table for the biennium 2019-2020 and the biennium 2021-2022, as amended and reported in the report of the Executive Secretary on the income and budget performance for the Convention on Biological Diversity, the Cartagena Protocol on Biosafety and the Nagoya Protocol on Access and Benefit-sharing for the biennium 2019-2020 and 2021 (CBD/COP/15/6).

- The distribution of resources is reflected in table 5.

#### Table 3.  Financial resources by component

|  |  |  |  | 2023-2024 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 | 2021-2022 |  | Zero Real Growth Scenario (8%) | Zero Nominal Growth Scenario (0%) |  |
|  | COP 14/37 | EM-2/1 & COP15/1 |  |  |  |  |
| Staff costs |  |  |  |  |  |  |
| Staff | 23,080.5 | 24,156.8 |  | 25,290.7 | 22,645.1 | a/ |
| General temporary assistance | 200.0 | 200.0 |  | 200.0 | 200.0 |  |
| Subtotal | 23,280.5 | 24,356.8 |  | 25,490.7 | 22,845.1 |  |
| Meetings costs |  |  |  |  |  |  |
| Bureau meetings | 365.0 | — |  | 278.9 | 278.9 |  |
| Expert meetings | 320.0 | — |  | 320.0 | 320.0 |  |
| Meetings of intergovernmental bodies | 3,688.0 | 1,469.8 |  | 3,970.0 | 3,970.0 |  |
| Extraordinary meetings on post-2020 | 1,310.0 | 350.0 |  | --- | --- |  |
| Subtotal | 5,683.0 | 1,819.8 |  | 4,568.9 | 4,568.9 |  |
| Operational costs |  |  |  |  |  |  |
| Consultants | 100.0 | 100.0 |  | 100.0 | 100.0 |  |
| Official travel | 800.0 | 550.0 |  | 640.0 | 600.0 |  |
| Rent and associated costs | 2,652.9 | 2,839.4 |  | 2,918.7 | 2,918.7 |  |
| Training | 10.0 | 10.0 |  | 10.0 | 10.0 |  |
| Information technology | — | — |  | 130.0 | 130.0 |  |
| General operating expenses | 1,453.2 | 1,453.2 |  | 1,453.2 | 1,453.2 |  |
| Public awareness material | 100.0 | 100.0 |  | 100.0 | 100.0 |  |
| Translation of CHM websites | 130.0 | 130.0 |  | 130.0 | 130.0 |  |
| Subtotal | 5,246.1 | 5,182.6 |  | 5,481.9 | 5,441.9 |  |
| Total requirements | 34,209.6 | 31,359.2 |  | 35,541.5 | 32,855.9 |  |
| Programme Support (13%) | 4,447.2 | 4,076.7 |  | 4,620.4 | 4,271.3 |  |
| Total | 38,656.8 | 35,435.9 |  | 40,161.9 | 37,127.2 |  |
| Working Capital Reserve | 187.3 | -223.7 |  | 281.9 | 54.0 |  |
| Total requirements | 38,844.1 | 35,212.2 |  | 40,443.8 | 37,181.2 |  |
| Less contributions from host country |  |  |  | -3,298.1 | -3,298.1 |  |
| Net total (to be shared by Parties) |  |  |  | 37,145.7 | 33,883.1 |  |
| Convention share of the integrated budget (72%) |  |  |  | 26,744.8 | 24,395.8 |  |
| Cartagena Protocol share of the integrated budget (15%) |  |  |  | 5,571.8 | 5,082.5 |  |
| Nagoya Protocol share of the integrated budget (13%) |  |  |  | 4,828.9 | 4,404.8 |  |

a/ reflects the application of standard vacancy rate used in the Standard Salary Cost for Professional posts.  No vacancy rate has been applied to General Service posts.

#### Table 4	.  Post resources

|  | ### Authorized core budget | ### Authorized | ### ZRG | ### ZNG |
| --- | --- | --- | --- | --- |
|  | ### 2019-20 | ### 2021-22 | ### 2023-24 | ### 2023-24 |
| ### Professional and higher |  |  |  |  |
| ### ASG | ### 1 | ### 1 | ### 1 | ### 1 |
| ### D-2 | ### – | ### – | ### 1 | ### 1 |
| ### D-1 | ### 3 | ### 3 | ### 2 | ### 2 |
| ### P-5 | ### 10 | ### 10 | ### 10 | ### 10 |
| ### P-4 | ### 12 | ### 13 | ### 17 | ### 12 |
| ### P-3 | ### 14 | ### 13 | ### 17 | ### 14 |
| ### P-2/1 | ### 9 | ### 9 | ### 9 | ### 9 |
| ### Subtotal | ### 49 | ### 49 | ### 57 | ### 49 |
| ### General Service | ### 29 | ### 29 | ### 29 | ### 29 |
| ### Subtotal | ### 29 | ### 29 | ### 86 | ### 29 |
| ### Total | ### 78 | ### 78 | ### 86 | ### 78 |

#### Table 5.  Distribution of resources by component

(Thousands of United States dollars)

|  | 2019-2020 approved budget |  | 2023-2024 ZRG1 | 2023-2024 ZNG |
| --- | --- | --- | --- | --- |
| A. Governing and Subsidiary bodies | 4,373.0 |  | 4,568.9 | 4,568.9 |
| B. Executive direction and management | 5,304.3 |  | 6,206.2 | 5,481.6 |
| C. Programme of work | 18,552.5 |  | 18,737.8 | 17,145.6 |
| D. Administrative support | 5,979.7 |  | 6,028.6 | 5,659.8 |
| Subtotal | 34,209.5 |  | 35,541.5 | 32,855.9 |
| PSC | 4,447.2 |  | 4,620.4 | 4,271.3 |
| Working Capital Reserve | 187.4 |  | 281.9 | 54.0 |
| Total requirements | 38,844.1 |  | 40,443.8 | 37,181.2 |

#### Table 6. Distribution of resources by component in percentage

(In percentage)

|  | Authorized | ZRG | ZNG |
| --- | --- | --- | --- |
|  | 2019-20 | 2023-24 | 2023-24 |
| A. Governing and Subsidiary bodies | 12.8 | 12.9 | 13.9 |
| B. Executive direction and management | 15.5 | 17.5 | 16.7 |
| C. Programme of work | 54.2 | 52.7 | 52.2 |
| D. Administrative support | 17.5 | 17.0 | 17.2 |
| Total | 100.0 | 100.0 | 100.0 |

a/ Included the provision of $1,310,000 for extraordinary meetings on the post-2020 global biodiversity framework

## B. 	Extrabudgetary resources

- The Secretariat continues to rely on voluntary contributions which are vital for the delivery of its mandates. The present section describes the preliminary estimate of the resources required developed in the context of the results-based management framework (see section III). The estimates will be refined following an analysis of draft decisions for the three bodies and an updated estimate will be provided. The estimate comprises the resources required by the Secretariat to undertake the programme of work for the period 2023-2024 under the following three special trust funds: (a) the Special Voluntary Trust Fund for Additional Voluntary Contributions in Support of Approved Activities (BE), (b) Special Voluntary Trust Fund (BZ) for facilitating the participation of Parties and (c) the Special Voluntary Trust Fund for the Participation of Indigenous and Local Communities (VB) for voluntary contributions.

Special Voluntary Trust Fund for Additional Voluntary Contributions in Support of Approved Activities (BE)

- The total resource requirements from the Special Voluntary Trust Fund for Additional Voluntary Contributions in Support of Approved Activities (BE) for the biennium 2023-2024, to complement the Zero-Real Growth Budget Scenario, is estimated at $21,630,000 for non-staff costs for the Convention and the two Protocols, as can be seen from the table below. In the case of the Zero-Nominal Growth budget, additional resources would be required through the BE Fund.

- In addition, resources would be required to cover the costs of staff posts that are not provided for in the core budget. It is expected that the ongoing analysis based on draft decisions and the results-based framework will identify the need for additional staff posts.

#### Table 7. Total resource requirements from the Special Voluntary Trust Fund for Additional Voluntary Contributions in Support of Approved Activities (BE) for the biennium 2023-2024 according to outcomes in the results-based framework

(Thousands of United States dollars)

| Number | Outcome | Consultants | Travel incl DSA | Contractual services | Transfers to Partners | Operational costs | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Through the Convention and its Protocols, the international community increasingly converges on common and integrated gender-sensitive approaches to biodiversity conservation, sustainable use and the fair and equitable sharing of the benefits arising out of the utilization of genetic resources | 3,149.9 | 2,226.0 | 396.0 | 50.0 | 230.0 | 6,051.9 |
| 2 | Through the application of the global biodiversity framework, national implementation of the Convention and its Protocols for improved status of biodiversity is enhanced | 1,980.6 | 1,986.0 | 935.0 | 2,515.0 | 45.0 | 7,461.6 |
| 3 | Awareness and action to conserve, sustainably use, and share the benefits of biodiversity is enhanced at all levels and across sectors of society | 612.0 | 345.0 | 245.0 | 1,470.0 | 125.0 | 2,797.0 |
| 4 | Regular review and assessment contribute to adaptive management and progressive enhancement of the implementation of the Convention and its Protocols | 1,276.5 | 1,940.0 | 816.0 | 740.0 | 12.0 | 4,784.5 |
| 5 | The CBD Secretariat is well managed. | 245.0 |  |  | 235.0 | 30.0 | 510.0 |
| 6 | Improved programme support for the Secretariat | 25.0 |  |  |  |  | 25.0 |
| Total |  | 7,289.0 | 6,497.0 | 2,392.0 | 5,010.0 | 442.0 | 21,630.0 |

- The Japan Biodiversity Fund (JBF), established by the Government of Japan as a legacy of its Presidency of the tenth meeting of the Conference of the Parties, continues to fund and facilitate capacity-building activities organized or led by the Secretariat and will be providing funding for a total of 5 posts (1 D-1, 2 P-4 and 2 GS) under the Special Voluntary Trust Fund for Additional Voluntary Contributions in Support of Approved Activities (BE).

Special Voluntary Trust Fund (BZ) for facilitating the participation of Parties

- The BZ Trust Fund for facilitating the participation of Parties is used by the Secretariat to provide eligible Party representatives with airline tickets and daily subsistence allowances to enable them to participate in meetings of the Conference of the Parties to the Convention, the Conference of the Parties serving as the meeting of the Parties to the Cartagena Protocol and the Conference of the Parties serving as the meeting of the Parties to the Nagoya Protocol. The Fund is also used to support the participation of eligible party representatives in the meetings of the subsidiary and associated bodies of the Convention and the Protocols.

- The Conference of the Parties has consistently noted the need for full participation of all Parties including developing country Parties and called for support to be provided for at least two delegates to its meetings. However, in the past, resources available have allowed the Secretariat to cover the costs of only one representative for each eligible Party. However, with the resumption of in-person meetings following restrictions due to the COVID-19 pandemic, and the convening of concurrent meetings of three bodies (the third meeting of the Open-Ended Working Group on the Post-2020 Global Biodiversity Framework (WG2020-3); the Subsidiary Body on Implementation (SBI-3) and the Subsidiary Body on Scientific, Technical and Technological Advice (SBSTTA-24) in Geneva, Switzerland in March 2022, the Bureau, in consultation with the respective Chairs and the Secretariat, determined that it was essential to fund at least two participants from each eligible Party, given that there were a significant number of issues that needed to be resolved. The same approach was used for the fourth meeting of the Working Group (WG2020-4) in Nairobi. Similarly, contributions are solicited to cover the cost of three participants per eligible Party for the meetings of COP-15 and of the Parties to the Protocols to enable all three instruments to be covered. Against this background, the Secretariat has prepared the following two options for each of the three sets of meetings, for consideration by the Conference of the Parties and by the meetings of the Parties to the Protocols:

#### Tables 8. Options for the funding of participants in meetings

Table 8 (a)

| A. Back-to-back SBSTTA+WG8J (8 days in Montreal) Options in 2023: | USD |
| --- | --- |
| Support for one delegate from each eligible Party to participate in an 8-day session (back-to-back) organized in Montreal | 859,700 |
| Support for two delegates from each eligible Party to participate in an 8-day session (back-to-back) organized in Montreal | 1,719,400 |

Table 8 (b)

| B. Back-to-Back SBSTTA+SBI (11 days in Montreal) Options in 2024: | USD |
| --- | --- |
| Support for one delegate from each eligible Party to participate in an 11-day session (SBSTTA 6 days, SBI 5 days) organized in Montreal | 1,003,400 |
| Support for two delegates from each eligible Party to participate in an 11-day session (SBSTTA 6 days, SBI 5 days) organized in Montreal | 2,006,800 |

Table 8 (c)

| C. COP-16 (14 days if in Istanbul) Options: | USD |
| --- | --- |
| Support for two delegates from each eligible Party, to participate in a two-week session organized in Istanbul | 1,747,700 |
| Support for three delegates from each eligible Party, to participate in a two-week session organized in Istanbul | 2,621,500 |

- It should be noted that these cost estimates include project support costs as required by UN rules. Notwithstanding resolution 2/18 of the United Nations Environment Assembly of UNEP, the United Nations Controller has informed UNEP that requests for waiver of PSC for donor contributions to support the travel of meeting participants from developing countries would not be approved.

- The Conference of the Parties also requested the Executive Secretary, in paragraph 37 of decision 14/37, to submit a proposal for adoption at COP-15, to revise the structure and rules related to the BZ Trust Fund adopted at the ninth meeting of the Conference of the Parties to address the perennial problem of the lack of predictable and sustainable funding. This report is contained in document CBD/COP/15/7/Add.3.

- With regard to the Special Voluntary Trust Fund for the Participation of Indigenous and Local Communities (VB), the Secretariat estimated that an amount of $455,200 will be required to ensure the participation of indigenous peoples and local communities, representing the indigenous regions of Africa, Asia, the Arctic, Central and Eastern Europe (CEE), North America, Latin America and the Caribbean, and the Pacific in meetings of vital importance to them, particularly the Ad Hoc Open-ended Working Group on Article 8(j) and Related Provisions, and in the deliberations concerning the Nagoya Protocol on Access and Benefit-sharing, SBI, SBSTTA and COP-16 as can be seen from the tables below.

#### Table 9. Estimated amount for the participation of indigenous peoples and local communities in meetings

|  | USD |
| --- | --- |
| Support for three delegates from each eligible region* to participate in an 8-day session of SBSTTA and WG8J back-to-back organized in Montreal (average per region) | 115,300 |
| Support for two delegates from each eligible region* to participate in an 11-day session of SBSTTA and SBI back-to-back organized in Montreal (average per region) | 94,600 |
| Support for five delegates from each eligible region* to participate in a 14-day session of COP-16 in Istanbul (average per region) | 245,300 |

* Africa, Asia, Arctic, CEE, North America, Latin America and Caribbean, Pacific

- In addition, the Government of Canada, in tandem with the Province of Quebec, renewed its host country grant agreement, which covers the rent of the premises and other associated costs including utilities for the Secretariat’s existing office space in Montreal, Canada, with an estimated value of CAD 3,775,000 (approximately USD 2,918,700) for the biennium 2023-2024 based on the existing lease.

# III.	RESULTS-BASED FRAMEWORK

- The world’s ecosystems and biodiversity are fundamental to human well-being and a healthy planet. Despite ongoing efforts, worldwide, biodiversity is declining at an alarming rate and is projected to continue or worsen under “business-as-usual” scenarios. Over the past 50 years, changes to the use of land and water, over-exploitation of natural resources, climate change, pollution and invasive alien species have led to considerable biodiversity loss and the degradation of ecosystems. Human-induced changes such as unsustainable consumption and production patterns and human population dynamics combined with weak governance have been identified as key underlying causes.

- In 2010, the Conference of the Parties adopted the Strategic Plan for Biodiversity 2011-2020, organized around 5 goals and 20 targets. The fifth edition of the Global Biodiversity Outlook (GBO) in 2020 reported that at the global level, none of the 20 targets had been fully achieved but six had been partially achieved. Despite limited progress in achieving the targets, the report concluded that it is not “too late to slow, halt and eventually reverse current trends in the decline of biodiversity”.  Both the GBO and the Global Assessment Report on Biodiversity and Ecosystem Services issued by the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services call for several transformational actions that would need to take place to restore ecosystems and biodiversity to put humanity on a path to achieve “living in harmony with nature by 2050”.

- In response to the increasingly dire state of biodiversity and ecosystems, Parties to the Convention and its Protocols have been developing a new strategic plan for the next decade, for adoption at the second part of COP-15. The post-2020 global biodiversity framework will provide a roadmap that includes goals and ambitious targets that will help countries protect and restore ecosystems and biodiversity to put humanity on a path to living in harmony with nature by 2050.

- The Secretariat’s programme of work aims to contribute to creating the enabling conditions for Parties to take urgent action and implement necessary transformations proposed by the global biodiversity framework, while facilitating the ongoing development and review of international biodiversity policy and approaches under the Convention and its Protocols. The Secretariat’s results are outlined in the theory of change and consist of four higher-level outcomes to be achieved over the next 10 years with key outputs planned at a 4-year interval and sub-outputs planned for the 2023-2024 biennium.

#### Table 10. Theory of Change

- The Secretariat’s theory of change holds that if Parties invest adequate human, financial and technological resources then the Secretariat can carry out activities that generate robust knowledge and information outputs and facilitate meetings and processes for the Parties it serves. If the Secretariat can reach its Parties and other relevant stakeholders through its approaches, products and services then it will contribute to raising awareness, strengthening capacities, mobilizing additional resources and sectors, and catalyzing action to change harmful behaviors and practices towards biodiversity conservation and restoration, foster sustainable use and the fair and equitable sharing of benefits that arise from the utilization of genetic resources. If these behaviours and practices are changed then all of society and all of government will work to reduce threats to biodiversity, while understanding and demonstrating how protecting and restoring ecosystems and using biodiversity sustainably benefit people, prosperity and the planet, and ultimately achieve the Convention’s vision of people everywhere “living in harmony with nature by 2050”.

Assumptions underpinning the Theory of Change

- Bringing about policy and social change is not a linear process and there are multiple factors that can facilitate or hinder the Secretariat’s contributions. The Secretariat is expected to achieve its results provided that the following conditions are present:

- The products and services generated by the Secretariat are timely, relevant and effective;

- The Secretariat has adequate internal resources and is well structured and managed;

- The importance of taking urgent action is understood and acted on by Parties at all levels;

- There is support from Parties and other stakeholders for strong synergies with other multilateral agreements aligning action to the 2030 Agenda for Sustainable Development and the Sustainable Development Goals (SDGs) to ensure policy coherence and consistency;

- Adequate level of resources for global and domestic implementation is mobilized;

- There is strong, worldwide political will for transformational and urgent change to reverse the trajectory of biodiversity loss.

- Some of the external factors that will support the achievement of the expected results include:

- Growing support within the United Nations system for mainstreaming biodiversity across the sustainable development agenda;

- The targets and indicators of the post-2020 global biodiversity framework are recognized as essential to the achievement of the 2030 Agenda for Sustainable Development and the Sustainable Development Goals, including SDGs 15 and 14, among others;

- Growing demand for ecosystem-based approaches and solutions provided by biodiversity to climate change, food and water security, disaster risk reduction and other sustainable development objectives, as well as the incorporation of the values of nature in national accounting and reporting;

- More disclosures on the impacts on biodiversity and dependencies on biodiversity from productive sectors to inform, guide and improve sustainable consumption and production patterns.

- At the same time, there are risks that may hinder expected accomplishments which include:

  - Insufficient political commitment at the national, regional, and global levels;

  - Lack of policy coherence at the national, regional, and global levels;

  - Competing priorities including land use demands;

  - The lack of or insufficient resources for biodiversity among COVID-19 recovery priorities and growing debt crises;

  - Limited capacities (enabling environment, organizational and individual) to support implementation at the national level.

- The objective of the Secretariat in the context of the theory of change is to facilitate and support the work of the Parties to the Convention and its Protocols to strengthen environmental governance through the development, implementation and regular review of international agreements and approaches for biodiversity. In addition to facilitating and supporting the Convention and Protocol processes, the Secretariat’s strategy includes supporting the implementation of the post-2020 GBF which sets forth medium-term agendas with biodiversity goals and targets for Parties. The post-2020 global biodiversity framework will be the successor of the Strategic Plan for Biodiversity 2011-2020 and its Aichi Biodiversity Targets which was adopted in 2010.

- The processes undertaken in the context of the Convention and its Protocols aim to contribute to ensuring urgent action is taken by Governments and other relevant stakeholders to put biodiversity and ecosystems on a path to recovery for the benefit of planet, people and prosperity, and to achieve the 2050 Vision of living in harmony with nature.

- The Secretariat will support the implementation of this framework over the next 10 years by focusing on contributing to the four substantive outcomes outlined in its theory of change as elaborated above. As part of the strategy, the Secretariat will invest in developing in-house capacities to support gender sensitive approaches and implementation. An internal gender mainstreaming plan will be developed to strengthen the Secretariat’s capacities to apply gender sensitive approaches in the delivery of its products and services. Another strategic approach will involve focusing on establishing and strengthening existing cooperation and strategic partnerships to support implementation of the global framework and supportive strategies, including the long-term approach on mainstreaming biodiversity across productive sectors and to support the development and strengthening of national capacities to integrate, plan and implement biodiversity commitments and actions.

- In order to contribute towards achieving the first outcome during 2023–2024, the Secretariat will facilitate evidence-based analyses and technical work to support the decision-making processes of the Convention and its Protocols and organize meetings of the Convention and Protocols that will enable Parties to continue to converge on common and integrated approaches to biodiversity conservation, sustainable use and the fair and equitable sharing of the benefits arising out of the utilization of genetic resources.  The Secretariat will also foster synergies with other multilateral environmental agreements, processes, and international organizations to realise further policy coherence and coordination. Moreover, specific activities will be carried out to foster greater integration of biodiversity into the United Nations system especially including through the United Nations Common Approach to Biodiversity, Environment Management Group (EMG) and mainstreaming the new biodiversity targets into the United Nations Sustainable Development Cooperation Frameworks at the country level.

- In relation to the second outcome, over the next biennium, the Secretariat will promote national implementation of the Convention and its Protocols through the application of the post-2020 global biodiversity framework. This will be accomplished by providing guidance and promoting partnerships for resource mobilization by Parties and relevant stakeholders to support national implementation. Moreover, the Secretariat will not only continue to promote the development of technical capacities, but a shift will be made to place greater focus on institutional capacity development for the effective implementation of the Convention and its Protocols. This will entail fostering all stakeholder engagement including gender and local communities, youth, etc., responsive global and regional programmes implemented through or by partners, that will support biodiversity-relevant capacity development at the national level. In addition, the Secretariat will foster partnerships with other UN funds and programmes to promote the integration of biodiversity targets and commitments in countries’ United Nations Sustainable Cooperation Frameworks. Greater investments will be made to enhance knowledge management through the clearing-house mechanisms and the provision of timely and good quality data and information specially to support the global monitoring framework.

- With regard to its third expected outcome, the Secretariat will enhance its endeavours to raise awareness and catalyse action to conserve, sustainably use, and share the benefits of biodiversity at all levels and across sectors of society. This will be achieved through a renewed stakeholder engagement including local communities, youth and gender responsive communication strategy that will include compelling message frameworks for different audiences. Moreover, the Secretariat will ensure strong presence in high level political events and will work with non-State partners and country champions to carry out campaigns and engage and mobilize all types of stakeholders to promote biodiversity, including through the Sharm el-Sheikh to Kunming Action Agenda for Nature and People. The Secretariat will also continue its outreach and awareness raising efforts to increase ratification and implementation of its Protocols, and will invest in participating or getting the core biodiversity related messages across in high-level meetings of the High-Level Political Forum on Sustainable Development (HLPF) and United Nations General Assembly (UNGA), as well as other fora such as the Group of 7 (G7) and the Group of 20 (G20), to reinforce political commitments and ambition for the implementation of the post-2020 global biodiversity framework.

- In relation to the fourth outcome, at its fourteenth meeting, in decision 14/34, the Conference of the Parties committed to an enhanced review mechanism with a view to strengthening the implementation of the Convention and its Protocols and achieving the goals and targets under the post-2020 GBF. To support Parties, the Secretariat will provide relevant and gender-sensitive guidance to enhance national planning, monitoring, and reporting. To foster synergies with other MEAs and the SDGs, and to alleviate the reporting burden for Parties, the Secretariat will promote harmonized and integrated reporting tools. Moreover, the Secretariat will facilitate party by party review of implementation of the Convention by organizing an SBI open-ended forum and promoting that Parties participate in voluntary peer-review processes. Additionally, the Secretariat will further step up its efforts to monitor and assess the status of biodiversity and implementation of obligations under the Convention and its Protocols. This will be accomplished through enhanced tools, including the Decision-Tracking Tool and capacity for high-quality monitoring of the global biodiversity framework targets; relevant assessments and stock taking, and evidence-based analysis to contribute to global review and decision-making.

- The following table presents the four substantive outcomes along with indicators of achievement. The baselines and targets have yet to be determined.

#### Table 11. Outcomes, indicators of achievement and performance measurements

| Objective of the Secretariat: Facilitate and support Parties of the Convention and its Protocols to strengthen environmental governance through the development, implementation and regular review of international agreements that seek to achieve the 2050 vision of living in harmony with nature |  |  |  |
| --- | --- | --- | --- |
| Outcomes of the Secretariat | Indicators of achievement |  | Baselines and Targets |
| (a) Through the Convention and its Protocols, the international community increasingly converges on common and gender-sensitive approaches to biodiversity conservation, sustainable use and the fair and equitable sharing of the benefits arising out of the utilization of genetic resources | 1.1 Proportion of Parties addressing biodiversity issues in line with guidance emerging from CBD and Protocol processes |  | B: TBD; T: TBD |
|  | 1.2 Proportion of Parties integrating globally agreed targets and guidance into broader national strategies, plans, policies, reporting systems and budgets |  | B: TBD; T: TBD |
|  | 1.3 Proportion of members of the United Nations Environment Management Group and international non-governmental organizations addressing biodiversity issues in line with guidance emerging from CBD and Protocol processes at the global and regional levels |  | B: TBD; T: TBD |
|  | 1.4 Increased membership to the Convention and its Protocols |  | B: Convention : 193; Nagoya Protocol: 138; Cartagena Protocol: 173; T: 100%; Nagoya Kuala Lumpur supplementary Protocol: 51, T: 10% increase |
| (b) Through the application of the global biodiversity framework (GBF), national implementation of the Convention and its Protocols for improved status of biodiversity is enhanced | 2.1 Increased funding for implementing GBF |  | B: TBD; T: TBD |
|  | 2.2 Parties report progress in achieving GBF targets in a gender-sensitive way |  | B: TBD; T: TBD |
|  | 2.3 Parties show progress in developing capacity at different levels (enabling environment, organizational and individual levels) |  | B: TBD; T: TBD |
|  | 2.4 Number of global and regional partnerships supporting the implementation of GBF (CBD and Protocols) at the national level |  | B: TBD; T: TBD |
| (c) Awareness and action to conserve, sustainably use, and share the benefits arising from the utilization of biodiversity is enhanced at all levels and across sectors of society |  | 3.1 Number of global and regional high-level political fora addressing biodiversity | B: TBD; T: TBD |
|  |  | 3.2 Number of times biodiversity is mentioned in resolutions resulting from international political debates | B: TBD; T: TBD |
|  |  | 3.3 Level of exposure of biodiversity in traditional and social media. Number of print, online and broadcast pieces, and potential reach; Social media reach, engagement rate and number of followers | B: TBD; T: 15% increase of print, online and broadcast pieces; 25% increase engagement and followers |
|  |  | 3.4 Number of multilateral decisions and resolutions on climate change and SDGs that incorporate biodiversity | B: TBD; T: TBD |
| (d) Regular monitoring, review and assessment contribute to informed planning and decision-making at all levels, resulting in progressive enhancement of the implementation of GBF, the Convention, and its Protocols |  | 4.1 Number of Parties reporting on their commitments and achievements according to the established review mechanisms 4.2 Status and trends of biodiversity are assessed nationally and globally and inform decision-making 4.3 Commitments and actions by Parties and other actors are revised in the light of the review mechanisms such that they are commensurate with targets of GBF and the obligations of the Protocols 4.4 Number of Parties assessing progress using SBI review mechanisms | B: TBD; T: TBD B: TBD; T: TBD B: TBD; T: TBD B: TBD; T: TBD |
| (e) The Secretariat is well led and managed. |  | 1. Proportion of staff expressing satisfaction with leadership and management 2. Proportion of accepted audit recommendations fully implemented 3. Proportion of audit findings rated as satisfactory or higher | Survey methodology and baseline to be developed Baseline : TBD; T: 100% Baseline : TBD; T: 100% |

## Monitoring progress in results-based budgeting

- The Secretariat is also required to prepare a monitoring and evaluation policy and plan for the biennium 2023-2024 designed to review progress and achievements against the results-based budget framework presented below to ensure accountability for the delivery of results assigned to the various divisions across the Secretariat.

- Resources under the proposed budget will be required to further develop and institutionalize the results-based budget framework as well as to develop indicators of achievements and fine-tune baselines for monitoring and evaluation processes. The evaluation policy and plan will ensure that mechanisms are put in place to assess the achievement of results and the sustainability, efficiency, and effectiveness of the delivery of the programmes, and will make use of evaluations to help assess the overall performance of the programmes in terms of results. The evaluation plan will include monitoring and periodic review of the Secretariat’s system wide workplan, which is based on the results-based budget format, taking into account deliverables and indicators of achievements by Divisions and Units, and includes meetings of the Convention and its Protocols, processes, initiatives, and projects. The evaluation and monitoring framework will be complemented by feedback on the Secretariat’s system-wide workplan, as well as programme coordination and implementation provided through a combination of measures including comprehensive monitoring coordinated by the office of the Executive Secretary. It is envisaged that project evaluations will be undertaken by external entities for projects above $500,000 to document results, assess performance and collect good practices and lessons learned. The new Integrated Project Management and Reporting tool (IPMR), which is an integral part of Umoja will be used to plan, design, manage and report on projects while the UN’s Strategic Management Application (SMA) is being adapted for use by the multilateral environmental agreements to plan and monitor implementation of their programmes of work.

- It is proposed that the evaluation and monitoring functions as mandated by the United Nations General Assembly will be carried out through the establishment of a Programme Officer position at the P-4 level in the Office of the Executive Secretary (see section C below). The staff member would oversee the rollout of the Umoja’s IPMR solution in the Secretariat, a key enabler of the United Nations Secretary-General’s management reform and data strategy initiatives, by providing qualitative and quantitative information on programme delivery as well as utilizing the results-based management methodology, to ensure effective management of programmes and projects. The new function is described in further detail in paragraph ‎77 below. With respect to each project funded from trust funds and earmarked contributions, evaluation costs form part of the project budget, based on the scope, duration, and complexity of the project.

# IV.	BUDGET PROPOSAL BY COMPONENTS

- This section provides details on the budgeting of resources under the three scenarios mandated in decision 14/37 and under four distinct components: (a) governing and Subsidiary Bodies; (b) executive direction and management; (c) delivery of work programme, which covers the substantive work of the Secretariat, and (d) administrative support.  It further attempts to align the budget document with the format of the biennial programme of work and budget of UNEP to better support decision-making and increase the transparency of information and introduce an element of monitoring of implementation and evaluation as part of a results-based management framework, in line with the Secretary-General’s bulletin ST/SGB/2018/3 of 1 June 2018, which governs the planning, programming, monitoring and evaluation of United Nations activities.

- As a result, the resources required for the Secretariat’s planned and scheduled meetings, such as COP, SBSTTA, SBI, WG8J, other expert meetings, informal advisory meetings, and bureau meetings are presented under sub-section A (Governing and Subsidiary Bodies) below.  Similarly, the resources required for management and coordination are presented under B (Executive Direction and Management), while the resources required for substantive units and divisions are contained under C (Programme of work), and lastly the administrative support are under sub-section D.

## A.  Governing and Subsidiary Bodies

Resource requirements (core budget): $4,568,900

- The Conference of the Parties is the governing body of the Convention and advances implementation of the Convention through the decisions it takes at its periodic meetings. Since 2000, the ordinary meetings of the Conference of the Parties are held every two years for a period of approximately two weeks except for COP-15, whereby the first part of COP-15 that took place in China, from 11 to 15 October 2021 and the second part of COP-15 is scheduled to take place in Montreal, Canada from 7 to 19 December 2022 due to the COVID-19 pandemic.

- The Conference of the Parties serving as the meeting of the Parties to the Cartagena Protocol is the governing body of the Cartagena Protocol on Biosafety. From 2004 to 2014, meetings of the Parties to the Protocol were held for one week (five days) back-to-back with meetings of the Conference of the Parties to the Convention. Beginning in 2016, meetings of the Parties to the Protocol have been held concurrently within the same two-week period as the Conference of the Parties to the Convention.

- The Conference of the Parties serving as the meeting of the Parties to the Cartagena Protocol also serves as the governing body for the Nagoya–Kuala Lumpur Supplementary Protocol on Liability and Redress. The Conference of the Parties serving as the meeting of the Parties to the Nagoya Protocol is the governing body of the Nagoya Protocol on Access and Benefit-Sharing. With the entry into force of the Protocol on 12 October 2014, the first meeting of the Parties to the Protocol was held concurrently with the second week of the twelfth meeting of the Conference of the Parties to the Convention. Subsequent meetings of the Parties to the Nagoya Protocol have been held concurrently within the same two-week period as the Conference of the Parties to the Convention.

- An amount of $2,050,000 is required to cover the costs associated with, inter alia, interpretation, translation, report writing and licence costs for the sixteenth meeting of the Conference of the Parties as well as the eleventh meeting of the Parties to the Cartagena Protocol and the fifth meeting of the Parties to the Nagoya Protocol. This figure does not include the cost of the venue or other costs associated with holding the meeting which would need to be borne by the host country or provided through extra-budgetary resources.

- In addition, resources are also required for the Secretariat’s regular meetings of SBSTTA, SBI, WG8J and other expert meetings, informal advisory meetings including bureau meetings in the biennium 2023-2024.

- As such, it is anticipated that SBSTTA-25 (3.5 days) will be held back-to-back with WG8J-12 (3.5 days) in 2023, for a total cost of $790,000. Similarly, it is anticipated that SBSTTA-26 (5 days) will be held back-to-back with SBI-4 (5 days) in 2024 for a total cost of $1,130,000. These cost estimates are based on estimated costs for simultaneous interpretation, translation of documents, report writing, security and limited use of a virtual meeting platform. They also cover an allocation of costs for the venue if held at the headquarters of the International Civil Aviation Organization (ICAO) in 2023 in Montreal. Canada. If ICAO is not available at the dates required, if a different venue is required to accommodate the larger attendance seen at recent meetings of the subsidiary bodies, or if additional services are required, then additional funding would be required through the voluntary budget.

- In accordance with prior practice and based on incurred expenditures in prior biennia, it is estimated that an amount of $320,000 will be required to cover the costs of the following expert meetings scheduled for 2023 and 2024, as follows: (a) one meeting of the Informal Advisory Committee to the Access and Benefit-sharing Clearing-House ($30,000); (b) one meeting of the Informal Advisory Committee to the Clearing-house Mechanism ($40,000); one meeting of the Informal Advisory Committee to the Biosafety Clearing-House ($40,000). In addition, three expert meetings are planned for 2024 as follows: (a) one meeting of the Compliance Committee under the Nagoya Protocol on Access and Benefit-sharing ($30,000); and (b) one meeting of the Informal Advisory Committee on Capacity-building for the Implementation of the Nagoya Protocol ($30,000). It is also anticipated that two meetings of the Compliance Committee under the Cartagena Protocol on Biosafety ($45,000 each) and two meetings of the Liaison Group for the Cartagena Protocol on Biosafety ($30,000 each) will take place both in 2023 and 2024.

- It may be noted that many of these in-person meetings are complemented by virtual discussions, e.g., there is regular information exchange by e-mail and through online discussion forums in support of the work of the informal advisory committees for the clearing-houses. However, in-person meetings remain necessary for decision-making.

- Provision of $278,900 is also made to cover the costs of travel for 8 Bureau members and 4 substitute Bureau members to attend Bureau meetings convened in association with the meetings of COP, SBI and WG8J.  This represents a reduction in costs compared to previous biennia, due to the increased use of video conferencing.  The costs of SBSTTA bureau meetings are included in the estimate for the meeting above in line with established practices.

- These non-post resources totalling $4,568,900 will provide for, inter alia, rental of premises, interpretation, report writing, translation and other conference services-related costs including hospitality to support the work of COP, MOPs, SBI and SBSTTA. It should be noted that the meetings will be serviced by relevant staff of the Secretariat, and as such, the post-related costs are included under the relevant divisions and units of the Secretariat.

## B.  Executive direction and management

### Office of the Executive Secretary

Resource allocation: $6,206,200

- The overall executive direction and integrated management of the Secretariat is led by the Executive Secretary. Under the Executive Secretary’s management direction, the Office of the Executive Secretary ensures effective coordination of the Secretariat’s activities and reviews progress in the implementation of the Secretariat’s integrated work programme with the view to promoting coherence and cost-effectiveness for the Secretariat’s work but also to respond to the Parties’ needs and requests. Responsibilities include providing the vision and direction for the work of the Secretariat, setting strategic priorities for effective and efficient management and execution of the Secretariat’s work, setting policy guidelines for divisions, providing representation and strategic political outreach, developing new partnerships, and liaising with Parties’ delegations, and other United Nations organizations, funds and programmes, as well as other intergovernmental organizations, and strategic partners. The coordination and management of the Secretariat’s activities is ensured through regular meetings of the senior management team, chaired by the Executive Secretary, and composed of the Heads of Divisions and other staff within the Office of the Executive Secretary, as well as through regular management meetings, which include senior managers and heads of units.

- The Office of the Executive Secretary includes the function of the Deputy Executive Secretary which has delegated responsibility for coordinating and reporting on the agendas for COP, MOPs, and the Subsidiary Bodies, to ensure the coherence of the concurrent meetings. The additional supervision functions for the work of the Protocols assigned to the Deputy Executive Secretary supports further integration between the Convention and the Protocols, enhancing consistency of procedures and improving the efficiency and the effectiveness of processes and structures under the three bodies. As such, both the Units responsible for the protocols report directly to the Deputy Executive Secretary and are part of the Office of the Executive Secretary. The costs associated with substantive work of the Access and Benefit-sharing and Biosafety Units are covered under the next section (see sub-section 1 below).

- The Office of the Executive Secretary also includes the Legal and Intergovernmental Affairs Unit headed by the Senior Legal Officer which provides legal advice and support to the Convention and Protocol processes and staff of the Secretariat, advising on the proper management of intergovernmental processes, the application of rules of procedure and practices so that such rules and practices are adhered to and guide the work of the Secretariat and the treaties bodies and processes. The functions of the Unit also include reviewing substantive governing bodies documents emanating from Divisions to ensure consistency and correct mandate references and responses as well as previous decisions of the Conference of the Parties, and maintaining the Decision-Tracking Tool consistent with the purpose identified by the Conference of the Parties in its decision XII/28. The Unit also provides legal advice on various substantive matters that are legal in their nature or have legal implications.

- The Office of the Executive Secretary also includes the Japan Biodiversity Fund (JBF) team led by the Global Coordinator which manages this fund in support of the implementation of the Convention and the Protocols and is entirely funded by a voluntary contribution by the Government of Japan. The fund has been extended to support the implementation of the post-2020 GBF to be adopted at the second part of COP-15.

- Effective 1 January 2021, the Conference Services Unit, responsible for facilitating, supporting, and coordinating the logistical aspects of the organization of meetings under the Convention and its Protocols, reports to the Deputy Executive Secretary, who is responsible for all the Secretariat’s major meetings and serves as the Secretary of the Conference of the Parties. The Unit is part of the Office of the Executive Secretary. It ensures the successful organization of meetings under the Convention and its Protocols by arranging for suitable conference services, including facilities and staffing, and through the timely production, translation and distribution of pre-session, in-session and post-session documentation.

- The Office of the Executive Secretary also includes a Special Advisor, working with the Executive Secretary as well as the Deputy Executive Secretary, other members of the Senior Management Team and Units to advise and follow up on key processes, partnerships, and initiatives to support the Convention’s rapidly growing political work. The Special Advisor also coordinates new activities including the Secretariat system-wide workplans, UN system-wide responses related to COVID-19, preparations on the United Nations Chief Executives Board for Coordination (CEB) Common Approach to Biodiversity and Nature Based Solutions, annual coordination on the high-level political forum on sustainable development, high-level political relations, and leads the management of the Sharm el-Sheikh to Kunming Action Agenda for Nature and People.

- The Office of the Executive Secretary also includes and relies upon the joint Liaison Office of the United Nations Convention to Combat Desertification (UNCCD) and CBD at the Headquarters of the United Nations (UNHQ) in New York that comprises (for the purposes of CBD) two half-time staff for strategic engagement and reporting, among other normative aspects, under the Economic and Social Council (ECOSOC), the second Committee of the General Assembly and other aspects related to the SDGs. These two half-time staff members are funded by programme support costs.

- The Secretariat Support Unit is also a part of the Office of the Executive Secretary and supports the Executive Secretary and the Deputy Executive Secretary in coordinating the external activities of the Secretariat and provides a resource channel between the Office of the Executive Secretary and the Parties, relevant intergovernmental and non-governmental organizations, major stakeholder groups and inter-agency processes as well as the Divisions, and Units of the United Nations Secretariat.

- To increase efficiencies and transversal communication services, the Communications and Awareness Unit is also a part of the Office of the Executive Secretary. The Unit supports the Secretariat’s strategic vision and goal to increase the visibility of the work of the Convention within the United Nations system, non-UN organizations, and the public, by leading the planning, design and delivery of activities and initiatives for common communications, advocacy, and outreach initiatives. The Unit is also improving the identification and development of storylines for publications and substantive articles to be published on the web and in other media channels.

- The Office of the Executive Secretary is responsible for the overall programme of work of the Secretariat. In addition to the four programmatic expected accomplishments presented in section C on the results-based framework, the Office of the Executive Secretary also oversees the implementation and delivery of the objectives and outputs reflected in table 12 below for the biennium 2023-2024. Underpinning the success of the Secretariat to achieve results is a commitment to strengthen leadership, management, and accountability. This will be accomplished by strengthening managerial capacities and installing dedicated internal planning, implementation, monitoring and evaluation functions. Implementable programmes of work combined with enhanced internal communications and adequate delegation of authority will be important elements of the strategy. The Office of the Executive Secretary is also directly responsible for several substantive outputs under the Secretariat’s programme of work which have been reflected in section C.

#### Table 12. Outputs related to strengthened leadership and management

Outputs and sub-outputs

Secretariat’s strategic leadership and managerial capacities are strengthened - Senior management team and heads of units undergo 360-degree management quality assessments - Two-way communication and information sharing take place regularly to set, review and enhance the organizational direction for the Secretariat

Dedicated planning, implementation, monitoring and evaluation capacity put in place - Implementable secretariat system wide workplan and results-based programme of work, based on COP and MOP decisions - Review of the Secretariat structure according to the priorities of the programme of work - A dedicated Results-Based Management Unit is made operational to lead the monitoring and maintenance of the results-based workplan, the management and monitoring and evaluation of programmes and projects, fundraising and donor relations. - Evaluation policy and work plan developed, and evaluations undertaken

#### Table 13. Resource allocations: Office of the Executive Secretary (excluding ABS and Biosafety Units)

|  | Resources (thousands of United States dollars) |  |  |  |  |  | Posts |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 |  | 2023-2024 ZRG | 2023-2024 ZNG |  | 2019-20 |  |  | 2021-22 |  | 2023-24 |  |
| Core budget |  |  |  |  |  |  |  |  |  |  |  |  |
| Post | 4,304.3 |  | 5,666.2 | 4,981.6 |  | 14 |  |  | 17 |  | 19 |  |
| Non-post | 1,000.0 | a/ | 540.0 | 500.0 | b/ |  |  |  |  |  |  |  |
| Subtotal | 5,304.3 |  | 6,206.2 | 5,481.6 |  | 14 |  |  | 17 |  | 19 |  |
| PSC (OTA) |  |  |  |  |  | 1 |  | c/ | 3 | e/ | 3 |  |
| XB |  |  |  |  |  | 7 |  | d/ | 8 | f/ | 7 |  |
| Total | 5,304.3 |  | 6,206.2 | 5,481.6 |  | 22 |  |  | 28 |  | 29 |  |
| a/ includes travel ($800,000), consultants ($100,000) and public information materials ($100,000). |  |  |  |  |  |  |  |  |  |  |  |
| b/ includes travel ($300,000), consultants ($100,000) and public information materials ($100,000). |  |  |  |  |  |  |  |  |  |  |  |
| c/ represents 50% of P-4 and 50% of GS in UNCCD-SCBD Liaison Office at UNHQ |  |  |  |  |  |  |  |  |  |  |  |
| d/ represent JBF (1 D-1, 2 P-4, 2 GS) and 1 JPO (Japan) and 1 P-3 Communications Officer (EU) |  |  |  |  |  |  |  |  |  |  |  |
| e/ represents 50% of P-4 and 50% of GS in UNCCD-SCBD Liaison Office at UNHQ and 2 s/m in the Conference Services Unit |  |  |  |  |  |  |  |  |  |  |  |
| f/ represent JBF (1 D-1, 2 P-4, 2 GS), 1 P-4 COP15 Liaison Officer and 1 JPO (Japan) and 1 P-3 Communications Officer (EU) |  |  |  |  |  |  |  |  |  |  |  |
| g/ represent JBF (1 D-1, 2 P-4, 2 GS), 1 P-4 COP-15 Liaison Officer and 1 JPO (Japan) |  |  |  |  |  |  |  |  |  |  |  |

- Post resources in the immediate office of the Executive Secretary, the Legal and Intergovernmental Affairs Unit, the Conference Services Unit and the Communications and Awareness Unit, amounting to $5,666,400 would provide for the continuation of 17 core funded posts (1 ASG, 1 D-1, 2 P-5, 3 P-4, 1 P-3, 1 P-2 and 8 GS), the proposed upgrade of the Deputy Executive Secretary from D-1 to D-2 and two new posts at the P-4 and P-3 levels respectively. These are further described below.

- The post resources for the continuation of 15.5 core funded posts for the ABS and Biosafety units (2 P-5, 1 P-4, 4.5 P-3, 2 P-2 and 6 GS) and the request for the conversion of two posts at the P-4 and P-3 levels funded from voluntary contributions are presented under Programme of work in Section C below.

- The upgrade of the Deputy Executive Secretary position from the D-1 to the D-2 level is requested to reflect the increased level of responsibilities since the reorganization that came into effect on 10 October 2018, related to the management and oversight of two Protocols and the Japan Biodiversity Fund, and since 1 January 2021, the oversight of the Conference Services Unit. The post upgrade was initially presented to the Parties at the second extraordinary meeting of the Conference of the Parties to the Convention and then at the first part of the fifteenth meeting of the Conference of the Parties.  Pursuant to the requests made by the Parties in decisions EM-2/1, paragraph 8 and 15/1, paragraph 7, the Secretariat is resubmitting this request. The reclassification of the position to the D-2 level has been approved by the Executive Director of the United Nations Environment Programme in response to a request by the Executive Secretary dated 22 May 2022.

- Under the guidance and supervision of the Executive Secretary, the incumbent will deputize for the Executive Secretary and coordinate the day-to-day operations of the Secretariat and its strategic and planning activities and substantive programme of work and lead the monitoring of the delivery of the responsibilities of the Secretariat and the work requested by Parties. The incumbent will also coordinate intergovernmental processes and activities under the Convention and its Protocols by acting as the Secretary of the Conference of the Parties and its Bureau, supervise the preparation of documents and ensure that the outputs produced by the Convention and the Protocols maintain high-quality standards, and administer the logistical arrangements, including provision of conference services, advising the chairs of the meetings and the Executive Secretary on agendas, conduct of meetings, procedures, strategies and substantive aspects of meetings and the drafting of decisions, recommendations and other outcomes of meetings, as well as liaise with and advise delegations and officers of intergovernmental organizations. In addition, the incumbent will provide policy advice to the Executive Secretary on the implementation of the Convention and its Protocols and support the Executive Secretary to lead the development and implementation of periodic strategic plans and to design approaches to address emerging issues as well as assist in high-level advocacy, represent and speak on behalf of the Executive Secretary at meetings, workshops and conferences and assist the Executive Secretary in providing strategic guidance to the Communications Unit. The incumbent will also supervise the Access and Benefit-sharing and Biosafety units and ensures coordination and integration among the Convention, the Cartagena Protocol on Biosafety and the Nagoya Protocol on Access and Benefit-sharing.  The incumbent will also advise the Executive Secretary in the results-based management of the Secretariat and in the planning, coordination and monitoring of strategic plans, programmes of work, and coordination/supervision of the administration of programme resources under his/her supervision.  He or she will also coordinate fundraising for supplementary funds including contact with officials of fundraising agencies and governments.

- By the same decision 15/1, paragraph 8, the Executive Secretary was also, on an exceptional basis, authorized to upgrade to the P-4 level the position of Special Assistant in the Office of the Executive Secretary, in accordance with all relevant United Nations rules and regulations, and was requested to provide the Conference of the Parties, at the second part of its fifteenth meeting, with information related to the legal basis, including the possible legal implications relating to the reclassification.  This information will be provided in the financial performance report referred to in paragraph ‎10 above.

- It should be noted that the United Nations General Assembly has on several occasions reaffirmed that results-based management and performance reporting are essential pillars of a comprehensive accountability framework, most recently in paragraph 13 of United Nations General Assembly Resolutions A/RES/72/303.  The United Nations General Assembly also requested the Secretary General, in paragraph 21 of resolution 74/271, to continue to take concrete measures to enhance in-house capacity for evaluation and self-evaluation.  Consequentially, the Secretariat proposes a Programme Management Officer at the P-4 level to oversee the implementation of the new RBB framework based on indicators of achievements, as well as responsible for the rollout of the Umoja’s Integrated Planning, Management and Reporting (IPMR) and Grantor modules in the Secretariat.  The establishment of this post will also address the open OIOS audit observation from 2019, which stated that the Secretariat, in consultation with UNEP should develop an evaluation policy and mechanism to facilitate evaluations of its multi-year programme of work.  As OIOS pointed out in its audit of the Secretariat (OIOS report 2019/095 of 31 October 2019), there are no defined mechanisms for evaluation at the Secretariat.  Moreover, the UNEP Evaluation Unit does not cover the activities of the Secretariats which it administers, and as a result the Secretariat has never systematically evaluated its activities to assure their relevance, efficiency, effectiveness, impact and sustainability.

- The Secretariat also proposes the conversion of a P-3 Communications Officer post, currently funded from extra-budgetary resources received from the European Union. Its inclusion under core funding from 2023 onwards is required in order to ensure stability and continuity of this communication function in a period which sees a rapid surge in communication and outreach activities at the Secretariat. The post will support communications and outreach activities, including initiatives in specific regions, on key topics, with relevant partners, building on the Convention’s global communications strategy, including through print and electronic media organizations and professionals, as well as in the systematic documentation, monitoring and evaluation of activities, at all levels. This post is key to managing the social media channels of the Secretariat, a key part of outreach.

- There has been an increased demand in recent years for Conference Services and there is therefore an urgent need to expand the Conference Services Unit. As a first step it is proposed to create two new General Service posts to support the logistical preparation for meetings.

- Non-post resources under the zero real growth scenario amount to $540,000 and would provide for travel of staff ($340,000) considering that in future some travels will be replaced by virtual and hybrid engagement as much as possible. Thus, cost estimate is based on actual expenditure pattern for the biennium 2019-2020. In addition, consultants ($100,000) and public awareness initiatives ($100,000) to support the implementation of the mandates under the programme.

- Under the zero nominal growth (0 per cent increase in nominal terms), maintaining the programme budget at the 2023-2024 level in real terms and in nominal terms, the Secretariat would propose the continuation of all existing posts and an amount of $500,000 under non-post to provide for travel of staff ($300,000) in the Office of the Executive Secretary, consultants ($100,000) and public awareness initiatives ($100,000) to support the implementation of the mandates under the programme.

## C. 	Delivery of the work programme

- The distribution of resources by Division is reflected in table 14 below.

#### Table 14. Resource allocations by Division

|  | 2019-2020 approved budget |  | 2023-2024 ZRG | 2023-2023 ZNG |
| --- | --- | --- | --- | --- |
| C. Programme of work |  |  |  |  |
| ABS and Biosafety Protocols | 4,698.5 |  | 4,927.8 | 4,278.1 |
| SSSF Division | 7,040.3 |  | 6,761.3 | 5,818.7 |
| Implementation Division | 6,813.2 |  | 7,048.8 | 7,048.8 |
| Total | 18,552.0 |  | 18,737.9 | 17,145.6 |

      - Office of the Executive Secretary: Substantive Units

(Access and Benefit-sharing Unit, Biosafety Unit,)

Resource allocation (core budget): $4,927,800 (scenario 1)

- As noted in section B, the Office of the Executive Secretary includes several units and staff that contribute to the delivery of the Secretariat’s work programme in a substantive manner. These include the ABS and Biosafety units. They also include units and staff whose work cuts across the work of the Secretariat and which work with all other units and divisions. This includes the Communications Unit, responsible for leading the work under outcome 3, and the Conference Services Unit. Similarly, the joint UNCCD/CBD Liaison Office at UNHQ in New York supports or represents the Secretariat in work of the Economic and Social Council (ECOSOC) and the second Committee of the General Assembly on all aspects related to the work of the Secretariat, also essential to outcome 3. It also includes the Special Advisor to the Executive Secretary, who advises and follows up on key processes, partnerships, and initiatives to support the Convention’s rapidly growing political work. It also includes the Legal and Intergovernmental Affairs Unit, headed by the Senior Legal Officer, which provides legal advice and support to the CBD processes and staff of the Secretariat. As such, the office of the Executive Secretary contributes towards the realization of all four substantive outcomes of the results-based framework. The specific outputs that it is directly responsible for are outlined in table 15.

- The Access and Benefit-sharing (ABS) Unit is responsible for matters related to access and benefit-sharing under the Convention and the Nagoya Protocol. The unit promotes and supports the ratification of the Nagoya Protocol by all Parties to the Convention and provides support to Parties, indigenous peoples and local communities, and relevant stakeholders in implementing access and benefit-sharing and the Nagoya Protocol. The unit facilitates and services meetings of the Conference of Parties serving as the meeting of the Parties to the Nagoya Protocol and provides relevant legal support, provides relevant capacity-building support and manages the ABS Clearing-House.  In addition, the Unit manages emerging issues such as digital sequence information on genetic resources under the Convention, in a coordinated manner with the Protocol.

- The Biosafety Unit is responsible for matters related to biosafety and biotechnology under the Convention and the Cartagena Protocol. The unit promotes and supports the ratification of the Cartagena Protocol on Biosafety and the Nagoya–Kuala Lumpur Supplementary Protocol on Liability and Redress. The Biosafety Unit also organizes and prepares for meetings under the Cartagena Protocol on Biosafety, Convention on Biological Diversity and the Nagoya–Kuala Lumpur supplementary Protocol on Liability and Redress on issues related to biosafety and biotechnology. The Unit supports Parties in their implementation efforts by facilitating the generation, sharing and exchange of information on issues related to biosafety and biotechnology, by providing relevant legal and capacity-building support, and by managing the Biosafety Clearing-House. In addition, the Unit manages synthetic biology technical issues under the Convention in a coordinated manner with the Protocol.

#### Table 15. Outputs and sub-outputs developed by the Office of the Executive Secretary

Outputs and sub-outputs per outcome

Outputs planned for the biennium in pursuit of outcome (1): Through the Convention and its Protocols, the international community increasingly converges on common and integrated gender-sensitive approaches to biodiversity conservation, sustainable use and the fair and equitable sharing of the benefits arising out of the utilization of genetic resources

1.1 Evidence based analysis/technical work informs decision-making processes of Parties during major meetings

1.1.1 Technical guidance documents prepared (including studies)

1.1.2 Technical meetings held (AHTEGs, IACs, IAGs, etc.)

1.1.3 Draft decisions and recommendations prepared

1. 2 Major meetings organized and delivered with the full and effective participation of Parties, IPLCs and other stakeholders

1.2.1 COP-16, MOP-11 (Cartagena), MOP-5 (Nagoya)

1. 3 Integration of biodiversity targets in the policies, strategies and workplans of the United Nations system and other international organizations promoted

1.3.2 Joint work programmes/guidelines/strategies developed with other MEAs and international organizations

Outputs planned for the biennium in pursuit of outcome (2): Through the application of the global biodiversity framework, national implementation of the Convention and its Protocols for improved status of biodiversity is enhanced

2.1 Resource mobilization is promoted to support implementation

2.1.1 Existing partnerships are further strengthened, and new partnerships are developed

2.2 Institutional and technical capacities of governments and stakeholders are strengthened to implement the Convention and its Protocols

2.2.1 Capacity development programmes/initiatives implemented (Protocols)

2.3 Knowledge management and information exchange enhanced to support the implementation of the Convention and its Protocols

2.3.2 The Biosafety and ABS clearing-houses, tools are well maintained, further developed and made available and interoperable with several partner platforms.

2.4 Partnerships are mobilized at the global and regional level to support implementation by Parties at the national level

2.4.1 Regional webinars delivered to United Nations Resident Coordinator system

Outputs planned for the biennium in pursuit of outcome (3): Awareness and action to conserve, sustainably use, and share the benefits of biodiversity is enhanced at all levels and across sectors of society

3.2 Biodiversity is promoted to support the programme of work of the Secretariat and the post-2020 GBF

3.2.1 Stakeholder responsive communication strategy

3.2.2 Strong presence at key high-level political events including messaging and representation at the G7, G20, HLPF and UNGA biodiversity related events.

3.2.3 Communication campaigns promoted and delivered with partners

3.2.4 Stakeholder groups engaged and mobilized to promote biodiversity

3.2.5 Subnational and non-State actor commitments and actions increasing through the Sharm el-Sheikh to Kunming Action Agenda for Nature and People

3.3 Outreach and awareness raising campaigns implemented for the Cartagena, Kuala-Lumpur supplementary Protocol and Nagoya Protocol to encourage ratification

Outputs planned for the biennium in pursuit of outcome (4): Regular monitoring, review and assessment contribute to informed planning and decision-making at all levels, resulting in progressive enhancement of the implementation of GBF, the Convention, and its Protocols

(4.3) Status of implementation assessed, and results made available to inform decision-making (for the Convention and the Protocols)

4.3.3 Relevant assessments and stock-takes including means of implementation and financial resources prepared and/or coordinated (Protocols)

4.3.4 Compliance committee meetings organized, and issues reviewed (Protocols)

4.3.5 Online tools, including decision-tracking tool fully developed, made available and regularly updated and maintained

- Post resources amounting to $4,827,800 would provide for the continuation of 15.5 posts (2 P-5, 1 P-4, 4.5 P-3, 2 P-2 and 6 GS) as well as 2 new posts at the P-4 and P-3 levels respectively.  These are described below.

- Given the ongoing work related to digital sequence information on genetic resources (DSI) and related emerging scientific and technical issues, such as synthetic biology, the Secretariat proposes the conversion of a Programme Officer post at the P-4 level currently funded by extrabudgetary resources to core budget funding. It should be noted that the issue of DSI emerged as a cross-cutting issue at COP-13 and NP-MOP-2. The post would ensure that the Secretariat can adequately carry out the work required on this topic in the coming years as well as follow other scientific and technological developments which may have an impact on the implementation of the Convention and its Protocols. It is recalled that in decisions XIII/16 and NP-2/14 respectively, Parties agreed to consider any potential implications of DSI on genetic resources for the objectives of the Convention and the objective of the Nagoya Protocol at COP-14 and NP-MOP-3.  The programme officer would be responsible for the implementation of this new area of work, and also cover work on taxonomy, follow developments on related issues in other international forums, collaborate with relevant organizations and liaise with the scientific and business community to ensure that developments under the Convention and its Protocols duly take into consideration the needs of Governments as well as stakeholders for the benefit of the international community.

- There is also an urgent need to regularize the Biosafety Clearing House (BCH) post (P-3) currently funded from extrabudgetary resources. The BCH is a mandatory mechanism established under the Cartagena Protocol on Biosafety and the lack of a core funded position has compromised the Secretariat’s ability to deliver on key outcomes relating to the migration of the BCH and the alignment with the clearing-house mechanism and the ABS Clearing-House. The post is critical for managing the online platforms as a means of engaging Parties and other stakeholders in the development of technical documents for biosafety and synthetic biology discussions. Furthermore, COP-15 and CP-MOP-10 are expected to adopt decisions that include specific elements that are dependent on a fully staffed and operational BCH, complete with online platforms for engagement and consolidation of the programmes of work for synthetic biology, risk assessment and risk management, socio-economic considerations and detection and identification of living modified organisms (LMOs). The integration of relevant issues and processes of the Convention and its Protocols continues to be a strategic priority for the Parties and the Secretariat. This was further emphasized in decision CP-9/7, where the Conference of the Parties serving as the meeting of the Parties to the Cartagena Protocol on Biosafety adopted a comprehensive process for the development of a post-2020 implementation plan for the Protocol that is anchored in and complementary to the post-2020 GBF As a result, it is expected that the BCH will play an important role in the enhanced planning, monitoring, reporting and review mechanisms and will require the requisite capacity and capability to be included within the staff allocations for the Cartagena Protocol on Biosafety. A Cartagena Protocol information and monitoring function is therefore required to address these additional elements and align with the Convention processes using the Biosafety Clearing-House as a primary tool for managing information and reporting.

#### Table 16. Resource allocations:  ABS and Biosafety Protocols

|  | Resources (thousands of United States dollars) |  |  |  |  | Posts |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 | 2023-2024 ZRG | 2023-2024 ZNG |  |  | 2019-20 |  | 2021-22 |  | 2023-24 |
| Core budget |  |  |  |  |  |  |  |  |  |  |
| Post | 4,255.3 | 4,827.8 | 4,178.1 |  |  | 15.5 |  | 15.5 |  | 17.5 |
| Non-post | 0.0 | 100.0 | 100.0 | a/ |  |  |  |  |  |  |
| Subtotal | 4,255.3 | 4,927.8 | 4,278.1 |  |  | 15.5 |  | 15.5 |  | 17.5 |
| PSC (OTA) |  |  |  |  |  |  |  |  |  |  |
| XB |  |  |  |  |  |  |  | 2 | b/ |  |
| Total | 4,255.3 | 4,927.8 | 4,278.1 |  |  | 15.5 |  | 17.5 |  | 17.5 |
| a/ includes travel ($100,) |  |  |  |  |  |  |  |  |  |  |
| b/ represents 1 P-4 for DSI and 1 P-3 for BCH |  |  |  |  |  |  |  |  |  |  |

- Non-post resources provide for travel of staff ($100,000) considering that in future some travels will be replaced by virtual and hybrid engagement as much as possible. Thus, cost estimate is based on actual expenditure pattern for the biennium 2019-2020.

- Under the Zero-Nominal Growth Scenario (0 per cent increase in nominal terms), maintaining the programme budget at the 2023-2024 level in nominal terms, the Secretariat would propose the continuation of all existing posts and an amount of $100,000 under non-post to provide for travel of staff to support the implementation of the mandates under the programme.

### 2. Science, Society and Sustainable Futures Division

Resource allocation (core budget): $6,761,300 (scenario 1)

- The Science, Society and Sustainable Futures Division (SSSF) serves as the Secretary of the Subsidiary Body on Scientific, Technical and Technological Advice (SBSTTA) of the Convention on Biological Diversity and provides scientific and technical support to the Open-ended Working Group on the Post-2020 Global Biodiversity Framework.  The Science, Society and Sustainable Futures Division comprises of three units:

- Biodiversity Science, Policy and Governance Unit covers the following programmes:

    - Area-based conservation;

    - Forest, land use and ecosystems restoration;

    - Marine, coastal and islands biodiversity;

    - Climate change and the ecosystem approach;

    - Agriculture and inland waters;

    - Global Taxonomy Initiative and invasive alien species;

    - Biodiversity and health.

- The Biodiversity Science, Policy and Governance Unit provides support to Parties, stakeholders, and partner organizations in advancing scientific understanding and knowledge on the status and trends of biodiversity and ecosystems and in enhancing scientific and technical tools and guidelines for the conservation and sustainable use of biodiversity in support of evidence-based decision-making. It is responsible for the coordination of scientific work in areas that include Targets 5 through 13, 17 and 19 of the Strategic Plan for Biodiversity 2011-2020, and the anticipated successor targets of the new framework to be adopted at COP-15, including through support for implementing the following thematic and cross-cutting issues: marine and coastal biodiversity, forest biodiversity, dry and sub-humid lands biodiversity, mountain biodiversity, agricultural biodiversity, inland waters biodiversity, island biodiversity; the ecosystem approach, impact assessments, ecosystem restoration; climate change and biological diversity, Global Strategy for Plant Conservation; Global Taxonomy Initiative, protected areas and other area-based conservation measures, sustainable use and sustainable wildlife management, technical and scientific cooperation, new and emerging issues among others in line with Articles 7, 8, 9, 10, 12, 14, 18 and 25 of the Convention.

- The Biodiversity Economy Transformation and Innovation Unit covers the following programmes:

- Biodiversity and sustainable development;

- Business, finance and biodiversity;

- Mainstreaming of biodiversity.

- The Biodiversity Economics, Transformation and Innovation Unit provides programmatic, technical and policy analysis to facilitate decision-making and implementation support on issues related to biodiversity mainstreaming across economic sectors and levels of governance, leading on economics and trade, finance and resource mobilization, business engagement, engagement with the financial sector, biodiversity for development, addressing subsidies harmful to biodiversity, and poverty eradication, as part of an integrated approach foreseen in Article 6 (b) of the Convention. This Unit cooperates with relevant partners to promote the development, assessment and implementation of tools, measures, and mechanisms for integrating the values of biodiversity into public and private sector plans, policies and programmes.

- The People and Biodiversity Unit covers the following programmes:

- Indigenous people, local communities and traditional knowledge;

- Nature and culture;

- Gender.

- The People and Biodiversity Unit provides scientific, technical and policy analysis to facilitate decision-making and implementation support for issues related to indigenous peoples, local communities and traditional knowledge (Article 8(j) and related provisions), culture and biological diversity (Nature and culture), gender mainstreaming, human dimension of health and biodiversity linkages, and human right-based approaches for biodiversity conservation and sustainable use. The Unit takes the overall lead to facilitate and service meetings related to Article 8(j) and other provisions of the Convention pertaining to indigenous peoples and local communities and supports servicing meetings of the Subsidiary Body on Scientific, Technical and Technological Advice, the Subsidiary Body of Implementation and the Conference of the Parties on issues under its responsibility. The Unit’s key role is to strengthen the social pillar of the Convention and respond to requests from Parties to enhance and communicate the relevance of biodiversity for people.

- The Science, Society and Sustainable Futures Division contributes towards all four substantive outcomes of the Secretariat. The following table presents the outputs and sub-outputs for which the division is directly responsible.

#### Table 17. Outputs and sub-outputs developed by the Science, Society and Sustainable Futures Division

Outputs and sub-outputs per outcome

Outputs planned for the biennium in pursuit of outcome (1): Through the Convention and its Protocols, the international community increasingly converges on common and integrated gender-sensitive approaches to biodiversity conservation and sustainable use

1.1 Evidence based analysis/technical work informs decision-making processes of Parties during major meetings

1.1.1 Technical guidance documents prepared (including studies)

1.1.2 Technical meetings held (AHTEGs, IACs, IAGs, etc.)

1.1.3 Draft decisions and recommendations prepared

1. 2 Major meetings organised and delivered with the full and effective participation of Parties, IPLCs and other stakeholders

1.2.1 SBSSTA-25 and 26, WG8J-12

1. 3 Integration of biodiversity targets in the policies, strategies and workplans of the United Nations system and other international organizations promoted

1.3.1 Information exchanges fostered between the CBD its Protocols, MEAs, other UN Organizations and international organizations to inform decisions and enhance policy coherence

1.3.2. Joint work programmes/guidelines/strategies developed with other MEAs and international organizations

Outputs planned for the biennium in pursuit of outcome (2): Through the application of GBF, national implementation of the Convention and its Protocols for improved status of biodiversity is enhanced

2.1 Resource mobilization is promoted to support implementation

2.1.1 Existing partnerships are further strengthened, and new partnerships are developed

2.2 Institutional and technical capacities of governments and stakeholders are strengthened to implement the Convention and its Protocols

2.2.2 Programme-specific and issue-specific capacity development programmes/initiatives implemented

2.2.3 Scientific and technical cooperation activities promoted and facilitated

2.4 Partnerships are mobilized at the global and regional level to support implementation by Parties at the national level

2.5 Implementation of GBF is facilitated through external partners

Outputs planned for the biennium in pursuit of outcome (4): Regular monitoring, review and assessment contribute to informed planning and decision-making at all levels, resulting in progressive enhancement of the implementation of GBF, the Convention, and its Protocols

4.3 Status of implementation assessed, and results made available to inform decision-making (for convention and protocols)

4.3.1 Assessments and stock-takes implemented and/or coordinated

4.4 Status of biodiversity assessed, and results made available to inform decision-making

4.4.1 Status of biodiversity monitored and evaluated based on relevant information, including identified indicators

- Post resources amounting to $6,661,300 would provide for the continuation of 18.5 posts (1 D-1, 3 P-5, 4.5 P-4, 2 P-3, 2 P-2 and 6 GS) as well as the conversion of two P-3 posts funded from extra-budgetary funds.  These are described below.

- The Secretariat proposes the conversion of a Programme Officer post at the P-3 level on Biodiversity and Business, currently funded by extrabudgetary resources to core budget funding. Since the adoption of the first decision on private sector engagement by the Conference of the Parties at its eight meeting, in 2006 (decision VIII/17), significant progress has been made in engaging businesses for achieving the objectives of the Convention, including: the growth of national or regional partnerships on business and biodiversity and the establishment of the Global Partnership as a network of networks, with currently almost 25 initiatives; the regular holding of the Global Business and Biodiversity Forum back-to-back with the meetings of the Conference of the Parties; and the building of a collaborative global network of international partner organizations and initiatives which was instrumental for the development of various outreach and guidance products, such as on business reporting. Work on business engagement is therefore bound to continue and its ongoing importance is likely to further increase, also in the context on increased engagement of the financial sector (which includes private businesses). It is therefore critical to secure sustainability of ongoing work activities through the conversion of this post to core budget funding.

- Similarly, further strengthening of staff support, which is currently managed as temporary post at P-3 level, is needed on addressing One Health approach through programme-wide level across all the relevant programme of works and cross-cutting issues based on strengthening social linkages with various sectors, global partners, civil society groups, Multi-Partnership Funds, and other donors, which will complement the scientific and technical approaches, to be undertaken by the merged post of P-4 on invasive alien species and health. In order to effectively seize the opportunities for partnerships and financial investment on this issue, the Secretariat would like to propose that the current temporary post be converted to core-budgeted post at P-3 level.

- In view of increasing need for mainstreaming various economic sectors for the implementation of post-2020 GBF, the Secretariat would like to propose that work in this area, which is currently covered by 50 per cent of a P-4 post, be fully resourced through the provision of a post of biodiversity mainstreaming Programme Officer (P-4). Work on integrating biodiversity considerations within and across economic sectors (“biodiversity mainstreaming”) has intensified considerably since the adoption of landmark decision XIII/3, bundling earlier work on economic sectors under thematic programmes of work and cross-sectorial work on incentives and on sustainable development. With decision 14/3 and its focus on key sectors not covered by existing programmes of work, the decision by the Conference of the Parties to establish a long-term strategic approach to mainstreaming, and the follow-up work already foreseen in the draft decision recommended by the Subsidiary Body on Implementation at its third meeting, the mainstreaming work is likely to continue and further intensify and requires, therefore, adequate staffing capacity of a full-time programme officer at P-4 level.

#### Table 18. Resource allocations:  Science, Society and Sustainable Futures Division

|  | Resources (thousands of United States dollars) |  |  |  |  | Posts |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 | 2023-2024 ZRG | 2023-2024 ZNG |  | 2019-20 |  |  | 2021-22 |  | 2023-24 |
| Core budget |  |  |  |  |  |  |  |  |  |  |
| Post | 5,842.1 | 6,661.3 | 5,718.7 |  | 18.5 |  |  | 18.5 |  | 21 |
| Non-post |  | 100.0 | 100.0 | a/ |  |  |  |  |  |  |
| Subtotal | 5,842.1 | 6,761.3 | 5,818.7 |  | 18.5 |  |  | 18.5 |  | 21 |
| PSC (OTA) |  |  |  |  | 1 |  | b/ | 1 | b/ | 1 |
| XB |  |  |  |  | 2 |  | c/ | 2 | c/ |  |
| Total | 5,842.1 | 6,761.3 | 5,818.7 |  | 21.5 |  |  | 21.5 |  | 22 |
| a/ includes travel ($100,000). |  |  |  |  |  |  |  |  |  |  |
| b/ represents 1 G-6 Programme Assistant in the People and Biodiversity Unit |  |  |  |  |  |  |  |  |  |  |
| c/ represents 2 P-3 posts funded by the EU |  |  |  |  |  |  |  |  |  |  |

- Non-post resources provide for travel of staff ($100,000) considering that in future some travels will be replaced by virtual and hybrid engagement as much as possible. Thus, cost estimate is based on actual expenditure pattern for the biennium 2019-2020.

- Under the zero nominal growth Scenario (0 per cent increase in nominal terms), maintaining the programme budget at the 2023-2024 level in real terms and in nominal terms, the Secretariat would propose the continuation of all existing posts and an amount of $100,000 under non-post to provide for travel of staff to support the implementation of the mandates under the programme.

- Implementation Support Division

Resource allocation (core budget): $7,048,800 (scenario 1)

- The Implementation Support Division provides support for the implementation, reporting and review of the Convention and its Protocols through (a) coordination of the implementation, monitoring and evaluation of capacity-building and development activities across the Secretariat; (b) supporting the clearing-house mechanism and advancing knowledge management; (c) facilitating the integration of the biodiversity agenda into relevant international intergovernmental processes and developing strategic partnerships; (d) facilitating the servicing of the meetings of the Subsidiary Body on Implementation and other relevant intergovernmental processes; and (e) providing inputs to Secretariat-wide integrated processes to support the implementation of the Convention and its Protocols.  The Head of Division serves as the Secretary for SBI and until recently also as the Secretary of the Open-ended Working Group on the Post-2020 Global Biodiversity Framework.

- The Implementation Support Division is comprised of the following three units:

  - The Monitoring, Review and Reporting Unit is responsible for supporting Parties in tracking progress towards objectives agreed under the Convention and in reflecting these objectives in biodiversity planning, review and reporting. The development of a holistic review system covering the Convention and its Protocol is one of the main goals of the Unit. This includes national reporting as an element of the review system;

  - The Stakeholder Engagement and Cooperation Unit is responsible for the engagement of major stakeholder groups in the work and processes of the Convention, and for cooperation with other international organizations and conventions, which are key partners in implementing the objectives of the Convention and its Protocols. Among stakeholder groups, it has particular responsibility for youth and for subnational and local authorities. The Unit facilitates the integration of the biodiversity agenda into relevant intergovernmental processes and develops and maintains partnerships to support implementation of the Convention and its Protocols. The Unit is also responsible for matters related to the financial mechanism of the Convention and its Protocols, and for cooperation with the Global Environment Facility.

  - The Capacity-building and Knowledge Management Unit is responsible for coordinating and facilitating capacity-building and development, technical and scientific cooperation and knowledge management programmes as well as developing and managing the clearing-house mechanism platforms and other information technology systems and digital solutions to support implementation of the Convention and its Protocols. It comprises the following programmes:

      - Capacity-building and Development;

      - Technical and Scientific Cooperation programme (including the Bio-Bridge Initiative);

      - Knowledge Management and the Clearing-house mechanism;

      - Information Technology and Digital Governance.

- The Implementation Support Division contributes towards all four substantive outcomes of the Secretariat. The following table presents the outputs and sub-outputs for which the division is directly responsible.

#### Table 19. Outputs and sub-outputs of the Implementation Support Division

Outputs and sub-outputs per outcome

Outputs planned for the biennium in pursuit of outcome (1): Through the Convention and its Protocols, the international community increasingly converges on common and integrated gender-sensitive approaches to biodiversity conservation, sustainable use and the fair and equitable sharing of the benefits arising out of the utilization of genetic resources

1.1 Evidence based analysis/technical work informs decision-making processes of Parties during major meetings

1.1.1 Technical guidance documents prepared (including studies)

1.1.2 Technical meetings held (AHTEGs, IACs, IAGs, etc.)

1.1.3 Draft decisions and recommendations prepared

1. 2 Major meetings organized and delivered with the full and effective participation of Parties, IPLCs and other stakeholders

1.2 SBI-4, SBI open-ended forum

1. 3 Integration of biodiversity targets in the policies, strategies and workplans of the United Nations system and other international organizations promoted

1.3.1 Information exchanges fostered between the CBD its Protocols, MEAs, other UN Organizations and international organizations to inform decisions and enhance policy coherence

1.3.2. Joint work programmes/guidelines/strategies developed with other MEAs and international organizations

Outputs planned for the biennium in pursuit of outcome (2): Through the application of GBF, national implementation of the Convention and its Protocols for improved status of biodiversity is enhanced

2.1 Resource mobilization is promoted to support implementation

2.1.1 Guidance is provided to a growing number of partners to mobilize resources to support national implementation

2.1.2 Existing partnerships are further strengthened, and new partnerships are developed

2.2 Institutional and technical capacities of Governments and stakeholders are strengthened to implement the Convention and its Protocols

2.2.1 Support mechanisms and tools identified, implemented and promoted

2.2.2 Capacity development programmes/initiatives implemented

2.2.3 Scientific cooperation activities promoted and facilitated

2. 3 Knowledge management and information exchange enhanced to support the implementation of the Convention and its Protocols

2.3.1 Data and information is well-structured, managed and exchanged

2.3.2 The clearing houses, websites, portals, and other Information Technology (IT) tools are well maintained, further developed, and made available and interoperable with several partner platforms.

2.4 Partnerships are mobilized at the global and regional level to support implementation by Parties at the national level

2.4.1 Implementation of GBF is facilitated through external partnerships

Outputs planned for the biennium in pursuit of outcome (4): Regular monitoring, review and assessment contribute to informed planning and decision-making at all levels, resulting in progressive enhancement of the implementation of GBF, the Convention, and its Protocols

4.1 Enhanced national planning and reporting facilitated

4.1.1 Support for national planning facilitated and gender-sensitive guidance provided 4.1.2 Support for national reporting facilitated 4.1.3 Increased synergies in reporting to the biodiversity-related Conventions, the Rio conventions and SDGs

4.2 Facilitated party by party review of implementation of the Convention and results disseminated to enhance capacities and inform decision-making

4.2.1 SBI open-ended forum established

4.2.2 Evidence-based Voluntary Peer-Review process facilitated for participating Parties and outcomes fed into SBI/COP

4.3 Status of implementation assessed, and results made available to inform decision-making (for convention and protocols)

4.3.1 Enhanced tools and capacity for high-quality, near real-time monitoring of the global biodiversity framework goals and targets at the national and global level.

4.3.2 High-quality, up to date, actionable analysis is available to contribute to global review and decision-making

4.3.3 Assessments and stock-takes implemented and/or coordinated

4.4. Status of biodiversity monitoring, and results made available to inform decision-making

4.4.1 Status of biodiversity monitored and evaluated based on relevant information, including identified indicators

- Post resources amounting to $7,006,400 would provide for the continuation of 23 posts (1 D-1, 3 P-5, 4.5 P-4, 3.5 P-3, 4 P-2 and 7 GS).  Currently, the Division also has two positions (1 P-4, 1 GS) funded from extra-budgetary funds.

- The Secretariat also proposes the creation of two posts to strengthen work in support of planning, reporting, monitoring and review of implementation. In recent years, work to support the development and updating of national biodiversity strategies and action plans has been supported through staff in the Japan Biodiversity Fund. JBF staff have also supported the voluntary peer review process and the development of proposals for country-led review processes. It is proposed that these gaps be funded through a permanent position at P4 level, especially since this area of work is expected to expand in light of the post 2020 global biodiversity framework it is expected that work in this area will further expand. It is also proposed to create a post at P3 level to advance work on indicators and scientific assessment of progress in order to further support Parties’ work in these areas.

#### Table 20. Resource allocations : Implementation Support Division

|  | Resources (thousands of United States dollars) |  |  |  |  |  |  | Posts |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 |  | 2023-2024 ZRG | 2023-2024 ZNG |  | 2019-20 |  |  |  | 2021-22 |  | 2023-24 |
| Core budget |  |  |  |  |  |  |  |  |  |  |  |  |
| Post | 7,015.2 |  | 6,818.8 | 6,818.8 |  | 23 |  |  |  | 23 |  | 23.5 |
| Non-post | 1,440.0 | a/ | 230.0 | 230.0 | b/ |  |  |  |  |  |  |  |
| Subtotal | 8,455.2 |  | 7,048.8 | 7,048.8 |  | 23 |  |  |  | 23 |  | 23.5 |
| PSC (OTA) |  |  |  |  |  |  |  |  |  |  |  |  |
| XB |  |  |  |  |  | 2 |  |  | c/ | 3 | c/ | 2 |
| Total | 8,455.2 |  | 7,048.8 | 7,048.8 |  | 25 |  |  |  | 26 |  | 25.5 |
| a/ includes extraordinary meetings on the post-2020 GBF and translation of CHM website |  |  |  |  |  |  |  |  |  |  |  |  |
| b/ includes travel ($100,000) and translation of CHM website ($130,000) and 2 reports ($250,000) |  |  |  |  |  |  |  |  |  |  |  |  |

- Non-post resources provide for travel of staff ($100,000) considering that in future some travels will be replaced by virtual and hybrid engagement as much as possible. This cost estimate is based on actual expenditure pattern for the biennium 2019-2020.  In addition, provision of $130,000 is made for the translation of the CHM website.

## D. Administrative support

Resource allocation (core budget): $6,028,600 (scenario 1)

- Programme support for the Secretariat is vested with the Administration, Finance and Commercial Services (AFC) Division, which provides fund management, financial services, and logistical and other backstopping support in addition to efficient administrative and human resources support for the Secretariat of the Convention and its Protocols, within the rules and regulations of the United Nations and under the guidance of Parties.

- The Division comprises the following units:

  - The Budget and Finance Unit, which ensures compliance with the UN Financial Regulations and Rules and financial directives issued by UNON and UN Controller in the expenditure and recording of expenditure of the funds administered by the Secretariat. It assists with the preparation of the biennium budgets for the trust funds managed by the Secretariat to the Conference of the Parties, monitors the Secretariat resources and their effective use in accordance with the approved programme, including the staff and participants travel arrangements. The unit also ensures the accounts of the Secretariat comply with the International Public Sector Accounting Standard (IPSAS) and reflected accurately in Umoja;

  - The Human Resources and Administration Unit provides administrative and personnel support to Secretariat staff through the interpretation and implementation of staff rules and regulations, the necessary actions in Umoja and Inspira and the provision of guidance to staff regarding all human resources issues, including training;

  - The Commercial Services Team ensures office management and provision and maintenance of services for the operation of the Secretariat (procurement, building management, etc.);

  - The IT Client Service Team provides IT infrastructure, services, information security and support to the Secretariat staff based on priorities agreed by the management in line with UN rules and regulations.

#### Table 21. 		Resource allocations: programme support

|  | Resources (thousands of United States dollars) |  |  |  |  |  |  | Posts |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2019-2020 |  | 2023-2024 ZRG | 2023-2024 ZNG |  |  | 2019-20 |  |  | 2021-22 |  | 2023-24 |  |  |
| Core budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Post | 1,664.8 |  | 1,316.7 | 947.9 |  |  | 7 |  |  | 4 |  | 5 |  |  |
| Non-post | 4,314.9 |  | 4,711.9 | 4,711.9 |  |  |  |  |  |  |  |  |  |  |
| Subtotal | 5,979.7 |  | 6,028.6 | 5,659.8 |  |  | 7 |  |  | 4 |  | 5 |  |  |
| PSC (OTA) |  |  |  |  |  |  | 20 |  |  | 16 |  | 16 |  |  |
| XB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total | 5,979.7 |  | 6,028.6 | 5,659.8 |  |  | 27 |  |  | 20 |  |  | 21 |  |  |  |

- Post resources in the Administration, Finance and Commercial Services (AFC) Division, is primarily funded through programme support costs (the 13 per cent overhead costs levied ono the core and all voluntary contributions to the Secretariat), which provides for the backstopping support for the Secretariat. It is anticipated that the current staffing level of a total of 16 posts (1 P-5 post, 2 P-4, 1 P-3, 12 GS) will be maintained for the biennium 2023-2024.  In addition, an amount of $1,316,700 is requested for the continuation of 4 core funded posts (2 P-3 and 2 GS) and one new post at the P-4 level.  The shortfall in the OTA that the Secretariat has incurred for more than the past than four years has highlighted the need to have a minimum number of posts in the Division funded from the core budget.  This view was also shared by the Board of Auditors (BOA) in their recent audit of the Secretariat, specifically that the funding gap reflects inadequate funding for operational activities provided by the Administration Division, and that it may have an impact on the continuity and efficiency of work provided by the Division, especially taking into consideration that more than 80 per cent of posts are funded through programme support costs and the recruitment was frozen as at 31 December 2021. The Secretariat is therefore proposing that the Administrative Officer post (P-4) be transferred to the core budget since it is considered an essential function.

- Non-post resources amounting to 4,711,900 would provide temporary assistance/overtime ($200,000), training of staff ($10,000), rent and associated costs ($2,918,700), general operating expenses ($1,453,200) and information technology ($130,000) to support the implementation of the mandates under the programme.  Given that considerable investment has been done and will be done to upgrade the information technology infrastructure in the Secretariat, it was decided to separate out the specific requirements for transparency purposes.  During the period, it will be necessary to replace the Secretariat’s network switches as well as cover the costs of Microsoft and Umoja licences.

# V. 	DRAFT DECISIONS

- This document provides proposals for the integrated programme of work and budget for the Convention and protocols for the 2023-4 biennium, with two scenarios for the core budget as follows:

| Zero-real Growth Scenario for 2023-2024 |  | USD 40,443.8 |
| --- | --- | --- |
| Zero-nominal Growth Scenario for 2023-2024 |  | USD 37,181.2 |

- As noted in paragraph 9, the draft decisions for the consideration of the Conference of the Parties are provided in the compilation of draft decisions (CBD/COP/15/2).

- The draft decisions for the respective meetings of the Parties to the Cartagena and Nagoya Protocols are provided in the respective compilations (CBD/CP/MOP/10/1/Add.5, and CBD/NP/MOP/4/1/Add.5).

# Annex I

# ORGANIZATIONAL STRUCTURE AND POST DISTRIBUTION FOR THE BIENNIUM 2023-2024

Annex II

SUMMARY OF FOLLOW-UP ACTION TAKEN TO IMPLEMENT RELEVANT RECOMMENDATIONS OF THE OVERSIGHT BODIES

|  | Action taken to implement the recommendation |
| --- | --- |
| Board of Auditors A/75/5/Add.7 Chapter II |  |
| The Board recommends that UNEP establish the proper liaison between its headquarters and the Executive Secretary of the Convention on Biological Diversity and its Protocols to agree on the procedures and responsibilities that each entity shall assume regarding the provision of secretariat services to the Conference of the Parties to the Convention on Biological Diversity, including the aspects related to non-administrative functions (para 170). The Board recommends that UNEP liaise with the Executive Secretary of the Convention on Biological Diversity to propose to the Conferences of Parties to the Convention on Biological Diversity and its Protocols the adoption of a memorandum of understanding. If agreed, this instrument shall include the arrangements for the provision of secretariat functions by UNEP, aiming to establish a regulatory framework that sets out clear responsibilities, transparency, guidance and accountability among the Parties and Member States (para 171). | UNEP notes that the roles and responsibilities are set out in the Revised Administrative Arrangements between UNEP and Convention of Biological Diversity (Annex to decision X/45). UNEP and the Secretariat plan to develop the service level agreement once COP 15 part 2 has taken place. UNEP notes that the roles and responsibilities are set out in the Revised Administrative Arrangements between UNEP and Convention of Biological Diversity (Annex to decision X/45). UNEP and the Secretariat plan to develop the memorandum of understanding once COP 15 part 2 has taken place. |
| The Board recommends to UNEP that the secretariat of the Convention on Biological Diversity issue the report on the administration of the Convention on Biological Diversity in line with the activities disclosed in its programme of work, presenting those activities in accordance with its budget and its execution (para 185). | The format of the bi-annual Secretariat report on the administration of the Convention on Biological Diversity on has been changed to comply with this audit recommendation. The Secretariat has developed a Results-Based Budgeting (RBB) Framework, which is presently used for the preparation of the 2023-24 budget document to be submitted to COP15, part 2. It is expected that the recommendation will be closed once the RBB has been presented to the COP. |
| The Board recommends that UNEP assist and coordinate with the secretariat of the Convention on Biological Diversity to standardize the secretariat’s reporting processes, with the aim of including indicators, means of verification, outcomes and assessment for each activity presented in the programme of work (para 186). | The Secretariat of the Convention of Biological Diversity notes that it reports to COP in accordance with Article 24 of the Convention and receives its mandate on programmatic and reporting matters from the COP. It is expected that the recommendation will be closed once the RBB has been presented to the COP. |
| The Board recommends that UNEP assess and correct the grants posted in its BHL and BXL trust funds (para 199). | The Board of Auditors noted that the Secretariat was continue analysing and reconciling the grants from BHL and BXL trust funds. The Secretariat will continue with the analysis and reconciliation and the necessary action will be taken to ensure that correction adjustments are done, and all grants closed by 31 December 2022 following a decision by COP on the use of the fund balances. |
| The Board recommends that UNEP coordinate with the Secretariat of the Convention on Biological Diversity to take the measures needed to comply with the preparation of a complete long-term strategic framework for capacity-building beyond 2020, in order for it to be presented in conformity with the requirements of the Conference of the Parties (para 209). The Board recommends that UNEP assist and liaise with the secretariat of the Convention on Biological Diversity to coordinate with the Conference of the Parties to the Convention to adjust the programme of work and budget submission, with the aim of evaluating and implementing a more realistic workplan for the secretariat in accordance with available resources (para 219). The Board recommends that UNEP assist and liaise with the secretariat of the Convention on Biological Diversity to coordinate with the Conference of the Parties to include the voluntary contributions in the budget submission in a way that reflects the necessary resources to implement the Conference of the Parties’ decisions (para 220). | The Secretariat for the Convention on Biological Diversity and UNEP’s Law Division will take measures needed to ensure conformity with Conference of the Parties’ decisions. The long-term strategic framework for capacity-building and development to support implementation of the post-2020 global biodiversity framework as approved by SBI 3 (Annex 1 of document CBD/SBI/3/L.13) is expected to be adopted during the second part of COP15 in the third quarter of 2022. Recommendation will be closed once the long-term strategy has been completed at COP15-2. The format of the bi-annual Secretariat for the Convention on Biological Diversity report on the administration of the Convention on Biological Diversity has been changed to comply with this audit recommendation. The Convention on Biological Diversity has prepared an information document on the alignment needed between resources and programme of work. As the programme of work and budget format is in use already UNEP has requested the closure of this recommendation. The SCBD programme budget for the biennium 2023-24, uses the UNEP Programme Budget format for 2018-19 as requested by the Parties in COP decision 14/37. This format requires that the voluntary contributions are included in the budget submission in a way that reflects the necessary resources to implement the Conference of the Parties’ decisions. As the programme of work and budget format is in use already UNEP considers requested the closure of this recommendation. |
| The Board recommends that UNEP assist and liaise with the secretariat of the Convention on Biological Diversity to coordinate with the Conference of the Parties to the Convention in order to agree on the implementation of a more effective resource mobilization mechanism for the secretariat (para 221). The Board recommends that UNEP ensure that the contracts contain all the information necessary to identify the department that signs the contract and the consultants and individual contractors hired at the Secretariat of the Convention on Biological Diversity (para 256). | UNEP has received clarification that it does not have a direct coordination role regarding the resource mobilization mechanism for the secretariat, a, therefore, this recommendation is not implementable, and closure has been requested. Secretariat has worked with the Umoja team to address this issue and the matter has been resolved. This recommendation remains under implementation as UNEP is required establish a proper coordination mechanism regarding Umoja roles to address the requirements for this recommendation and provide updates of its implementation in future audits. However, due to competing constraints the UMOJA Team has not been able to give this task sufficient priority, and its implementation is therefore beyond the control of Secretariat or UNEP. |

# Annex III

# Contributions to the Trust Fund for the Convention on Biological Diversity and its Protocols for 2023

## A.	Trust Fund for the Convention on Biological Diversity

| Member Country | Scale of assessment 2022-2024 | Scale with 22% ceiling, no LDC paying more than 0.01 per cent |  | Zero Real Growth |  |  | Zero Nominal Growth |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |
| Afghanistan | 0.006 | 0.008 |  | 1,006 | 1,000 |  | 912 | 917 |
| Albania | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Algeria | 0.109 | 0.136 |  | 18,284 | 18,158 |  | 16,574 | 16,667 |
| Andorra | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Angola | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Antigua and Barbuda | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Argentina | 0.719 | 0.899 |  | 120,609 | 119,776 |  | 109,329 | 109,943 |
| Armenia | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,064 | 1,070 |
| Australia | 2.111 | 2.639 |  | 354,111 | 351,665 |  | 320,993 | 322,795 |
| Austria | 0.679 | 0.849 |  | 113,899 | 113,113 |  | 103,247 | 103,827 |
| Azerbaijan | 0.030 | 0.038 |  | 5,032 | 4,998 |  | 4,562 | 4,587 |
| Bahamas | 0.019 | 0.024 |  | 3,187 | 3,165 |  | 2,889 | 2,905 |
| Bahrain | 0.054 | 0.068 |  | 9,058 | 8,996 |  | 8,211 | 8,257 |
| Bangladesh | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Barbados | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Belarus | 0.041 | 0.051 |  | 6,878 | 6,830 |  | 6,234 | 6,269 |
| Belgium | 0.828 | 1.035 |  | 138,893 | 137,934 |  | 125,903 | 126,610 |
| Belize | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Benin | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Bhutan | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Bolivia (Plurinational State of) | 0.019 | 0.024 |  | 3,187 | 3,165 |  | 2,889 | 2,905 |
| Bosnia and Herzegovina | 0.012 | 0.015 |  | 2,013 | 1,999 |  | 1,825 | 1,835 |
| Botswana | 0.015 | 0.019 |  | 2,516 | 2,499 |  | 2,281 | 2,294 |
| Brazil | 2.013 | 2.516 |  | 337,672 | 335,340 |  | 306,091 | 307,810 |
| Brunei-Darussalam | 0.021 | 0.026 |  | 3,523 | 3,498 |  | 3,193 | 3,211 |
| Bulgaria | 0.056 | 0.070 |  | 9,394 | 9,329 |  | 8,515 | 8,563 |
| Burkina Faso | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Burundi | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Cape Verde | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Cambodia | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,064 | 1,070 |
| Cameroon | 0.013 | 0.016 |  | 2,181 | 2,166 |  | 1,977 | 1,988 |
| Canada | 2.628 | 3.285 |  | 440,836 | 437,790 |  | 399,606 | 401,850 |
| Central African Republic | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Chad | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Chile | 0.420 | 0.525 |  | 70,453 | 69,967 |  | 63,864 | 64,223 |
| China | 15.254 | 19.069 |  | 2,558,794 | 2,541,117 |  | 2,319,481 | 2,332,505 |
| Colombia | 0.246 | 0.308 |  | 41,265 | 40,980 |  | 37,406 | 37,616 |
| Comoros | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Congo | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Cook Islands | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Costa Rica | 0.069 | 0.086 |  | 11,574 | 11,494 |  | 10,492 | 10,551 |
| Cote d'Ivoire | 0.022 | 0.028 |  | 3,690 | 3,665 |  | 3,345 | 3,364 |
| Croatia | 0.091 | 0.114 |  | 15,265 | 15,159 |  | 13,837 | 13,915 |
| Cuba | 0.095 | 0.119 |  | 15,936 | 15,826 |  | 14,445 | 14,527 |
| Cyprus | 0.036 | 0.045 |  | 6,039 | 5,997 |  | 5,474 | 5,505 |
| Czechia | 0.340 | 0.425 |  | 57,034 | 56,640 |  | 51,699 | 51,990 |
| Democratic People's Republic of Korea | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Democratic Republic of the Congo | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Denmark | 0.553 | 0.691 |  | 92,763 | 92,123 |  | 84,088 | 84,560 |
| Djibouti | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Dominica | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Dominican Republic | 0.067 | 0.084 |  | 11,239 | 11,161 |  | 10,188 | 10,245 |
| Ecuador | 0.077 | 0.096 |  | 12,916 | 12,827 |  | 11,708 | 11,774 |
| Egypt | 0.139 | 0.174 |  | 23,317 | 23,156 |  | 21,136 | 21,255 |
| El Salvador | 0.013 | 0.016 |  | 2,181 | 2,166 |  | 1,977 | 1,988 |
| Equatorial Guinea | 0.012 | 0.015 |  | 2,013 | 1,999 |  | 1,825 | 1,835 |
| Eritrea | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Estonia | 0.044 | 0.055 |  | 7,381 | 7,330 |  | 6,691 | 6,728 |
| Eswatini | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Ethiopia | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| European Union |  | 2.500 |  | 335,470 | 333,153 |  | 304,095 | 305,803 |
| Fiji | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Finland | 0.417 | 0.521 |  | 69,950 | 69,467 |  | 63,408 | 63,764 |
| France | 4.318 | 5.398 |  | 724,326 | 719,322 |  | 656,583 | 660,270 |
| Gabon | 0.013 | 0.016 |  | 2,181 | 2,166 |  | 1,977 | 1,988 |
| Gambia | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Georgia | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Germany | 6.111 | 7.639 |  | 1,025,094 | 1,018,013 |  | 929,222 | 934,440 |
| Ghana | 0.024 | 0.030 |  | 4,026 | 3,998 |  | 3,649 | 3,670 |
| Greece | 0.325 | 0.406 |  | 54,517 | 54,141 |  | 49,419 | 49,696 |
| Grenada | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Guatemala | 0.041 | 0.051 |  | 6,878 | 6,830 |  | 6,234 | 6,269 |
| Guinea | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Guinea-Bissau | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Guyana | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Haiti | 0.006 | 0.008 |  | 1,006 | 1,000 |  | 912 | 917 |
| Honduras | 0.009 | 0.011 |  | 1,510 | 1,499 |  | 1,369 | 1,376 |
| Hungary | 0.228 | 0.285 |  | 38,246 | 37,982 |  | 34,669 | 34,864 |
| Iceland | 0.036 | 0.045 |  | 6,039 | 5,997 |  | 5,474 | 5,505 |
| India | 1.044 | 1.305 |  | 175,127 | 173,917 |  | 158,749 | 159,639 |
| Indonesia | 0.549 | 0.686 |  | 92,092 | 91,456 |  | 83,480 | 83,948 |
| Iran (Islamic Republic of) | 0.371 | 0.464 |  | 62,234 | 61,804 |  | 56,414 | 56,730 |
| Iraq | 0.128 | 0.160 |  | 21,471 | 21,323 |  | 19,464 | 19,573 |
| Ireland | 0.439 | 0.549 |  | 73,640 | 73,132 |  | 66,754 | 67,128 |
| Israel | 0.561 | 0.701 |  | 94,105 | 93,455 |  | 85,305 | 85,783 |
| Italy | 3.189 | 3.987 |  | 534,941 | 531,246 |  | 484,912 | 487,633 |
| Jamaica | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Japan | 8.033 | 10.042 |  | 1,347,502 | 1,338,193 |  | 1,221,477 | 1,228,335 |
| Jordan | 0.022 | 0.028 |  | 3,690 | 3,665 |  | 3,346 | 3,364 |
| Kazakhstan | 0.133 | 0.166 |  | 22,310 | 22,156 |  | 20,225 | 20,337 |
| Kenya | 0.030 | 0.038 |  | 5,032 | 4,998 |  | 4,563 | 4,587 |
| Kiribati | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Kuwait | 0.234 | 0.293 |  | 39,253 | 38,981 |  | 35,582 | 35,781 |
| Kyrgyzstan | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Lao People's Democratic Republic | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,065 | 1,070 |
| Latvia | 0.050 | 0.063 |  | 8,387 | 8,329 |  | 7,604 | 7,646 |
| Lebanon | 0.036 | 0.045 |  | 6,039 | 5,997 |  | 5,475 | 5,505 |
| Lesotho | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Liberia | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Libya | 0.018 | 0.023 |  | 3,019 | 2,999 |  | 2,738 | 2,752 |
| Liechtenstein | 0.010 | 0.013 |  | 1,677 | 1,666 |  | 1,522 | 1,529 |
| Lithuania | 0.077 | 0.096 |  | 12,916 | 12,827 |  | 11,709 | 11,774 |
| Luxembourg | 0.068 | 0.085 |  | 11,407 | 11,328 |  | 10,340 | 10,398 |
| Madagascar | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Malawi | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Malaysia | 0.348 | 0.435 |  | 58,376 | 57,972 |  | 52,916 | 53,213 |
| Maldives | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Mali | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Malta | 0.019 | 0.024 |  | 3,187 | 3,165 |  | 2,889 | 2,905 |
| Marshall Islands | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Mauritania | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Mauritius | 0.019 | 0.024 |  | 3,187 | 3,165 |  | 2,889 | 2,905 |
| Mexico | 1.221 | 1.526 |  | 204,818 | 203,403 |  | 185,662 | 186,704 |
| Micronesia (Federated States of) | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Monaco | 0.011 | 0.014 |  | 1,845 | 1,832 |  | 1,673 | 1,682 |
| Mongolia | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Montenegro | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Morocco | 0.055 | 0.069 |  | 9,226 | 9,162 |  | 8,363 | 8,410 |
| Mozambique | 0.004 | 0.005 |  | 671 | 666 |  | 608 | 612 |
| Myanmar | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Namibia | 0.009 | 0.011 |  | 1,510 | 1,499 |  | 1,369 | 1,376 |
| Nauru | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Nepal | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Netherlands | 1.377 | 1.721 |  | 230,986 | 229,390 |  | 209,383 | 210,559 |
| New Zealand | 0.309 | 0.386 |  | 51,833 | 51,475 |  | 46,986 | 47,250 |
| Nicaragua | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Niger | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Nigeria | 0.182 | 0.228 |  | 30,530 | 30,319 |  | 27,674 | 27,830 |
| Niue | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Norway | 0.679 | 0.849 |  | 113,899 | 113,113 |  | 103,247 | 103,827 |
| Oman | 0.111 | 0.139 |  | 18,620 | 18,491 |  | 16,878 | 16,973 |
| Pakistan | 0.114 | 0.143 |  | 19,123 | 18,991 |  | 17,335 | 17,432 |
| Palau | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Panama | 0.090 | 0.113 |  | 15,097 | 14,993 |  | 13,685 | 13,762 |
| Papua New Guinea | 0.010 | 0.013 |  | 1,677 | 1,665 |  | 1,521 | 1,529 |
| Paraguay | 0.026 | 0.033 |  | 4,361 | 4,330 |  | 3,953 | 3,976 |
| Peru | 0.163 | 0.204 |  | 27,343 | 27,153 |  | 24,785 | 24,925 |
| Philippines | 0.212 | 0.265 |  | 35,562 | 35,315 |  | 32,236 | 32,417 |
| Poland | 0.837 | 1.046 |  | 140,403 | 139,432 |  | 127,272 | 127,987 |
| Portugal | 0.353 | 0.441 |  | 59,214 | 58,804 |  | 53,676 | 53,978 |
| Qatar | 0.269 | 0.336 |  | 45,124 | 44,811 |  | 40,903 | 41,133 |
| Republic of Korea | 2.574 | 3.218 |  | 431,778 | 428,794 |  | 391,395 | 393,593 |
| Republic of Moldova | 0.005 | 0.006 |  | 839 | 833 |  | 760 | 765 |
| Romania | 0.312 | 0.390 |  | 52,337 | 51,975 |  | 47,442 | 47,708 |
| Russian Federation | 1.866 | 2.333 |  | 313,014 | 310,850 |  | 283,739 | 285,332 |
| Rwanda | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Saint Kitts and Nevis | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Saint Lucia | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Saint Vincent and the Grenadines | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Samoa | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| San Marino | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Sao Tome and Principe | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Saudi Arabia | 1.184 | 1.480 |  | 198,611 | 197,238 |  | 180,036 | 181,047 |
| Senegal | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,064 | 1,070 |
| Serbia | 0.032 | 0.040 |  | 5,368 | 5,331 |  | 4,866 | 4,893 |
| Seychelles | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Sierra Leone | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Singapore | 0.504 | 0.630 |  | 84,544 | 83,959 |  | 76,637 | 77,067 |
| Slovakia | 0.155 | 0.194 |  | 26,001 | 25,820 |  | 23,569 | 23,701 |
| Slovenia | 0.079 | 0.099 |  | 13,252 | 13,159 |  | 12,013 | 12,080 |
| Solomon Islands | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Somalia | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| South Africa | 0.244 | 0.305 |  | 40,930 | 40,646 |  | 37,102 | 37,310 |
| South Sudan | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Spain | 2.134 | 2.668 |  | 357,969 | 355,496 |  | 324,490 | 326,311 |
| Sri Lanka | 0.045 | 0.056 |  | 7,549 | 7,496 |  | 6,843 | 6,880 |
| State of Palestine | 0.011 | 0.014 |  | 1,845 | 1,832 |  | 1,673 | 1,681 |
| Sudan | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,222 |
| Suriname | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Sweden | 0.871 | 1.089 |  | 146,107 | 145,097 |  | 132,442 | 133,185 |
| Switzerland | 1.134 | 1.418 |  | 190,224 | 188,910 |  | 172,433 | 173,400 |
| Syrian Arab Republic | 0.009 | 0.011 |  | 1,510 | 1,499 |  | 1,369 | 1,375 |
| Tajikistan | 0.003 | 0.004 |  | 503 | 500 |  | 456 | 459 |
| Thailand | 0.368 | 0.460 |  | 61,730 | 61,303 |  | 55,957 | 56,271 |
| The Former Yugoslav Republic of Macedonia | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,064 | 1,070 |
| Timor-Leste | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Togo | 0.002 | 0.003 |  | 335 | 333 |  | 304 | 306 |
| Tonga | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Trinidad and Tobago | 0.037 | 0.046 |  | 6,207 | 6,164 |  | 5,626 | 5,658 |
| Tunisia | 0.019 | 0.024 |  | 3,187 | 3,165 |  | 2,889 | 2,905 |
| Türkiye | 0.845 | 1.056 |  | 141,745 | 140,766 |  | 128,488 | 129,210 |
| Turkmenistan | 0.034 | 0.043 |  | 5,703 | 5,664 |  | 5,170 | 5,199 |
| Tuvalu | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Uganda | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Ukraine | 0.056 | 0.070 |  | 9,394 | 9,329 |  | 8,515 | 8,563 |
| United Arab Emirates | 0.635 | 0.794 |  | 106,519 | 105,782 |  | 96,556 | 97,099 |
| United Kingdom of Great Britain and Northern Ireland | 4.375 | 5.469 |  | 733,887 | 728,817 |  | 665,251 | 668,986 |
| United Republic of Tanzania | 0.010 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Uruguay | 0.092 | 0.115 |  | 15,433 | 15,326 |  | 13,989 | 14,068 |
| Uzbekistan | 0.027 | 0.034 |  | 4,529 | 4,498 |  | 4,106 | 4,129 |
| Vanuatu | 0.001 | 0.001 |  | 168 | 167 |  | 152 | 153 |
| Venezuela (Bolivarian Republic of) | 0.175 | 0.219 |  | 29,356 | 29,153 |  | 26,610 | 26,759 |
| Viet Nam | 0.093 | 0.116 |  | 15,600 | 15,493 |  | 14,141 | 14,221 |
| Yemen | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Zambia | 0.008 | 0.010 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Zimbabwe | 0.007 | 0.009 |  | 1,174 | 1,166 |  | 1,064 | 1,070 |
| Total | 78.013 | 100.00 |  | 13,418,800 | 13,326,100 |  | 12,163,800 | 12,232,100 |

## B.	Trust Fund for the Cartagena Protocol on Biosafety

| Member Country | Scale of assessment 2022-2024 | Scale with 22% ceiling, no LDC paying more than 0.01 per cent |  | Zero Real Growth |  |  | Zero Nominal Growth |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |
| Afghanistan | 0.006 | 0.008 |  | 237 | 235 |  | 215 | 216 |
| Albania | 0.008 | 0.011 |  | 316 | 314 |  | 286 | 288 |
| Algeria | 0.109 | 0.154 |  | 4,302 | 4,272 |  | 3,899 | 3,921 |
| Angola | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Antigua and Barbuda | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Armenia | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Austria | 0.679 | 0.959 |  | 26,798 | 26,613 |  | 24,291 | 24,428 |
| Azerbaijan | 0.030 | 0.042 |  | 1,184 | 1,176 |  | 1,073 | 1,079 |
| Bahamas | 0.019 | 0.027 |  | 750 | 745 |  | 680 | 684 |
| Bahrain | 0.054 | 0.076 |  | 2,131 | 2,116 |  | 1,932 | 1,943 |
| Bangladesh | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Barbados | 0.008 | 0.011 |  | 316 | 314 |  | 286 | 288 |
| Belarus | 0.041 | 0.058 |  | 1,618 | 1,607 |  | 1,467 | 1,475 |
| Belgium | 0.828 | 1.169 |  | 32,678 | 32,453 |  | 29,621 | 29,789 |
| Belize | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Benin | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Bhutan | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Bolivia (Plurinational State of) | 0.019 | 0.027 |  | 750 | 745 |  | 680 | 684 |
| Bosnia and Herzegovina | 0.012 | 0.017 |  | 474 | 470 |  | 429 | 432 |
| Botswana | 0.015 | 0.021 |  | 592 | 588 |  | 537 | 540 |
| Brazil | 2.013 | 2.842 |  | 79,446 | 78,898 |  | 72,015 | 72,421 |
| Bulgaria | 0.056 | 0.079 |  | 2,210 | 2,195 |  | 2,003 | 2,015 |
| Burkina Faso | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Burundi | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Cambodia | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Cameroon | 0.013 | 0.018 |  | 513 | 510 |  | 465 | 468 |
| Cape Verde | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Central African Republic | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Chad | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| China | 15.254 | 21.535 |  | 602,022 | 597,866 |  | 545,708 | 548,787 |
| Colombia | 0.246 | 0.347 |  | 9,709 | 9,642 |  | 8,801 | 8,850 |
| Comoros | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Congo | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Costa Rica | 0.069 | 0.097 |  | 2,723 | 2,704 |  | 2,468 | 2,482 |
| Cote d'Ivoire | 0.022 | 0.031 |  | 868 | 862 |  | 787 | 791 |
| Croatia | 0.091 | 0.128 |  | 3,591 | 3,567 |  | 3,256 | 3,274 |
| Cuba | 0.095 | 0.134 |  | 3,749 | 3,723 |  | 3,399 | 3,418 |
| Cyprus | 0.036 | 0.051 |  | 1,421 | 1,411 |  | 1,288 | 1,295 |
| Czechia | 0.340 | 0.480 |  | 13,419 | 13,326 |  | 12,163 | 12,232 |
| Democratic People's Republic of Korea | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Democratic Republic of the Congo | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Denmark | 0.553 | 0.781 |  | 21,825 | 21,674 |  | 19,782 | 19,895 |
| Djibouti | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Dominica | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Dominican Republic | 0.067 | 0.095 |  | 2,644 | 2,626 |  | 2,397 | 2,410 |
| Ecuador | 0.077 | 0.109 |  | 3,039 | 3,018 |  | 2,755 | 2,770 |
| Egypt | 0.139 | 0.196 |  | 5,486 | 5,448 |  | 4,973 | 5,001 |
| El Salvador | 0.013 | 0.018 |  | 513 | 510 |  | 465 | 468 |
| Eritrea | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Estonia | 0.044 | 0.062 |  | 1,737 | 1,725 |  | 1,574 | 1,583 |
| Eswatini | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Ethiopia | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| European Union |  | 2.500 |  | 69,890 | 69,408 |  | 63,353 | 63,710 |
| Fiji | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Finland | 0.417 | 0.589 |  | 16,458 | 16,344 |  | 14,918 | 15,002 |
| France | 4.318 | 6.096 |  | 170,416 | 169,240 |  | 154,475 | 155,347 |
| Gabon | 0.013 | 0.018 |  | 513 | 510 |  | 465 | 468 |
| Gambia | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Georgia | 0.008 | 0.011 |  | 316 | 314 |  | 286 | 288 |
| Germany | 6.111 | 8.627 |  | 241,180 | 239,515 |  | 218,620 | 219,852 |
| Ghana | 0.024 | 0.034 |  | 947 | 941 |  | 859 | 863 |
| Greece | 0.325 | 0.459 |  | 12,827 | 12,738 |  | 11,627 | 11,692 |
| Grenada | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Guatemala | 0.041 | 0.058 |  | 1,618 | 1,607 |  | 1,467 | 1,475 |
| Guinea | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| Guinea-Bissau | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Guyana | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Honduras | 0.009 | 0.013 |  | 355 | 353 |  | 322 | 324 |
| Hungary | 0.228 | 0.322 |  | 8,998 | 8,936 |  | 8,157 | 8,203 |
| India | 1.044 | 1.474 |  | 41,203 | 40,919 |  | 37,349 | 37,560 |
| Indonesia | 0.549 | 0.775 |  | 21,667 | 21,518 |  | 19,640 | 19,751 |
| Iran (Islamic Republic of) | 0.371 | 0.524 |  | 14,642 | 14,541 |  | 13,272 | 13,347 |
| Iraq | 0.128 | 0.181 |  | 5,052 | 5,017 |  | 4,579 | 4,605 |
| Ireland | 0.439 | 0.620 |  | 17,326 | 17,206 |  | 15,705 | 15,794 |
| Italy | 3.189 | 4.502 |  | 125,859 | 124,990 |  | 114,086 | 114,730 |
| Jamaica | 0.008 | 0.011 |  | 316 | 314 |  | 286 | 288 |
| Japan | 8.033 | 11.340 |  | 317,034 | 314,846 |  | 287,379 | 289,001 |
| Jordan | 0.022 | 0.031 |  | 868 | 862 |  | 787 | 791 |
| Kazakhstan | 0.133 | 0.188 |  | 5,249 | 5,213 |  | 4,758 | 4,785 |
| Kenya | 0.030 | 0.042 |  | 1,184 | 1,176 |  | 1,073 | 1,079 |
| Kiribati | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Kuwait | 0.234 | 0.330 |  | 9,235 | 9,171 |  | 8,371 | 8,419 |
| Kyrgyzstan | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Lao People's Democratic Republic | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Latvia | 0.050 | 0.071 |  | 1,973 | 1,960 |  | 1,789 | 1,799 |
| Lebanon | 0.036 | 0.051 |  | 1,421 | 1,411 |  | 1,288 | 1,295 |
| Lesotho | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Liberia | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Libya | 0.018 | 0.025 |  | 710 | 705 |  | 644 | 648 |
| Lithuania | 0.077 | 0.109 |  | 3,039 | 3,018 |  | 2,755 | 2,770 |
| Luxembourg | 0.068 | 0.096 |  | 2,684 | 2,665 |  | 2,433 | 2,446 |
| Madagascar | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Malawi | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Malaysia | 0.348 | 0.491 |  | 13,734 | 13,640 |  | 12,450 | 12,519 |
| Maldives | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Mali | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Malta | 0.019 | 0.027 |  | 750 | 745 |  | 680 | 684 |
| Marshall Islands | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Mauritania | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Mauritius | 0.019 | 0.027 |  | 750 | 745 |  | 680 | 684 |
| Mexico | 1.221 | 1.724 |  | 48,189 | 47,856 |  | 43,681 | 43,928 |
| Mongolia | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Montenegro | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Morocco | 0.055 | 0.078 |  | 2,171 | 2,156 |  | 1,968 | 1,979 |
| Mozambique | 0.004 | 0.006 |  | 158 | 157 |  | 143 | 144 |
| Myanmar | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Namibia | 0.009 | 0.013 |  | 355 | 353 |  | 322 | 324 |
| Nauru | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Netherlands | 1.377 | 1.944 |  | 54,346 | 53,970 |  | 49,262 | 49,540 |
| New Zealand | 0.309 | 0.436 |  | 12,195 | 12,111 |  | 11,054 | 11,117 |
| Nicaragua | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Niger | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| Nigeria | 0.182 | 0.257 |  | 7,183 | 7,133 |  | 6,511 | 6,548 |
| Niue | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Norway | 0.679 | 0.959 |  | 26,799 | 26,613 |  | 24,291 | 24,428 |
| Oman | 0.111 | 0.157 |  | 4,381 | 4,351 |  | 3,971 | 3,993 |
| Pakistan | 0.114 | 0.161 |  | 4,499 | 4,468 |  | 4,078 | 4,101 |
| Palau | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Panama | 0.090 | 0.127 |  | 3,553 | 3,527 |  | 3,220 | 3,238 |
| Papua New Guinea | 0.010 | 0.014 |  | 395 | 392 |  | 358 | 360 |
| Paraguay | 0.026 | 0.037 |  | 1,026 | 1,019 |  | 930 | 935 |
| Peru | 0.163 | 0.230 |  | 6,433 | 6,389 |  | 5,831 | 5,863 |
| Philippines | 0.212 | 0.299 |  | 8,367 | 8,309 |  | 7,584 | 7,627 |
| Poland | 0.837 | 1.182 |  | 33,034 | 32,805 |  | 29,944 | 30,112 |
| Portugal | 0.353 | 0.498 |  | 13,932 | 13,835 |  | 12,629 | 12,700 |
| Qatar | 0.269 | 0.380 |  | 10,616 | 10,543 |  | 9,623 | 9,678 |
| Republic of Korea | 2.574 | 3.634 |  | 101,588 | 100,884 |  | 92,084 | 92,603 |
| Republic of Moldova | 0.005 | 0.007 |  | 197 | 196 |  | 179 | 180 |
| Romania | 0.312 | 0.440 |  | 12,314 | 12,229 |  | 11,162 | 11,225 |
| Rwanda | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| Saint Kitts and Nevis | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Saint Lucia | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Saint Vincent and the Grenadines | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Samoa | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Saudi Arabia | 1.184 | 1.671 |  | 46,728 | 46,406 |  | 42,357 | 42,595 |
| Senegal | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Serbia | 0.032 | 0.045 |  | 1,263 | 1,254 |  | 1,145 | 1,151 |
| Seychelles | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Sierra Leone | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Slovakia | 0.155 | 0.219 |  | 6,117 | 6,075 |  | 5,545 | 5,577 |
| Slovenia | 0.079 | 0.112 |  | 3,118 | 3,096 |  | 2,826 | 2,843 |
| Solomon Islands | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Somalia | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| South Africa | 0.244 | 0.344 |  | 9,630 | 9,563 |  | 8,729 | 8,778 |
| Spain | 2.134 | 3.013 |  | 84,221 | 83,640 |  | 76,343 | 76,774 |
| Sri Lanka | 0.045 | 0.064 |  | 1,776 | 1,764 |  | 1,610 | 1,619 |
| State of Palestine | 0.011 | 0.016 |  | 434 | 431 |  | 394 | 396 |
| Sudan | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Suriname | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| Sweden | 0.871 | 1.230 |  | 34,376 | 34,137 |  | 31,160 | 31,335 |
| Switzerland | 1.134 | 1.601 |  | 44,756 | 44,446 |  | 40,569 | 40,797 |
| Syrian Arab Republic | 0.009 | 0.013 |  | 355 | 353 |  | 322 | 324 |
| Tajikistan | 0.003 | 0.004 |  | 118 | 118 |  | 107 | 108 |
| Thailand | 0.368 | 0.520 |  | 14,524 | 14,422 |  | 13,165 | 13,239 |
| The Former Yugoslav Republic of Macedonia | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Togo | 0.002 | 0.003 |  | 79 | 78 |  | 72 | 72 |
| Tonga | 0.001 | 0.001 |  | 39 | 39 |  | 36 | 36 |
| Trinidad and Tobago | 0.037 | 0.052 |  | 1,460 | 1,450 |  | 1,324 | 1,331 |
| Tunisia | 0.019 | 0.027 |  | 750 | 745 |  | 680 | 684 |
| Türkiye | 0.845 | 1.193 |  | 33,350 | 33,118 |  | 30,230 | 30,399 |
| Turkmenistan | 0.034 | 0.048 |  | 1,342 | 1,333 |  | 1,216 | 1,223 |
| Uganda | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Ukraine | 0.056 | 0.079 |  | 2,210 | 2,195 |  | 2,003 | 2,015 |
| United Arab Emirates | 0.635 | 0.896 |  | 25,061 | 24,887 |  | 22,717 | 22,846 |
| United Kingdom of Great Britain and Northern Ireland | 4.375 | 6.176 |  | 172,667 | 171,473 |  | 156,514 | 157,397 |
| United Republic of Tanzania | 0.010 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Uruguay | 0.092 | 0.130 |  | 3,631 | 3,606 |  | 3,291 | 3,310 |
| Uzbekistan | 0.027 | 0.038 |  | 1,066 | 1,058 |  | 966 | 971 |
| Venezuela (Bolivarian Republic of) | 0.175 | 0.247 |  | 6,907 | 6,859 |  | 6,261 | 6,296 |
| Viet Nam | 0.093 | 0.131 |  | 3,670 | 3,645 |  | 3,327 | 3,346 |
| Yemen | 0.008 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Zambia | 0.008 | 0.010 |  | 280 | 278 |  | 253 | 255 |
| Zimbabwe | 0.007 | 0.010 |  | 276 | 274 |  | 250 | 252 |
| Total | 69.092 | 100.000 |  | 2,795,600 | 2,776,300 |  | 2,534,100 | 2,548,400 |

## C.	Trust Fund for the Nagoya Protocol on Access to Genetic Resources

| Member Country | Scale of assessment 2022-2024 | Scale with 22% ceiling, no LDC paying more than 0.01 per cent |  | Zero Real Growth Scenario - 8% |  |  | Zero Nominal Growth Scenario - 0% |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |  | Contributions per 1 Jan 2023 | Contributions per 1 Jan 2024 |
| Afghanistan | 0.006 | 0.009 |  | 227 | 226 |  | 206 | 207 |
| Albania | 0.008 | 0.013 |  | 303 | 301 |  | 275 | 276 |
| Angola | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Antigua and Barbuda | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Argentina | 0.719 | 1.125 |  | 27,246 | 27,058 |  | 24,698 | 24,837 |
| Austria | 0.679 | 1.062 |  | 25,730 | 25,553 |  | 23,324 | 23,456 |
| Bahamas | 0.019 | 0.030 |  | 720 | 715 |  | 653 | 656 |
| Bahrein | 0.054 | 0.084 |  | 2,046 | 2,032 |  | 1,855 | 1,865 |
| Belarus | 0.041 | 0.064 |  | 1,554 | 1,543 |  | 1,408 | 1,416 |
| Belgium | 0.828 | 1.295 |  | 31,377 | 31,159 |  | 28,442 | 28,603 |
| Benin | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Bhutan | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Bolivia (Plurinational State of) | 0.019 | 0.030 |  | 720 | 715 |  | 653 | 656 |
| Botswana | 0.015 | 0.023 |  | 568 | 565 |  | 515 | 518 |
| Brazil | 2.013 | 3.148 |  | 76,282 | 75,756 |  | 69,147 | 69,538 |
| Bulgaria | 0.056 | 0.088 |  | 2,122 | 2,107 |  | 1,924 | 1,934 |
| Burkina Faso | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Burundi | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Cambodia | 0.007 | 0.011 |  | 265 | 263 |  | 240 | 242 |
| Cameroon | 0.013 | 0.020 |  | 493 | 489 |  | 447 | 449 |
| Central African Republic | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Chad | 0.003 | 0.005 |  | 114 | 113 |  | 103 | 104 |
| China | 15.254 | 23.858 |  | 578,043 | 574,058 |  | 523,980 | 526,939 |
| Comoros | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Congo | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Cote d'Ivoire | 0.022 | 0.034 |  | 834 | 828 |  | 756 | 760 |
| Croatia | 0.091 | 0.142 |  | 3,448 | 3,425 |  | 3,126 | 3,144 |
| Cuba | 0.095 | 0.149 |  | 3,600 | 3,575 |  | 3,263 | 3,282 |
| Czechia | 0.340 | 0.532 |  | 12,884 | 12,794 |  | 11,679 | 11,745 |
| Democratic Republic of Korea | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Democratic Republic of the Congo | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Denmark | 0.553 | 0.865 |  | 20,956 | 20,811 |  | 18,996 | 19,103 |
| Djibouti | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Dominican Republic | 0.067 | 0.105 |  | 2,539 | 2,521 |  | 2,301 | 2,314 |
| Ecuador | 0.077 | 0.120 |  | 2,918 | 2,898 |  | 2,645 | 2,660 |
| Egypt | 0.139 | 0.217 |  | 5,267 | 5,231 |  | 4,775 | 4,802 |
| Eritrea | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Estonia | 0.044 | 0.069 |  | 1,667 | 1,656 |  | 1,511 | 1,520 |
| Eswatini | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Ethiopia | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| European Union |  | 2.500 |  | 60,570 | 60,153 |  | 54,905 | 55,215 |
| Fiji | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Finland | 0.417 | 0.652 |  | 15,802 | 15,693 |  | 14,324 | 14,405 |
| France | 4.318 | 6.754 |  | 163,629 | 162,501 |  | 148,325 | 149,162 |
| Gabon | 0.013 | 0.020 |  | 493 | 489 |  | 447 | 449 |
| Gambia | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Germany | 6.111 | 9.558 |  | 231,573 | 229,976 |  | 209,915 | 211,100 |
| Ghana | 0.024 | 0.038 |  | 909 | 903 |  | 824 | 829 |
| Greece | 0.325 | 0.508 |  | 12,316 | 12,231 |  | 11,164 | 11,227 |
| Guatemala | 0.041 | 0.064 |  | 1,554 | 1,543 |  | 1,408 | 1,416 |
| Guinea | 0.003 | 0.005 |  | 114 | 113 |  | 103 | 104 |
| Guinea-Bissau | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Guyana | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Honduras | 0.009 | 0.014 |  | 341 | 339 |  | 309 | 311 |
| Hungary | 0.228 | 0.357 |  | 8,640 | 8,580 |  | 7,832 | 7,876 |
| India | 1.044 | 1.633 |  | 39,562 | 39,289 |  | 35,862 | 36,064 |
| Indonesia | 0.549 | 0.859 |  | 20,804 | 20,661 |  | 18,858 | 18,965 |
| Japan | 8.033 | 12.564 |  | 304,406 | 302,308 |  | 275,936 | 277,494 |
| Jordan | 0.022 | 0.034 |  | 834 | 828 |  | 756 | 760 |
| Kazakhstan | 0.133 | 0.208 |  | 5,040 | 5,005 |  | 4,569 | 4,594 |
| Kenya | 0.030 | 0.047 |  | 1,137 | 1,129 |  | 1,031 | 1,036 |
| Kiribati | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Kuwait | 0.234 | 0.366 |  | 8,867 | 8,806 |  | 8,038 | 8,083 |
| Kyrgyzstan | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Lao People's Democratic Republic | 0.007 | 0.011 |  | 265 | 263 |  | 240 | 242 |
| Lebanon | 0.036 | 0.056 |  | 1,364 | 1,355 |  | 1,237 | 1,244 |
| Lesotho | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Liberia | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Luxembourg | 0.068 | 0.106 |  | 2,577 | 2,559 |  | 2,336 | 2,349 |
| Madagascar | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Malawi | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Malaysia | 0.348 | 0.544 |  | 13,187 | 13,096 |  | 11,954 | 12,020 |
| Maldives | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Mali | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Malta | 0.019 | 0.030 |  | 720 | 715 |  | 653 | 656 |
| Marshall Islands | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Mauritania | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Mauritius | 0.019 | 0.030 |  | 720 | 715 |  | 653 | 656 |
| Mexico | 1.221 | 1.910 |  | 46,269 | 45,950 |  | 41,942 | 42,179 |
| Micronesia (Federated States of) | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Mongolia | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Montenegro | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Morocco | 0.055 | 0.086 |  | 2,084 | 2,070 |  | 1,889 | 1,900 |
| Mozambique | 0.004 | 0.006 |  | 152 | 151 |  | 137 | 138 |
| Myanmar | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Namibia | 0.009 | 0.014 |  | 341 | 339 |  | 309 | 311 |
| Nepal | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Netherlands | 1.377 | 2.154 |  | 52,181 | 51,821 |  | 47,300 | 47,566 |
| Nicaragua | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Niger | 0.003 | 0.005 |  | 114 | 113 |  | 103 | 104 |
| Nigeria | 0.182 | 0.285 |  | 6,897 | 6,849 |  | 6,252 | 6,287 |
| Norway | 0.679 | 1.062 |  | 25,730 | 25,553 |  | 23,324 | 23,455 |
| Oman | 0.111 | 0.174 |  | 4,206 | 4,177 |  | 3,813 | 3,834 |
| Pakistan | 0.114 | 0.178 |  | 4,320 | 4,290 |  | 3,916 | 3,938 |
| Palau | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Panama | 0.090 | 0.141 |  | 3,411 | 3,387 |  | 3,092 | 3,109 |
| Peru | 0.163 | 0.255 |  | 6,177 | 6,134 |  | 5,599 | 5,631 |
| Philippines | 0.212 | 0.332 |  | 8,034 | 7,978 |  | 7,282 | 7,323 |
| Portugal | 0.353 | 0.552 |  | 13,377 | 13,285 |  | 12,126 | 12,194 |
| Qatar | 0.269 | 0.421 |  | 10,194 | 10,123 |  | 9,240 | 9,292 |
| Republic of Korea | 2.574 | 4.026 |  | 97,541 | 96,868 |  | 88,418 | 88,916 |
| Republic of Moldova | 0.005 | 0.008 |  | 189 | 188 |  | 172 | 173 |
| Romania | 0.312 | 0.488 |  | 11,823 | 11,742 |  | 10,717 | 10,778 |
| Rwanda | 0.003 | 0.005 |  | 114 | 113 |  | 103 | 104 |
| Saint Kitts and Nevis | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Saint Lucia | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Samoa | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Sao Tome and Principe | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Saudi Arabia | 1.184 | 1.852 |  | 44,867 | 44,558 |  | 40,672 | 40,899 |
| Senegal | 0.007 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Serbia | 0.032 | 0.050 |  | 1,213 | 1,204 |  | 1,099 | 1,105 |
| Seychelles | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Sierra Leone | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Slovakia | 0.155 | 0.242 |  | 5,874 | 5,833 |  | 5,324 | 5,354 |
| Solomon Islands | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| South Africa | 0.244 | 0.382 |  | 9,246 | 9,183 |  | 8,381 | 8,429 |
| Spain | 2.134 | 3.338 |  | 80,867 | 80,310 |  | 73,304 | 73,717 |
| Sudan | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Sweden | 0.871 | 1.362 |  | 33,006 | 32,778 |  | 29,919 | 30,087 |
| Switzerland | 1.134 | 1.774 |  | 42,972 | 42,676 |  | 38,953 | 39,173 |
| Syrian Arab Republic | 0.009 | 0.014 |  | 341 | 339 |  | 309 | 311 |
| Tajikistan | 0.003 | 0.005 |  | 114 | 113 |  | 103 | 104 |
| Togo | 0.002 | 0.003 |  | 76 | 75 |  | 69 | 69 |
| Tonga | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Tunisia | 0.019 | 0.030 |  | 720 | 715 |  | 653 | 656 |
| Turkmenistan | 0.034 | 0.053 |  | 1,288 | 1,280 |  | 1,168 | 1,175 |
| Tuvalu | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Uganda | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Ukraine | 0.056 | 0.088 |  | 2,122 | 2,107 |  | 1,924 | 1,934 |
| United Arab Emirates | 0.635 | 0.993 |  | 24,063 | 23,896 |  | 21,812 | 21,936 |
| United Kingdom of Great Britain and Northern Ireland | 4.375 | 6.843 |  | 165,788 | 164,645 |  | 150,284 | 151,130 |
| United Republic of Tanzania | 0.010 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Uruguay | 0.092 | 0.144 |  | 3,486 | 3,462 |  | 3,160 | 3,178 |
| Vanuatu | 0.001 | 0.002 |  | 38 | 38 |  | 34 | 35 |
| Venezuela (Bolivarian Republic of) | 0.175 | 0.274 |  | 6,632 | 6,585 |  | 6,011 | 6,045 |
| Viet Nam | 0.093 | 0.145 |  | 3,524 | 3,500 |  | 3,195 | 3,213 |
| Zambia | 0.008 | 0.010 |  | 242 | 241 |  | 220 | 221 |
| Zimbabwe | 0.007 | 0.011 |  | 265 | 263 |  | 240 | 242 |
| Total | 62.368 | 100.000 |  | 2,422,800 | 2,406,100 |  | 2,196,200 | 2,208,600 |

_____________________________

Given that decision 14/37 anticipated that the proposal would be prepared after a regular two-year period, it may be inferred that this cap should be raised to 8 per cent after a four-year period. This would be equal to a zero real growth budget. Thus, even with such an interpretation, it is not possible to prepare a budget with the “required rate of growth”.

UNEP/EA.2/Res.18

Fifth edition of the Global Biodiversity Outlook and IPBES (2019): Global assessment report on biodiversity and ecosystem services of the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services. E. S. Brondizio, J. Settele, S. Díaz, and H. T. Ngo (editors). IPBES secretariat, Bonn, Germany. 1148 pages. https://doi.org/10.5281/zenodo.3831673

See CBD/SBI/3/INF/39

A/77/5/Add.7, para 52-59.