## Slide 1
Resource Mobilization and Financial Reporting under the CBD
Assessing funding needs, gaps, and priorities: costing the NBSAPs
Sub-regional workshop on financial reporting and resource mobilization for the Pacific region
Avarua, Cook Islands, 5-6 October 2015
Csoban Somodi
Secretariat of the Convention on Biological Diversity

## Slide 2: Introduction
Very few countries have so far submitted fully costed NBSAP
Every country has its own approach to budgeting
The question to ask is : “who will be deciding on the budget financing?”
Notes: Although a significant number of countries are currently working on costing their NBSAPs, very few countries have so far submitted fully costed NBSAPs to the Convention. Budgeting is not a new topic to most actors in government, since not only do almost all organizations, agencies, ministries and companies establish annual budgets, but they also develop medium and long-term strategic plans with clear budgets.
It is important to note that every country, organization, and business has its own approach to budgeting. As such, with any budgeting initiative, the most important initial question is: “who will be deciding on the budget financing?” For the case of NBSAPs, it is usually the Ministry of Finance (or Planning, etc.) that will make initial decision on basic internal financing. Other potential financial decision makers include line ministries, ministries of planning, international donors, development banks, NGOs, etc. If the NBSAP budgeting process adheres to the national budget process, it has a much greater chance of being effectively integrated into national budgets. In fact, the use of the detailed budgeting codes of a country is one of the best practices promoted by the UNDP BIOFIN initiative.
Costing of NBSAP actions: The fourth step is to identify the costs associated with implementing each of the actions within the national biodiversity strategies and action plans (NBSAPs). The focus is on an activity-based cost accounting method, whereby each action is aggregated into specific per-unit costs. This step also looks at the financial gap between the projected future expenditures and the likely costs. This is the finance gap, which is the focus of the final step.

## Slide 3: Financial decision makers
Ministry of Finance
Other ministries
International donors
Development banks
NGOs
Notes: usually the Ministry of Finance (or Planning, etc.) that will make initial decision on basic internal financing. Other potential financial decision makers include line ministries, ministries of planning, international donors, development banks, NGOs, etc.

## Slide 4: Better integration of NBSAPs
Aligning NBSAP budgeting with the national budgeting process
The role of using national budgeting codes (UNDP BIOFIN initiative).
Notes: If the NBSAP budgeting process adheres to the national budget process, it has a much greater chance of being effectively integrated into national budgets. In fact, the use of the detailed budgeting codes of a country is one of the best practices promoted by the UNDP BIOFIN initiative.

## Slide 5: Setting priorities: guidance on cost effectiveness
Use NBSAP process by identifying, prioritizing and categorizing the most critical areas.
Begin with the effective tools that are already in place and where we have experience.
It is advised to do as much costing as possible and, as a precondition, to develop an action plan with clear, quantifiable targets.
Notes: In terms of guidance for countries, it was suggested to follow the NBSAP process by identifying, prioritizing and categorizing the most critical areas, and getting support from key agencies to ensure that the activities get funded;
Begin with the effective tools that are already in place and where we have experience (e.g. Protected Area management effectiveness, conservation programs), noting that many economic values are not known in countries.
The group noted the tradeoff between comprehensiveness and quantitative indicators in the NBSAP process, and advised to do as much costing as possible and developing an action plan with clear, quantifiable targets. NBSAPs should have sustainable financing components (multiple action plans within NBSAPs; within each action plan, activities should be prioritized based on a combination of urgency and special mapping of ecosystem services); geographic and activities-based prioritization.

## Slide 6: How to determine funding needs
Use the NBSAP to identify the activities that need to be implemented in order to achieve the national targets – including scope, scale, timing, and responsible actors
Assess the actual cost of achieving specific target or associated strategies by developing a detailed programme of ‘costable’ activities (‘work breakdown structure’ – WBS)
Synergize with the GEF cycle and the GEF-7 needs assessment (see questionnaire)

## Slide 7: Key elements to prepare for accurate NBSAP costing
Scope and scale
Timing of implementation
Responsible actors
Disbursement
Capital Investment
Recurring costs
Identified early and during the process
Different expectations
Region
Quantified results
Notes: Scope and scale – for each NBSAP activity, the scope of the activity and the scale of the effort should be identified. Does the activity include the entire country or certain regions? Which regions? What are the quantified results that the activity will produce? For example, if the activity is initially designed as “Expand the PA network for ecological representativeness”, will the activity result in the Aichi Target goal of 17% coverage? Will certain PAs be expanded or will new PAs be created? Since the location of the PA relative to existing pressures will determine the cost of management, the specific location of future PAs may be important input into the costing.
Timing of implementation – the timing of both capital investments and recurring costs should be mapped out as part of the costing effort to better plan and finance activities.
Responsible actors – it is essential that the responsible actors are identified during the process of NBSAP costing. That is because various actors will have different cost basis for achieving specific results and implementing specific activities. As well, it is essential for resource mobilization goals that the implementing actors are identified during the costing process.

## Slide 8: Stakeholders identification and analysis
Identify all potential stakeholders
Analyze the potential impact and support and classify them
Assess how key stakeholders are likely to react
  Result: Stakeholder classification
Notes: Is the process of identifying people, groups, or organizations that could impact or be impacted by a decision, activity or outcome of an activity, analyzing and documenting relevant information regarding their interests, involvement, interdependencies, influence and potential impact on the success of the activity.
It is critical for the activity to identify the stakeholders early and to analyze their level of interest, expectations, and influence.
3) In order to plan how to influence them to enhance their support and mitigate potential negative impact
Multiple classification models for stakeholders analysis:
Power/interest grid
Power/influence grid
Influence/impact grid

## Slide 9: Stakeholders identification and analysis (cont.)

## Slide 10: Stakeholders identification and analysis
Stakeholder
roles
departments
expectations
influence
interests
knowledge
Notes: Is the process of identifying people, groups, or organizations that could impact or be impacted by a decision, activity or outcome of an activity, analyzing and documenting relevant information regarding their interests, involvement, interdependencies, influence and potential impact on the success of the activity.
It is critical for the activity to identify the stakeholders early and to analyze their level of interest, expectations, and influence.
Roles, departments, interests, knowledge, expectations, influence levels.

## Slide 11: Power/interest grid with Stakeholders

## Slide 12: Scope
NBSAP as a basis for creating a work breakdown structure (WBS)
Lowest level of WBS to be used for estimation of duration, resource needs, and associated cost
Pitfall: Excessive decomposition
Recommendation: stop further decomposition when associated cost can be identified with reasonable accuracy
Notes: Using the top-down method by disaggregating as far as practicable the relevant activities that have been identified. It provides a structured vision of what has to be measured. The input would be the NBSAP as a starting point to create the work breakdown structure.
Once the work packages, the lowest level of WBS components, have been created then they can be used to group activities in order to estimate, monitor and control cost and duration.
Pitfall: Excessive decomposition can lead to non-productive management effort, inefficient use of resources, decreased efficiency in performing work and difficulty of aggregating data over different levels of WBS.
Without WBS the project will take longer, elements will slip through and activity, project will be negatively impacted.

## Slide 13: Decomposition of targets/strategies
Strategic Goal A
Sub-strategy 1
Action 1
Action 2
Sub-strategy 2
Action 1
Strategic Goal A
Sub-strategy 1
Action 1
Action 2
Sub-strategy 2
Action 1
Notes: Decomposition is a technique used for dividing and sub-dividing into smaller, more manageable parts. Activities (actions) represent the effort to complete a work package.

## Slide 14: Decomposition: example
Notes: Decomposition is a technique used for dividing and sub-dividing into smaller, more manageable parts. Activities (actions) represent the effort to complete a work package.

## Slide 15: Timing
Principle: manage by stages
Tool: “Rolling” wave planning (progressive elaboration)
  Result: Scheduled activities for resource estimations
(‘Gantt chart’)
Notes: RW planning is an iterative planning technique in which the work to be accomplished in the near term is planned in detail, while the work in the future is planned in higher level.
Decomposition: dividing and subdividing the project scope and deliverables into smaller more manageable parts.

## Slide 16: Timing
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Consultatory meeting for TOR | 0 | x |  |  |  |  | 
 | Inception workshop | 0 |  | x |  |  |  | 
 | Consultancy | 0 |  |  | x | x |  | 
 | Review and testing | 0 |  |  |  |  | x | 
 | Validation workshop | 0 |  |  |  |  | x | 
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Inception workshop (for 1.1.1) | 0 |  | x |  |  |  | 
 | Research | 0 |  |  | x |  |  | 
 | Validation workshop (for 1.1.1) | 0 |  |  |  | x |  | 
 | Academic publication of assessment study | 0 |  |  |  |  | x | 
 | . | 0 |  |  |  |  |  | 
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
 | Elaboration of requirements( meetings) | 0 |  |  | x |  |  | 
 | Execution of the development (meetings, validation, purchasing software) | 0 |  |  |  | x | x | 
 | Conducting tests | 0 |  |  |  |  | x | 
 | Validation of final product | 0 |  |  |  |  | x | 
 | Workshop for training on the IS | 0 |  |  |  |  |  | x
Timing
(Gantt chart)
Notes: RW planning is an iterative planning technique in which the work to be accomplished in the near term is planned in detail, while the work in the future is planned in higher level.
Decomposition: dividing and subdividing the project scope and deliverables into smaller more manageable parts.

## Slide 17: How to estimate resource needs and costs?
TOOLS:
Expert judgment
Alternative analysis
Published estimating data
Bottom-up estimating (cost aggregation)
Notes: Alternative Analysis: include using various levels of resource capabilities or skills, different tools (hand versus-machine)
Published updated rates, unit costs by organizations.
B. Up estimating is a method of estimating cost or duration by aggregating the estimates of the lower-level components of WBS.

## Slide 18: How to estimate activity durations?
TOOLS:
Analogous estimating (historical data from similar project)
Parametric estimating (statistical relationship)
Three point estimating (Beta distribution (tO+4tM+tP)/6)
Expert judgment
Group decision-making techniques
Notes: Analogous: A technique for estimating the duration or cost of an activity or a project using historical data from a similar activity or project. (TO PREDICT FUTURE). Ex: last 5 projects similar to this one, each took 8 months, so this one should as well.
Parametric: An estimating technique in which an algorithm is used to calculate cost or duration based on historical data and project parameters. higher level of accuracy. (BETWEEN VARIABLES). Historical records from previous projects, ex: industry requirements, standard metrics, time per installation for irrigation.
Group decision-making techniques: Technique to assess multiple alternatives that will be used to generate classify and prioritize requirements.
Expert Judgment: with specialized education, skills, knowledge, experience or training.
Three point estimating An average of the 3 when there is an uncertainty with the activity estimates

## Slide 19: How about administrative cost?
Need to be included in estimations of the biodiversity budget and expenditure data.
The degree to which it is deemed as relevant is taken as proportionate to the rest of the activities in that programme.
For example: if 90% of the non-administration activities are deemed to be relevant to biodiversity, then 90% of the administration budget is assumed to be relevant to biodiversity.
Notes: Therefore, if administration was included as an activity within a programme, the degree to which it is deemed as relevant is taken as proportionate to the rest of the activities in that programme. For example, if 90% of the non-administration activities are deemed to be relevant to biodiversity, then 90% of the administration budget is assumed to be relevant to biodiversity.

## Slide 20: Example from Tuvalu NBSAP
Programmes, sub-programmes, and activities are taken verbatim from the NBSAP
‘Costable’ activities and numbers assigned are our making, for illustrative purposes
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 21: Example from Tuvalu NBSAP
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 305,000 | 30,000 | 60,000 | 65,000 | 150,000 | 173,000 | 45,000 | 523,000
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 200,000 | 30,000 | 60,000 | 60,000 | 50,000 | 83,000 | 0 | 283,000
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 190,000 | 30,000 | 60,000 | 50,000 | 50,000 | 80,000 | 0 | 270,000
 | Consultatory meeting for TOR | 30,000 | 30,000 |  |  |  |  |  | 30,000
 | Inception workshop | 60,000 |  | 60,000 |  |  |  |  | 60,000
 | Consultancy | 100,000 |  |  | 50,000 | 50,000 |  |  | 100,000
 | Review and testing | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation workshop | 0 |  |  |  |  | 60,000 |  | 60,000
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 10,000 | 0 | 0 | 10,000 | 0 | 3,000 | 0 | 13,000
 | Inception workshop (for 1.1.1) | 0 |  | 0 |  |  |  |  | 0
 | Research | 10,000 |  |  | 10,000 |  |  |  | 10,000
 | Validation workshop (for 1.1.1) | 0 |  |  |  | 0 |  |  | 0
 | Academic publication of assessment study | 0 |  |  |  |  | 3,000 |  | 3,000
 | . | 0 |  |  |  |  |  |  | 0
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
 | Elaboration of requirements( meetings) | 5,000 |  |  | 5,000 |  |  |  | 5,000
 | Execution of the development (meetings, validation, purchasing software) | 100,000 |  |  |  | 100,000 | 60,000 |  | 160,000
 | Conducting tests | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation of final product | 0 |  |  |  |  | 10,000 |  | 10,000
 | Workshop for training on the IS | 0 |  |  |  |  |  | 45,000 | 45,000
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 22: Example from Tuvalu NBSAP
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 305,000 | 30,000 | 60,000 | 65,000 | 150,000 | 173,000 | 45,000 | 523,000
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 200,000 | 30,000 | 60,000 | 60,000 | 50,000 | 83,000 | 0 | 283,000
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 190,000 | 30,000 | 60,000 | 50,000 | 50,000 | 80,000 | 0 | 270,000
 | Consultatory meeting for TOR | 30,000 | 30,000 |  |  |  |  |  | 30,000
 | Inception workshop | 60,000 |  | 60,000 |  |  |  |  | 60,000
 | Consultancy | 100,000 |  |  | 50,000 | 50,000 |  |  | 100,000
 | Review and testing | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation workshop | 0 |  |  |  |  | 60,000 |  | 60,000
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 10,000 | 0 | 0 | 10,000 | 0 | 3,000 | 0 | 13,000
 | Inception workshop (for 1.1.1) | 0 |  | 0 |  |  |  |  | 0
 | Research | 10,000 |  |  | 10,000 |  |  |  | 10,000
 | Validation workshop (for 1.1.1) | 0 |  |  |  | 0 |  |  | 0
 | Academic publication of assessment study | 0 |  |  |  |  | 3,000 |  | 3,000
 | . | 0 |  |  |  |  |  |  | 0
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
 | Elaboration of requirements( meetings) | 5,000 |  |  | 5,000 |  |  |  | 5,000
 | Execution of the development (meetings, validation, purchasing software) | 100,000 |  |  |  | 100,000 | 60,000 |  | 160,000
 | Conducting tests | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation of final product | 0 |  |  |  |  | 10,000 |  | 10,000
 | Workshop for training on the IS | 0 |  |  |  |  |  | 45,000 | 45,000
Verbatim from NBSAP
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 23: Example from Tuvalu NBSAP
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 305,000 | 30,000 | 60,000 | 65,000 | 150,000 | 173,000 | 45,000 | 523,000
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 200,000 | 30,000 | 60,000 | 60,000 | 50,000 | 83,000 | 0 | 283,000
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 190,000 | 30,000 | 60,000 | 50,000 | 50,000 | 80,000 | 0 | 270,000
 | Consultatory meeting for TOR | 30,000 | 30,000 |  |  |  |  |  | 30,000
 | Inception workshop | 60,000 |  | 60,000 |  |  |  |  | 60,000
 | Consultancy | 100,000 |  |  | 50,000 | 50,000 |  |  | 100,000
 | Review and testing | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation workshop | 0 |  |  |  |  | 60,000 |  | 60,000
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 10,000 | 0 | 0 | 10,000 | 0 | 3,000 | 0 | 13,000
 | Inception workshop (for 1.1.1) | 0 |  | 0 |  |  |  |  | 0
 | Research | 10,000 |  |  | 10,000 |  |  |  | 10,000
 | Validation workshop (for 1.1.1) | 0 |  |  |  | 0 |  |  | 0
 | Academic publication of assessment study | 0 |  |  |  |  | 3,000 |  | 3,000
 | . | 0 |  |  |  |  |  |  | 0
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
 | Elaboration of requirements( meetings) | 5,000 |  |  | 5,000 |  |  |  | 5,000
 | Execution of the development (meetings, validation, purchasing software) | 100,000 |  |  |  | 100,000 | 60,000 |  | 160,000
 | Conducting tests | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation of final product | 0 |  |  |  |  | 10,000 |  | 10,000
 | Workshop for training on the IS | 0 |  |  |  |  |  | 45,000 | 45,000
Work breakdown structure
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 24: Example from Tuvalu NBSAP
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 305,000 | 30,000 | 60,000 | 65,000 | 150,000 | 173,000 | 45,000 | 523,000
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 200,000 | 30,000 | 60,000 | 60,000 | 50,000 | 83,000 | 0 | 283,000
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 190,000 | 30,000 | 60,000 | 50,000 | 50,000 | 80,000 | 0 | 270,000
 | Consultatory meeting for TOR | 30,000 | 30,000 |  |  |  |  |  | 30,000
 | Inception workshop | 60,000 |  | 60,000 |  |  |  |  | 60,000
 | Consultancy | 100,000 |  |  | 50,000 | 50,000 |  |  | 100,000
 | Review and testing | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation workshop | 0 |  |  |  |  | 60,000 |  | 60,000
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 10,000 | 0 | 0 | 10,000 | 0 | 3,000 | 0 | 13,000
 | Inception workshop (for 1.1.1) | 0 |  | 0 |  |  |  |  | 0
 | Research | 10,000 |  |  | 10,000 |  |  |  | 10,000
 | Validation workshop (for 1.1.1) | 0 |  |  |  | 0 |  |  | 0
 | Academic publication of assessment study | 0 |  |  |  |  | 3,000 |  | 3,000
 | . | 0 |  |  |  |  |  |  | 0
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
 | Elaboration of requirements( meetings) | 5,000 |  |  | 5,000 |  |  |  | 5,000
 | Execution of the development (meetings, validation, purchasing software) | 100,000 |  |  |  | 100,000 | 60,000 |  | 160,000
 | Conducting tests | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation of final product | 0 |  |  |  |  | 10,000 |  | 10,000
 | Workshop for training on the IS | 0 |  |  |  |  |  | 45,000 | 45,000
Timing
(Gantt chart)
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 25: Example from Tuvalu NBSAP
 | Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters |  | 305,000 | 30,000 | 60,000 | 65,000 | 150,000 | 173,000 | 45,000 | 523,000
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity |  | 200,000 | 30,000 | 60,000 | 60,000 | 50,000 | 83,000 | 0 | 283,000
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity |  | 190,000 | 30,000 | 60,000 | 50,000 | 50,000 | 80,000 | 0 | 270,000
 | Consultatory meeting for TOR | 30,000 | 30,000 |  |  |  |  |  | 30,000
 | Inception workshop | 60,000 |  | 60,000 |  |  |  |  | 60,000
 | Consultancy | 100,000 |  |  | 50,000 | 50,000 |  |  | 100,000
 | Review and testing | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation workshop | 0 |  |  |  |  | 60,000 |  | 60,000
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation |  | 10,000 | 0 | 0 | 10,000 | 0 | 3,000 | 0 | 13,000
 | Inception workshop (for 1.1.1) | 0 |  | 0 |  |  |  |  | 0
 | Research | 10,000 |  |  | 10,000 |  |  |  | 10,000
 | Validation workshop (for 1.1.1) | 0 |  |  |  | 0 |  |  | 0
 | Academic publication of assessment study | 0 |  |  |  |  | 3,000 |  | 3,000
 | . | 0 |  |  |  |  |  |  | 0
Sub-program 1.2 Ensure meteorology and climate change information systems are relevant to biodiversity protection and conservation. |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
Action 1.2.1 Work closely with the Met Office to develop information systems that are relevant to biodiversity |  | 105,000 | 0 | 0 | 5,000 | 100,000 | 90,000 | 45,000 | 240,000
 | Elaboration of requirements( meetings) | 5,000 |  |  | 5,000 |  |  |  | 5,000
 | Execution of the development (meetings, validation, purchasing software) | 100,000 |  |  |  | 100,000 | 60,000 |  | 160,000
 | Conducting tests | 0 |  |  |  |  | 20,000 |  | 20,000
 | Validation of final product | 0 |  |  |  |  | 10,000 |  | 10,000
 | Workshop for training on the IS | 0 |  |  |  |  |  | 45,000 | 45,000
Rolling wave planning
(here: first year more detailed)
Notes: Decision tree methodology is also suggested to determine which expenditure require further research and assessment:

## Slide 26: Example (cont.): towards standard cost items
Sub-division of costs by categories |  |  |  |  |  | 
 | 2016 |  |  |  |  | 
Categories of expenses | Salary | Operating Exp | Transfert | Investissement | Total | Validation
Sum by Expenses | 75,000 | 150,000 | - | 80,000 | 305,000 | 
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters | 75,000 | 150,000 | 0 | 80,000 | 305,000 | -
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity | 55,000 | 145,000 | 0 | 0 | 200,000 | -
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity | 45,000 | 145,000 | - | - | 190,000 | -
Consultatory meeting for TOR | 5,000 | 25,000 |  |  | 30,000 | -
Inception workshop | 40,000 | 20,000 |  |  | 60,000 | -
Consultancy | - | 100,000 |  |  | 100,000 | -
Review and testing |  |  |  |  | - | -
Validation workshop |  |  |  |  | - | -
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation | 10,000 | - | - | - | 10,000 | -
Inception workshop (for 1.1.1) |  |  |  |  | - | -
Research | 10,000 |  |  |  | 10,000 | -
Validation workshop (for 1.1.1) |  |  |  |  | - | -
Academic publication of assessment study |  |  |  |  | - | -
. |  |  |  |  | - | -

## Slide 27: Example (cont.): towards standard expenditure categories
Sub-division of costs by categories |  |  |  |  |  | 
 | 2016 |  |  |  |  | 
Categories of expenses | Salary | Operating Exp | Transfert | Investissement | Total | Validation
Sum by Expenses | 75,000 | 150,000 | - | 80,000 | 305,000 | 
Program 1 Build resilience of biodiversity to manage, control and reduce the risks and impacts of climate change and natural disasters | 75,000 | 150,000 | 0 | 80,000 | 305,000 | -
Sub-program 1.1 Improve knowledge on the impact of climate change and natural disasters on biodiversity | 55,000 | 145,000 | 0 | 0 | 200,000 | -
Action 1.1.1 Conduct assessment of impacts of climate change and natural disasters on biodiversity | 45,000 | 145,000 | - | - | 190,000 | -
Consultatory meeting for TOR | 5,000 | 25,000 |  |  | 30,000 | -
Inception workshop | 40,000 | 20,000 |  |  | 60,000 | -
Consultancy | - | 100,000 |  |  | 100,000 | -
Review and testing |  |  |  |  | - | -
Validation workshop |  |  |  |  | - | -
Action 1.1.2 Raise awareness of meteorologists and climatologists on the linkages between climate information and biodiversity conservation | 10,000 | - | - | - | 10,000 | -
Inception workshop (for 1.1.1) |  |  |  |  | - | -
Research | 10,000 |  |  |  | 10,000 | -
Validation workshop (for 1.1.1) |  |  |  |  | - | -
Academic publication of assessment study |  |  |  |  | - | -
. |  |  |  |  | - | -
Standard expenditure categories

## Slide 28: Example (cont.): standard expenditure categories
Expenses by categories from 2016-2018 |  |  |  |  | 
Expenses by categories |  |  |  |  | 
Categories/years | 2016 | 2017 | 2018 | Total | %
Salary | 75,000 | 66,000 | 25,000 | 166,000 | 31.7%
Operating Exp | 150,000 | 47,000 | 20,000 | 217,000 | 41.5%
Transfert | - | - | - | - | 0.0%
Investissement | 80,000 | 60,000 | - | 140,000 | 26.8%
TOTAL expenses | 305,000 | 173,000 | 45,000 | 523,000 | 100.0%

## Slide 29: Example: towards a cost profile
Chart: 
| 2016 | 2017 | 2018
Salary | 75000 | 66000 | 25000
Operating Exp | 150000 | 47000 | 20000
Transfert | 0 | 0 | 0
Investissement | 80000 | 60000 | 0

## Slide 30
Thank you!

## Slide 31: Group work: I. defining the WBS
Define the WBS

## Slide 32: Group work: II. Establish the time profile

## Slide 33: Group work: III. Establish expenditures under standard categories