## Exp planification
Costing Exercise
| Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Enhance implementation of NBSAP through participatory planning, knowledge management and capacity building |  | 172000 | 5000 | 114000 | 12000 | 41000 | 77000 | 27000 | 276000
Sub-program 1.1 By 2022, ecosystems that provide essential services and contribute to health, livelihoods and well-being are safeguarded, and restoration programmes have been initiated for degraded ecosystems covering at least 15 per cent of the priority areas |  | 172000 | 5000 | 114000 | 12000 | 41000 | 77000 | 27000 | 276000
Action 1.1.1 Foster the implementation of integrated water management plans, including restoration and protection of critical wetlands systems |  | 172000 | 5000 | 114000 | 12000 | 41000 | 77000 | 27000 | 276000
| sensitization and mobilisation of communities around the wetland | 16000 | 4000 | 4000 | 4000 | 4000 | 10000 | 5000 | 31000
| procuerement of materials and recruitment of staff | 101000 | 1000 | 100000 |  |  |  |  | 101000
| Construction of soil and water conservation structures | 15000 |  |  |  | 15000 | 45000 | 10000 | 70000
| Reintroduction of species | 5000 |  |  |  | 5000 | 10000 | 10000 | 25000
| Removal of Invasive Species | 23000 |  | 10000 | 3000 | 10000 | 10000 |  | 33000
| Develop by laws on the use of the wetland | 10000 |  |  | 5000 | 5000 |  |  | 10000
| Monitoring and reporting of implementation | 2000 |  |  |  | 2000 | 2000 | 2000 | 6000

## Costs by categories
Sub-division of costs by categories
| 2016 |  |  |  |  | 2017 |  |  |  |  | 2018
Categories of expenses | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation
Sum by Expenses | 5000 | 86000 | 81000 | 172000 |  | 0 | 47000 | 30000 | 77000 |  | 0 | 27000 | 0 | 27000
Program 1 Enhance implementation of NBSAP through participatory planning, knowledge management and capacity building | 5000 | 86000 | 81000 | 172000 | 0 | 0 | 47000 | 30000 | 77000 | 0 | 0 | 27000 | 0 | 27000 | 0
Sub-program 1.1 By 2022, ecosystems that provide essential services and contribute to health, livelihoods and well-being are safeguarded, and restoration programmes have been initiated for degraded ecosystems covering at least 15 per cent of the priority areas | 5000 | 86000 | 81000 | 172000 | 0 | 0 | 47000 | 30000 | 77000 | 0 | 0 | 27000 | 0 | 27000 | 0
Action 1.1.1 Foster the implementation of integrated water management plans, including restoration and protection of critical wetlands systems | 5000 | 86000 | 81000 | 172000 | 0 | 0 | 47000 | 30000 | 77000 | 0 | 0 | 27000 | 0 | 27000 | 0
sensitization and mobilisation of communities around the wetland |  | 16000 |  | 16000 | 0 |  | 10000 |  | 10000 | 0 |  | 5000 |  | 5000 | 0
procuerement of materials and recruitment of staff |  | 20000 | 81000 | 101000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Construction of soil and water conservation structures |  | 15000 |  | 15000 | 0 |  | 15000 | 30000 | 45000 | 0 |  | 10000 |  | 10000 | 0
Reintroduction of species |  | 5000 |  | 5000 | 0 |  | 10000 |  | 10000 | 0 |  | 10000 |  | 10000 | 0
Removal of Invasive Species | 5000 | 18000 |  | 23000 | 0 |  | 10000 |  | 10000 | 0 |  |  |  | 0 | 0
Develop by laws on the use of the wetland |  | 10000 |  | 10000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Monitoring and reporting of implementation |  | 2000 |  | 2000 | 0 |  | 2000 |  | 2000 | 0 |  | 2000 |  | 2000 | 0

## Chart
2 | Expenses by categories from 2016-2018
Expenses by categories
| Categories/years | 2016 | 2017 | 2018 | Total | %
| Salary | 5000 | 0 | 0 | 5000 | 1.812%
| Operating Exp | 86000 | 47000 | 27000 | 160000 | 57.97%
| Investment | 81000 | 30000 | 0 | 111000 | 40.22%
| TOTAL expenses | 172000 | 77000 | 27000 | 276000 | 100%