## Exp planification
Costing Exercise
| Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Enhance implementation of NBSAP through participatory planning, knowledge management and capacity building |  | 388000 | 77000 | 127000 | 97000 | 87000 | 219000 | 219000 | 826000
Sub-program 1.1 By 2022, ecosystems that provide essential services and contribute to health, livelihoods and well-being are safeguarded, and restoration programmes have been initiated for degraded ecosystems covering at least 15 per cent of the priority areas |  | 388000 | 77000 | 127000 | 97000 | 87000 | 219000 | 219000 | 826000
Action 1.1.1 Foster the implementation of integrated water management plans, including restoration and protection of critical wetlands systems |  | 388000 | 77000 | 127000 | 97000 | 87000 | 219000 | 219000 | 826000
| Activity1 - Hold community meetings to raise awareness on water and wetland management plans | 48000 | 12000 | 12000 | 12000 | 12000 | 24000 | 24000 | 96000
| Activity2- Develop water and wetland management plans | 45000 | 30000 | 15000 |  |  |  |  | 45000
| Activity3- Training on value of wetland and water resources management | 50000 | 25000 |  | 25000 |  |  |  | 50000
| Activity4- Restoration of degraded areas | 125000 |  | 75000 | 50000 |  | 125000 | 125000 | 375000
| Activity5- Valuation of wetlands | 50000 |  |  |  | 50000 |  |  | 50000
| Activity6- Implement wetland and water resources management plan bylaws | 30000 |  | 15000 |  | 15000 | 30000 | 30000 | 90000
| Activity7- Monitoring, Reporting and Evaluation of progress | 40000 | 10000 | 10000 | 10000 | 10000 | 40000 | 40000 | 120000

## Costs by categories
Sub-division of costs by categories
| 2016 |  |  |  |  | 2017 |  |  |  |  | 2018
Categories of expenses | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation
Sum by Expenses | 107000 | 176000 | 105000 | 388000 |  | 47000 | 67000 | 105000 | 219000 |  | 47000 | 67000 | 105000 | 219000
Program 1 Enhance implementation of NBSAP through participatory planning, knowledge management and capacity building | 107000 | 176000 | 105000 | 388000 | 0 | 47000 | 67000 | 105000 | 219000 | 0 | 47000 | 67000 | 105000 | 219000 | 0
Sub-program 1.1 By 2022, ecosystems that provide essential services and contribute to health, livelihoods and well-being are safeguarded, and restoration programmes have been initiated for degraded ecosystems covering at least 15 per cent of the priority areas | 107000 | 176000 | 105000 | 388000 | 0 | 47000 | 67000 | 105000 | 219000 | 0 | 47000 | 67000 | 105000 | 219000 | 0
Action 1.1.1 Foster the implementation of integrated water management plans, including restoration and protection of critical wetlands systems | 107000 | 176000 | 105000 | 388000 | 0 | 47000 | 67000 | 105000 | 219000 | 0 | 47000 | 67000 | 105000 | 219000 | 0
Activity1 - Hold community meetings to raise awareness on water and wetland management plans | 12000 | 36000 |  | 48000 | 0 | 12000 | 12000 |  | 24000 | 0 | 12000 | 12000 |  | 24000 | 0
Activity2- Develop water and wetland management plans | 15000 | 30000 |  | 45000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Activity3- Training on value of wetland and water resources management | 20000 | 30000 |  | 50000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Activity4- Restoration of degraded areas | 10000 | 10000 | 105000 | 125000 | 0 | 10000 | 10000 | 105000 | 125000 | 0 | 10000 | 10000 | 105000 | 125000 | 0
Activity5- Valuation of wetlands | 25000 | 25000 |  | 50000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Activity6- Implement wetland and water resources management plan bylaws | 5000 | 25000 |  | 30000 | 0 | 10000 | 20000 |  | 30000 | 0 | 10000 | 20000 |  | 30000 | 0
Activity7- Monitoring, Reporting and Evaluation of progress | 20000 | 20000 |  | 40000 | 0 | 15000 | 25000 |  | 40000 | 0 | 15000 | 25000 |  | 40000 | 0

## Chart
2 | Expenses by categories from 2016-2018
Expenses by categories
| Categories/years | 2016 | 2017 | 2018 | Total | %
| Salary | 107000 | 47000 | 47000 | 201000 | 24.33%
| Operating Exp | 176000 | 67000 | 67000 | 310000 | 37.53%
| Investment | 105000 | 105000 | 105000 | 315000 | 38.14%
| TOTAL expenses | 388000 | 219000 | 219000 | 826000 | 100%