## Exp planification
Costing Exercise
| Activity structure | 2016 | Q1 | Q2 | Q3 | Q4 | 2017 | 2018 | Total 2016-2018
Program 1 Reduce the pressure on biodiversity to ensure sustainable development |  | 405000 | 30000 | 100000 | 130000 | 145000 | 120000 | 105000 | 630000
Sub-program 1.1 Ensure the conservation of rare, vulnerable and endangered species |  | 400000 | 30000 | 100000 | 130000 | 140000 | 55000 | 90000 | 545000
Action 1.1.1 Restore natural habitats of endangered species populations |  | 290000 | 30000 | 60000 | 100000 | 100000 | 50000 | 90000 | 430000
| Consultatory meeting for TOR | 30000 | 30000 | [5 empty] | 30000
| Inception workshop about the conservation | 60000 |  | 60000 |  |  |  |  | 60000
| Execution of the development | 200000 |  |  | 100000 | 100000 | 30000 |  | 230000
| Follow up on the execution | 0 |  |  |  |  | 20000 | 10000 | 30000
| Maintain the conservation | 0 | [5 empty] | 80000 | 80000
Action 1.1.2 Develop management plans for ecosystems and plant and animal species of community interest |  | 110000 | 0 | 40000 | 30000 | 40000 | 5000 | 0 | 115000
| Elaboration of requirements (meetings) | 40000 |  | 40000 |  |  |  |  | 40000
| Research | 30000 |  |  | 30000 |  |  |  | 30000
| Validation workshop | 40000 |  |  |  | 40000 |  |  | 40000
| Finalization and distribution | 0 |  |  |  |  | 5000 |  | 5000
| . | 0 | [6 empty] | 0
Sub-program 1.2 Implement biological safety measures |  | 5000 | 0 | 0 | 0 | 5000 | 65000 | 15000 | 85000
Action 1.2.1 Implement the National Framework on Biological Safety in accordance with the provisions of the Cartagena Protocol |  | 5000 | 0 | 0 | 0 | 5000 | 65000 | 15000 | 85000
| Inception workshop about the planning | 5000 |  |  |  | 5000 |  |  | 5000
| Development of the implementation plan | 0 |  |  |  |  | 30000 |  | 30000
| Implementation | 0 |  |  |  |  | 10000 |  | 10000
| Analyze and follow up on the implementation | 0 |  |  |  |  | 25000 | 15000 | 40000
|  | 0 | [6 empty] | 0

## Costs by categories
Sub-division of costs by categories
| 2016 |  |  |  |  | 2017 |  |  |  |  | 2018
Categories of expenses | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation | Salary | Operating Exp | Investment | Total | Validation
Sum by Expenses | 135000 | 170000 | 100000 | 405000 |  | 63000 | 27000 | 30000 | 120000 |  | 75000 | 30000 | 0 | 105000
Program 1 Reduce the pressure on biodiversity to ensure sustainable development | 135000 | 170000 | 100000 | 405000 | 0 | 63000 | 27000 | 30000 | 120000 | 0 | 75000 | 30000 | 0 | 105000 | 0
Sub-program 1.1 Ensure the conservation of rare, vulnerable and endangered species | 130000 | 170000 | 100000 | 400000 | 0 | 15000 | 10000 | 30000 | 55000 | 0 | 60000 | 30000 | 0 | 90000 | 0
Action 1.1.1 Restore natural habitats of endangered species populations | 60000 | 130000 | 100000 | 290000 | 0 | 10000 | 10000 | 30000 | 50000 | 0 | 60000 | 30000 | 0 | 90000 | 0
Consultatory meeting for TOR | 20000 | 10000 |  | 30000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Inception workshop about the conservation | 40000 | 20000 |  | 60000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Execution of the development | 0 | 100000 | 100000 | 200000 | 0 |  |  | 30000 | 30000 | 0 |  |  |  | 0 | 0
Follow up on the execution |  |  |  | 0 | 0 | 10000 | 10000 |  | 20000 | 0 | 10000 |  |  | 10000 | 0
Maintain the conservation |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 50000 | 30000 |  | 80000 | 0
Action 1.1.2 Develop management plans for ecosystems and plant and animal species of community interest | 70000 | 40000 | 0 | 110000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0
Elaboration of requirements (meetings) | 30000 | 10000 |  | 40000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Research | 20000 | 10000 |  | 30000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Validation workshop | 20000 | 20000 |  | 40000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Finalization and distribution |  |  |  | 0 | 0 | 5000 |  |  | 5000 | 0 |  |  |  | 0 | 0
. |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Sub-program 1.2 Implement biological safety measures | 5000 | 0 | 0 | 5000 | 0 | 48000 | 17000 | 0 | 65000 | 0 | 15000 | 0 | 0 | 15000 | 0
Action 1.2.1 Implement the National Framework on Biological Safety in accordance with the provisions of the Cartagena Protocol | 5000 | 0 | 0 | 5000 | 0 | 48000 | 17000 | 0 | 65000 | 0 | 15000 | 0 | 0 | 15000 | 0
Inception workshop about the planning | 5000 |  |  | 5000 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
Development of the implementation plan |  |  |  | 0 | 0 | 25000 | 5000 |  | 30000 | 0 |  |  |  | 0 | 0
Implementation |  |  |  | 0 | 0 | 8000 | 2000 |  | 10000 | 0 |  |  |  | 0 | 0
Analyze and follow up on the implementation |  |  |  | 0 | 0 | 15000 | 10000 |  | 25000 | 0 | 15000 |  |  | 15000 | 0
0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0

## Chart
2 | Expenses by categories from 2016-2018
Expenses by categories
| Categories/years | 2016 | 2017 | 2018 | Total | %
| Salary | 135000 | 63000 | 75000 | 273000 | 43.33%
| Operating Exp | 170000 | 27000 | 30000 | 227000 | 36.03%
| Investissement | 100000 | 30000 | 0 | 130000 | 20.63%
| TOTAL expenses | 405000 | 120000 | 105000 | 630000 | 100%